## Sheet1
rsrc_id | task_id | TASK__status_code | role_id | acct_id | rsrc_type | target_qty | act_qty | remain_qty | user_field_130 | delete_record_flag
OCB EQP -18 | EX SR A-13.060 | In Progress |  |  | Nonlabor |  |  |  | 3.1.2.4
OCB EQP -13 | EX SR A-13.070 | In Progress |  |  | Nonlabor |  |  |  | 3.1.2.2
OCB EQP -14 | EX SR A-13.070 | In Progress |  |  | Nonlabor |  |  |  | 3.1.2.2
OCB EQP -18 | EX SR A-13.080 | In Progress |  |  | Nonlabor |  |  |  | 3.1.2.5
OCB EQP -13 | EX SR A-13.090 | In Progress |  |  | Nonlabor |  |  |  | 3.1.2.3
OCB EQP -14 | EX SR A-13.090 | In Progress |  |  | Nonlabor |  |  |  | 3.1.2.3
OCB EQP -11 | EXE CGD 1030 | In Progress |  |  | Nonlabor |  |  |  | 3.2.1.3
OCB EQP -11 | EXE CGD 1040 | In Progress |  |  | Nonlabor |  |  |  | 3.2.1.4
OCB EQP -17 | EXE TXY P A-01.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -16 | EXE TXY P A-01.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -19 | EXE TXY P A-01.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -18 | EXE TXY P A-01.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -15 | EXE TXY P A-01.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -17 | EXE TXY P A-01.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -19 | EXE TXY P A-01.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -18 | EXE TXY P A-01.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -15 | EXE TXY P A-01.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -9 | EXE TXY P A-01.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -5 | EXE TXY P A-01.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -13 | EXE TXY P A-01.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -14 | EXE TXY P A-01.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -15 | EXE TXY P A-01.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -6 | EXE TXY P A-01.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -9 | EXE TXY P A-01.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -5 | EXE TXY P A-01.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -13 | EXE TXY P A-01.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -14 | EXE TXY P A-01.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -15 | EXE TXY P A-01.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -6 | EXE TXY P A-01.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -3 | EXE TXY P A-01.190 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -9 | EXE TXY P A-01.190 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -12 | EXE TXY P A-01.190 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -8 | EXE TXY P A-01.190 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -4 | EXE TXY P A-01.190 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -18 | EXE TXY P A-02.070 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.4
OCB EQP -18 | EXE TXY P A-02.130 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.5
OCB EQP -13 | EXE TXY P A-02.080 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -14 | EXE TXY P A-02.080 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -18 | EXE TXY P A-02.150 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.6
OCB EQP -13 | EXE TXY P A-02.140 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.3
OCB EQP -14 | EXE TXY P A-02.140 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.3
OCB EQP -17 | EXE TXY P A-02.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -16 | EXE TXY P A-02.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -19 | EXE TXY P A-02.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -18 | EXE TXY P A-02.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -15 | EXE TXY P A-02.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -17 | EXE TXY P A-02.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -19 | EXE TXY P A-02.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -18 | EXE TXY P A-02.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -15 | EXE TXY P A-02.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -9 | EXE TXY P A-02.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -5 | EXE TXY P A-02.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -13 | EXE TXY P A-02.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -14 | EXE TXY P A-02.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -15 | EXE TXY P A-02.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -6 | EXE TXY P A-02.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -9 | EXE TXY P A-02.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -5 | EXE TXY P A-02.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -13 | EXE TXY P A-02.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -14 | EXE TXY P A-02.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -15 | EXE TXY P A-02.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -6 | EXE TXY P A-02.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -3 | EXE TXY P A-02.190 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -9 | EXE TXY P A-02.190 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -12 | EXE TXY P A-02.190 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -8 | EXE TXY P A-02.190 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -4 | EXE TXY P A-02.190 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -18 | EXE TXY P A-03.070 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.4
OCB EQP -18 | EXE TXY P A-03.130 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.5
OCB EQP -13 | EXE TXY P A-03.080 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -14 | EXE TXY P A-03.080 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -18 | EXE TXY P A-03.090 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.6
OCB EQP -13 | EXE TXY P A-03.140 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.3
OCB EQP -14 | EXE TXY P A-03.140 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.3
OCB EQP -17 | EXE TXY P A-03.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -16 | EXE TXY P A-03.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -19 | EXE TXY P A-03.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -18 | EXE TXY P A-03.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -15 | EXE TXY P A-03.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -17 | EXE TXY P A-03.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -19 | EXE TXY P A-03.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -18 | EXE TXY P A-03.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -15 | EXE TXY P A-03.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -9 | EXE TXY P A-03.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -5 | EXE TXY P A-03.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -13 | EXE TXY P A-03.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -14 | EXE TXY P A-03.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -15 | EXE TXY P A-03.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -6 | EXE TXY P A-03.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -9 | EXE TXY P A-03.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -5 | EXE TXY P A-03.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -13 | EXE TXY P A-03.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -14 | EXE TXY P A-03.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -15 | EXE TXY P A-03.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -6 | EXE TXY P A-03.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -3 | EXE TXY P A-03.190 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -9 | EXE TXY P A-03.190 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -12 | EXE TXY P A-03.190 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -8 | EXE TXY P A-03.190 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -4 | EXE TXY P A-03.190 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -18 | EXE TXY P A-04.070 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.4
OCB EQP -18 | EXE TXY P A-04.130 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.5
OCB EQP -13 | EXE TXY P A-04.080 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -14 | EXE TXY P A-04.080 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -18 | EXE TXY P A-04.090 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.6
OCB EQP -13 | EXE TXY P A-04.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.3
OCB EQP -14 | EXE TXY P A-04.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.3
OCB EQP -17 | EXE TXY P A-04.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -16 | EXE TXY P A-04.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -19 | EXE TXY P A-04.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -18 | EXE TXY P A-04.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -15 | EXE TXY P A-04.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -17 | EXE TXY P A-04.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -19 | EXE TXY P A-04.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -18 | EXE TXY P A-04.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -15 | EXE TXY P A-04.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -9 | EXE TXY P A-04.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -5 | EXE TXY P A-04.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -13 | EXE TXY P A-04.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -14 | EXE TXY P A-04.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -15 | EXE TXY P A-04.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -6 | EXE TXY P A-04.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -9 | EXE TXY P A-04.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -5 | EXE TXY P A-04.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -13 | EXE TXY P A-04.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -14 | EXE TXY P A-04.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -15 | EXE TXY P A-04.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -6 | EXE TXY P A-04.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -17 | EX NOTM TX A-09L.070 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.4
OCB EQP -16 | EX NOTM TX A-09L.070 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.4
OCB EQP -19 | EX NOTM TX A-09L.070 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.4
OCB EQP -18 | EX NOTM TX A-09L.070 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.4
OCB EQP -15 | EX NOTM TX A-09L.070 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.4
OCB EQP -17 | EX NOTM TX A-09L.130 | Not Started |  |  | Nonlabor |  |  |  | 3.2.6.5
OCB EQP -19 | EX NOTM TX A-09L.130 | Not Started |  |  | Nonlabor |  |  |  | 3.2.6.5
OCB EQP -18 | EX NOTM TX A-09L.130 | Not Started |  |  | Nonlabor |  |  |  | 3.2.6.5
OCB EQP -15 | EX NOTM TX A-09L.130 | Not Started |  |  | Nonlabor |  |  |  | 3.2.6.5
OCB EQP -9 | EX NOTM TX A-09L.080 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.2
OCB EQP -5 | EX NOTM TX A-09L.080 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.2
OCB EQP -13 | EX NOTM TX A-09L.080 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.2
OCB EQP -14 | EX NOTM TX A-09L.080 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.2
OCB EQP -15 | EX NOTM TX A-09L.080 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.2
OCB EQP -6 | EX NOTM TX A-09L.080 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.2
OCB EQP -17 | EX NOTM TX A-09L.090 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.6
OCB EQP -19 | EX NOTM TX A-09L.090 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.6
OCB EQP -18 | EX NOTM TX A-09L.090 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.6
OCB EQP -15 | EX NOTM TX A-09L.090 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.6
OCB EQP -9 | EX NOTM TX A-09L.140 | Not Started |  |  | Nonlabor |  |  |  | 3.2.6.3
OCB EQP -5 | EX NOTM TX A-09L.140 | Not Started |  |  | Nonlabor |  |  |  | 3.2.6.3
OCB EQP -13 | EX NOTM TX A-09L.140 | Not Started |  |  | Nonlabor |  |  |  | 3.2.6.3
OCB EQP -14 | EX NOTM TX A-09L.140 | Not Started |  |  | Nonlabor |  |  |  | 3.2.6.3
OCB EQP -15 | EX NOTM TX A-09L.140 | Not Started |  |  | Nonlabor |  |  |  | 3.2.6.3
OCB EQP -6 | EX NOTM TX A-09L.140 | Not Started |  |  | Nonlabor |  |  |  | 3.2.6.3
OCB EQP -3 | EX NOTM TX A-09L.060 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.1
OCB EQP -9 | EX NOTM TX A-09L.060 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.1
OCB EQP -12 | EX NOTM TX A-09L.060 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.1
OCB EQP -8 | EX NOTM TX A-09L.060 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.1
OCB EQP -4 | EX NOTM TX A-09L.060 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.1
OCB EQP -17 | EX NOTM TX A-10K.070 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.4
OCB EQP -16 | EX NOTM TX A-10K.070 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.4
OCB EQP -19 | EX NOTM TX A-10K.070 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.4
OCB EQP -18 | EX NOTM TX A-10K.070 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.4
OCB EQP -15 | EX NOTM TX A-10K.070 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.4
OCB EQP -17 | EX NOTM TX A-10K.130 | Not Started |  |  | Nonlabor |  |  |  | 3.2.5.5
OCB EQP -19 | EX NOTM TX A-10K.130 | Not Started |  |  | Nonlabor |  |  |  | 3.2.5.5
OCB EQP -18 | EX NOTM TX A-10K.130 | Not Started |  |  | Nonlabor |  |  |  | 3.2.5.5
OCB EQP -15 | EX NOTM TX A-10K.130 | Not Started |  |  | Nonlabor |  |  |  | 3.2.5.5
OCB EQP -9 | EX NOTM TX A-10K.080 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.2
OCB EQP -5 | EX NOTM TX A-10K.080 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.2
OCB EQP -13 | EX NOTM TX A-10K.080 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.2
OCB EQP -14 | EX NOTM TX A-10K.080 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.2
OCB EQP -15 | EX NOTM TX A-10K.080 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.2
OCB EQP -6 | EX NOTM TX A-10K.080 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.2
OCB EQP -17 | EX NOTM TX A-10K.090 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.6
OCB EQP -19 | EX NOTM TX A-10K.090 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.6
OCB EQP -18 | EX NOTM TX A-10K.090 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.6
OCB EQP -15 | EX NOTM TX A-10K.090 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.6
OCB EQP -9 | EX NOTM TX A-10K.140 | Not Started |  |  | Nonlabor |  |  |  | 3.2.5.3
OCB EQP -5 | EX NOTM TX A-10K.140 | Not Started |  |  | Nonlabor |  |  |  | 3.2.5.3
OCB EQP -13 | EX NOTM TX A-10K.140 | Not Started |  |  | Nonlabor |  |  |  | 3.2.5.3
OCB EQP -14 | EX NOTM TX A-10K.140 | Not Started |  |  | Nonlabor |  |  |  | 3.2.5.3
OCB EQP -15 | EX NOTM TX A-10K.140 | Not Started |  |  | Nonlabor |  |  |  | 3.2.5.3
OCB EQP -6 | EX NOTM TX A-10K.140 | Not Started |  |  | Nonlabor |  |  |  | 3.2.5.3
OCB EQP -3 | EX NOTM TX A-10K.060 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.1
OCB EQP -9 | EX NOTM TX A-10K.060 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.1
OCB EQP -12 | EX NOTM TX A-10K.060 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.1
OCB EQP -8 | EX NOTM TX A-10K.060 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.1
OCB EQP -4 | EX NOTM TX A-10K.060 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.1
OCB EQP -17 | EX NOTM TX A-09L.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -16 | EX NOTM TX A-09L.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -19 | EX NOTM TX A-09L.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -18 | EX NOTM TX A-09L.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -15 | EX NOTM TX A-09L.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -17 | EX NOTM TX A-09L.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -19 | EX NOTM TX A-09L.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -18 | EX NOTM TX A-09L.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -15 | EX NOTM TX A-09L.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -9 | EX NOTM TX A-09L.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -5 | EX NOTM TX A-09L.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -13 | EX NOTM TX A-09L.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -14 | EX NOTM TX A-09L.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -15 | EX NOTM TX A-09L.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -6 | EX NOTM TX A-09L.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -9 | EX NOTM TX A-09L.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -5 | EX NOTM TX A-09L.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -13 | EX NOTM TX A-09L.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -14 | EX NOTM TX A-09L.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -15 | EX NOTM TX A-09L.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -6 | EX NOTM TX A-09L.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -3 | EX NOTM TX A-09L.190 | Completed |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -9 | EX NOTM TX A-09L.190 | Completed |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -12 | EX NOTM TX A-09L.190 | Completed |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -8 | EX NOTM TX A-09L.190 | Completed |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -4 | EX NOTM TX A-09L.190 | Completed |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -17 | EX NOTM TX A-10K.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -16 | EX NOTM TX A-10K.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -19 | EX NOTM TX A-10K.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -18 | EX NOTM TX A-10K.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -15 | EX NOTM TX A-10K.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -17 | EX NOTM TX A-10K.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -19 | EX NOTM TX A-10K.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -18 | EX NOTM TX A-10K.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -15 | EX NOTM TX A-10K.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -9 | EX NOTM TX A-10K.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -5 | EX NOTM TX A-10K.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -13 | EX NOTM TX A-10K.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -14 | EX NOTM TX A-10K.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -15 | EX NOTM TX A-10K.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -6 | EX NOTM TX A-10K.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -9 | EX NOTM TX A-10K.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -5 | EX NOTM TX A-10K.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -13 | EX NOTM TX A-10K.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -14 | EX NOTM TX A-10K.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -15 | EX NOTM TX A-10K.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -6 | EX NOTM TX A-10K.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -3 | EX NOTM TX A-10K.190 | Completed |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -9 | EX NOTM TX A-10K.190 | Completed |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -12 | EX NOTM TX A-10K.190 | Completed |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -8 | EX NOTM TX A-10K.190 | Completed |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -4 | EX NOTM TX A-10K.190 | Completed |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -17 | EX NOTM TX A-11E.080 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.4
OCB EQP -16 | EX NOTM TX A-11E.080 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.4
OCB EQP -19 | EX NOTM TX A-11E.080 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.4
OCB EQP -18 | EX NOTM TX A-11E.080 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.4
OCB EQP -15 | EX NOTM TX A-11E.080 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.4
OCB EQP -17 | EX NOTM TX A-11E.150 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.5
OCB EQP -19 | EX NOTM TX A-11E.150 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.5
OCB EQP -18 | EX NOTM TX A-11E.150 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.5
OCB EQP -15 | EX NOTM TX A-11E.150 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.5
OCB EQP -9 | EX NOTM TX A-11E.090 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.2
OCB EQP -5 | EX NOTM TX A-11E.090 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.2
OCB EQP -13 | EX NOTM TX A-11E.090 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.2
OCB EQP -14 | EX NOTM TX A-11E.090 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.2
OCB EQP -15 | EX NOTM TX A-11E.090 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.2
OCB EQP -6 | EX NOTM TX A-11E.090 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.2
OCB EQP -17 | EX NOTM TX A-11E.100 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.6
OCB EQP -19 | EX NOTM TX A-11E.100 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.6
OCB EQP -18 | EX NOTM TX A-11E.100 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.6
OCB EQP -15 | EX NOTM TX A-11E.100 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.6
OCB EQP -9 | EX NOTM TX A-11E.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.3
OCB EQP -5 | EX NOTM TX A-11E.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.3
OCB EQP -13 | EX NOTM TX A-11E.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.3
OCB EQP -14 | EX NOTM TX A-11E.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.3
OCB EQP -15 | EX NOTM TX A-11E.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.3
OCB EQP -6 | EX NOTM TX A-11E.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.3
OCB EQP -3 | EX NOTM TX A-11E.070 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.1
OCB EQP -9 | EX NOTM TX A-11E.070 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.1
OCB EQP -12 | EX NOTM TX A-11E.070 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.1
OCB EQP -8 | EX NOTM TX A-11E.070 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.1
OCB EQP -4 | EX NOTM TX A-11E.070 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.1
OCB EQP -17 | EX NOTM TX A-11E.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -16 | EX NOTM TX A-11E.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -19 | EX NOTM TX A-11E.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -18 | EX NOTM TX A-11E.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -15 | EX NOTM TX A-11E.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -17 | EX NOTM TX A-11E.240 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -19 | EX NOTM TX A-11E.240 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -18 | EX NOTM TX A-11E.240 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -15 | EX NOTM TX A-11E.240 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -9 | EX NOTM TX A-11E.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -5 | EX NOTM TX A-11E.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -13 | EX NOTM TX A-11E.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -14 | EX NOTM TX A-11E.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -15 | EX NOTM TX A-11E.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -6 | EX NOTM TX A-11E.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -9 | EX NOTM TX A-11E.250 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -5 | EX NOTM TX A-11E.250 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -13 | EX NOTM TX A-11E.250 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -14 | EX NOTM TX A-11E.250 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -15 | EX NOTM TX A-11E.250 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -6 | EX NOTM TX A-11E.250 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -3 | EX NOTM TX A-11E.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -9 | EX NOTM TX A-11E.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -12 | EX NOTM TX A-11E.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -8 | EX NOTM TX A-11E.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -4 | EX NOTM TX A-11E.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -13 | EXE TXY P A-02.100 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -14 | EXE TXY P A-02.100 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -13 | EXE TXY P A-02.120 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -14 | EXE TXY P A-02.120 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -13 | EXE TXY P A-02.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.3
OCB EQP -14 | EXE TXY P A-02.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.3
OCB EQP -18 | EXE TXY P A-02.090 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.6
OCB EQP -18 | EXE TXY P A-02.110 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.6
OCB EQP -13 | EXE TXY P A-03.100 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -14 | EXE TXY P A-03.100 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -13 | EXE TXY P A-03.120 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -14 | EXE TXY P A-03.120 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -18 | EXE TXY P A-03.110 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.6
OCB EQP -18 | EXE TXY P A-03.150 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.6
OCB EQP -13 | EXE TXY P A-03.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.3
OCB EQP -14 | EXE TXY P A-03.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.3
OCB EQP -13 | EXE TXY P A-04.100 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -14 | EXE TXY P A-04.100 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -13 | EXE TXY P A-04.120 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -14 | EXE TXY P A-04.120 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -13 | EXE TXY P A-04.140 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.3
OCB EQP -14 | EXE TXY P A-04.140 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.3
OCB EQP -18 | EXE TXY P A-04.110 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.6
OCB EQP -18 | EXE TXY P A-04.150 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.6
OCB EQP -3 | EXE TXY P A-04.190 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -9 | EXE TXY P A-04.190 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -12 | EXE TXY P A-04.190 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -8 | EXE TXY P A-04.190 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -4 | EXE TXY P A-04.190 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -9 | EX NOTM TX A-09L.100 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.2
OCB EQP -5 | EX NOTM TX A-09L.100 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.2
OCB EQP -13 | EX NOTM TX A-09L.100 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.2
OCB EQP -14 | EX NOTM TX A-09L.100 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.2
OCB EQP -15 | EX NOTM TX A-09L.100 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.2
OCB EQP -6 | EX NOTM TX A-09L.100 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.2
OCB EQP -9 | EX NOTM TX A-09L.120 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.2
OCB EQP -5 | EX NOTM TX A-09L.120 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.2
OCB EQP -13 | EX NOTM TX A-09L.120 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.2
OCB EQP -14 | EX NOTM TX A-09L.120 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.2
OCB EQP -15 | EX NOTM TX A-09L.120 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.2
OCB EQP -6 | EX NOTM TX A-09L.120 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.2
OCB EQP -9 | EX NOTM TX A-09L.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.6.3
OCB EQP -5 | EX NOTM TX A-09L.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.6.3
OCB EQP -13 | EX NOTM TX A-09L.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.6.3
OCB EQP -14 | EX NOTM TX A-09L.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.6.3
OCB EQP -15 | EX NOTM TX A-09L.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.6.3
OCB EQP -6 | EX NOTM TX A-09L.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.6.3
OCB EQP -17 | EX NOTM TX A-09L.110 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.6
OCB EQP -19 | EX NOTM TX A-09L.110 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.6
OCB EQP -18 | EX NOTM TX A-09L.110 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.6
OCB EQP -15 | EX NOTM TX A-09L.110 | Completed |  |  | Nonlabor |  |  |  | 3.2.6.6
OCB EQP -17 | EX NOTM TX A-09L.150 | Not Started |  |  | Nonlabor |  |  |  | 3.2.6.6
OCB EQP -19 | EX NOTM TX A-09L.150 | Not Started |  |  | Nonlabor |  |  |  | 3.2.6.6
OCB EQP -18 | EX NOTM TX A-09L.150 | Not Started |  |  | Nonlabor |  |  |  | 3.2.6.6
OCB EQP -15 | EX NOTM TX A-09L.150 | Not Started |  |  | Nonlabor |  |  |  | 3.2.6.6
OCB EQP -9 | EX NOTM TX A-10K.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.5.3
OCB EQP -5 | EX NOTM TX A-10K.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.5.3
OCB EQP -13 | EX NOTM TX A-10K.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.5.3
OCB EQP -14 | EX NOTM TX A-10K.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.5.3
OCB EQP -15 | EX NOTM TX A-10K.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.5.3
OCB EQP -6 | EX NOTM TX A-10K.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.5.3
OCB EQP -9 | EX NOTM TX A-10K.100 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.2
OCB EQP -5 | EX NOTM TX A-10K.100 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.2
OCB EQP -13 | EX NOTM TX A-10K.100 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.2
OCB EQP -14 | EX NOTM TX A-10K.100 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.2
OCB EQP -15 | EX NOTM TX A-10K.100 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.2
OCB EQP -6 | EX NOTM TX A-10K.100 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.2
OCB EQP -9 | EX NOTM TX A-10K.120 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.2
OCB EQP -5 | EX NOTM TX A-10K.120 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.2
OCB EQP -13 | EX NOTM TX A-10K.120 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.2
OCB EQP -14 | EX NOTM TX A-10K.120 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.2
OCB EQP -15 | EX NOTM TX A-10K.120 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.2
OCB EQP -6 | EX NOTM TX A-10K.120 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.2
OCB EQP -17 | EX NOTM TX A-10K.110 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.6
OCB EQP -19 | EX NOTM TX A-10K.110 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.6
OCB EQP -18 | EX NOTM TX A-10K.110 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.6
OCB EQP -15 | EX NOTM TX A-10K.110 | Completed |  |  | Nonlabor |  |  |  | 3.2.5.6
OCB EQP -17 | EX NOTM TX A-10K.150 | Not Started |  |  | Nonlabor |  |  |  | 3.2.5.6
OCB EQP -19 | EX NOTM TX A-10K.150 | Not Started |  |  | Nonlabor |  |  |  | 3.2.5.6
OCB EQP -18 | EX NOTM TX A-10K.150 | Not Started |  |  | Nonlabor |  |  |  | 3.2.5.6
OCB EQP -15 | EX NOTM TX A-10K.150 | Not Started |  |  | Nonlabor |  |  |  | 3.2.5.6
OCB EQP -9 | EX NOTM TX A-11E.180 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.3
OCB EQP -5 | EX NOTM TX A-11E.180 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.3
OCB EQP -13 | EX NOTM TX A-11E.180 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.3
OCB EQP -14 | EX NOTM TX A-11E.180 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.3
OCB EQP -15 | EX NOTM TX A-11E.180 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.3
OCB EQP -6 | EX NOTM TX A-11E.180 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.3
OCB EQP -9 | EX NOTM TX A-11E.110 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.2
OCB EQP -5 | EX NOTM TX A-11E.110 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.2
OCB EQP -13 | EX NOTM TX A-11E.110 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.2
OCB EQP -14 | EX NOTM TX A-11E.110 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.2
OCB EQP -15 | EX NOTM TX A-11E.110 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.2
OCB EQP -6 | EX NOTM TX A-11E.110 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.2
OCB EQP -9 | EX NOTM TX A-11E.130 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.2
OCB EQP -5 | EX NOTM TX A-11E.130 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.2
OCB EQP -13 | EX NOTM TX A-11E.130 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.2
OCB EQP -14 | EX NOTM TX A-11E.130 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.2
OCB EQP -15 | EX NOTM TX A-11E.130 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.2
OCB EQP -6 | EX NOTM TX A-11E.130 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.2
OCB EQP -17 | EX NOTM TX A-11E.120 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.6
OCB EQP -19 | EX NOTM TX A-11E.120 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.6
OCB EQP -18 | EX NOTM TX A-11E.120 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.6
OCB EQP -15 | EX NOTM TX A-11E.120 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.6
OCB EQP -17 | EX NOTM TX A-11E.170 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.6
OCB EQP -19 | EX NOTM TX A-11E.170 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.6
OCB EQP -18 | EX NOTM TX A-11E.170 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.6
OCB EQP -15 | EX NOTM TX A-11E.170 | Not Started |  |  | Nonlabor |  |  |  | 3.2.4.6
OCB EQP -18 | NOTM TX-New A-12.070 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.4
OCB EQP -18 | NOTM TX-New A-12.130 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.5
OCB EQP -13 | NOTM TX-New A-12.080 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -14 | NOTM TX-New A-12.080 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -18 | NOTM TX-New A-12.090 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.6
OCB EQP -13 | NOTM TX-New A-12.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.3
OCB EQP -14 | NOTM TX-New A-12.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.3
OCB EQP -13 | NOTM TX-New A-12.100 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -14 | NOTM TX-New A-12.100 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -13 | NOTM TX-New A-12.120 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -14 | NOTM TX-New A-12.120 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -13 | NOTM TX-New A-12.140 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.3
OCB EQP -14 | NOTM TX-New A-12.140 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.3
OCB EQP -18 | NOTM TX-New A-12.110 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.6
OCB EQP -18 | NOTM TX-New A-12.150 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.6
OCB EQP -17 | NOTM TX-New A-12.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -16 | NOTM TX-New A-12.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -19 | NOTM TX-New A-12.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -18 | NOTM TX-New A-12.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -15 | NOTM TX-New A-12.200 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.4
OCB EQP -17 | NOTM TX-New A-12.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -19 | NOTM TX-New A-12.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -18 | NOTM TX-New A-12.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -15 | NOTM TX-New A-12.220 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.5
OCB EQP -9 | NOTM TX-New A-12.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -5 | NOTM TX-New A-12.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -13 | NOTM TX-New A-12.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -14 | NOTM TX-New A-12.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -15 | NOTM TX-New A-12.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -6 | NOTM TX-New A-12.210 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.2
OCB EQP -9 | NOTM TX-New A-12.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -5 | NOTM TX-New A-12.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -13 | NOTM TX-New A-12.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -14 | NOTM TX-New A-12.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -15 | NOTM TX-New A-12.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -6 | NOTM TX-New A-12.230 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.3
OCB EQP -3 | NOTM TX-New A-12.190 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -9 | NOTM TX-New A-12.190 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -12 | NOTM TX-New A-12.190 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -8 | NOTM TX-New A-12.190 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -4 | NOTM TX-New A-12.190 | Not Started |  |  | Nonlabor |  |  |  | 3.2.7.1
OCB EQP -18 | EXE TXY P A-01.070 | Completed |  |  | Nonlabor |  |  |  | 3.2.3.4
OCB EQP -18 | EXE TXY P A-01.130 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.5
OCB EQP -13 | EXE TXY P A-01.080 | In Progress |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -14 | EXE TXY P A-01.080 | In Progress |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -18 | EXE TXY P A-01.090 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.6
OCB EQP -13 | EXE TXY P A-01.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.3
OCB EQP -14 | EXE TXY P A-01.160 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.3
OCB EQP -13 | EXE TXY P A-01.100 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -14 | EXE TXY P A-01.100 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -13 | EXE TXY P A-01.120 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -14 | EXE TXY P A-01.120 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.2
OCB EQP -13 | EXE TXY P A-01.140 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.3
OCB EQP -14 | EXE TXY P A-01.140 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.3
OCB EQP -18 | EXE TXY P A-01.110 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.6
OCB EQP -18 | EXE TXY P A-01.150 | Not Started |  |  | Nonlabor |  |  |  | 3.2.3.6
OCB EQP -15 | EXE RS A-08.251 | In Progress |  |  | Nonlabor |  |  |  | 3.2.13.5f (i)
OCB EQP - 21 | EXE RS A-08.251 | In Progress |  |  | Nonlabor |  |  |  | 3.2.13.5f (i)
OCB EQP - 20 | EXE RS A-08.251 | In Progress |  |  | Nonlabor |  |  |  | 3.2.13.5f (i)
OCB EQP - 22 | EXE RS A-08.252 | In Progress |  |  | Nonlabor |  |  |  | 3.2.13.5f (ii)
OCB EQP -15 | EXE RS A-08.253 | Not Started |  |  | Nonlabor |  |  |  | 3.2.13.5f (iii)
OCB EQP - 21 | EXE RS A-08.253 | Not Started |  |  | Nonlabor |  |  |  | 3.2.13.5f (iii)
OCB EQP - 20 | EXE RS A-08.253 | Not Started |  |  | Nonlabor |  |  |  | 3.2.13.5f (iii)