## Sheet1
Resource ID | Activity ID | TASK__status_code | role_id | acct_id | Resource Type | rsrc__rsrc_name | target_cost | act_cost | remain_cost | Budgeted Units | Actual Units | Remaining Units | BOQ Item No. | user_field_131 | delete_record_flag | Budgeted Units_MAT | Actual Units_MAT | Remaining Units_MAT | Description of Resources | Qty/Unit (Norms) | Calc Budgeted Units | Calc Actual Units | Calc Remaining Units | CALC_OK
R.3.2.2.1 | EXE RE A-05.020 | Completed |  |  | Material | Excavation: Earthwork Excavation below the foundation of Reinforced Earth Structure | 1221600 | 1221600 | 0 | 12216 | 12216 | 0 | 3.2.2.1
R.3.2.2.2 | EXE RE A-05.030 | Completed |  |  | Material | Soil improvement below foundation: Replacement of foundation soil below the Reinforced Earth structure | 14870475 | 13866790.5 | 0 | 13833 | 12899 | 0 | 3.2.2.2
R.3.2.2.3 | EXE RE A-05.040 | Completed |  |  | Material | Reinforced Earth Structure (Facia Panels, Geostrap, Mechnical Connectors) | 415548000 | 415548000 | 0 | 6596 | 6596 | 0 | 3.2.2.3
R.3.2.2.4 | EXE RE A-05.050 | In Progress |  |  | Material | Technical backfill: Backfilling, grading and compaction with selected granular backfill soil in layers | 203906987.76 | 222656364 | 0 | 121373 | 132534 | 0 | 3.2.2.4
R.3.2.12.6 | EX NOTM TX A-11E.280 | Not Started |  |  | Material | 1000 mm dia concrete pipe culvert | 1785000 | 0 | 1785000 | 105 | 0 | 105 | 3.2.12.6
R.3.2.12.6 | EXE RS A-08.056 | In Progress |  |  | Material | 1000 mm dia concrete pipe culvert | 3910000 | 3825000 | 85000 | 230 | 225 | 5 | 3.2.12.6
R.3.2.13.1 | EXE RS A-08.130 | Not Started |  |  | Material | 0.30 m x 0.30 m concrete trapezoidal ditch | 1750000 | 0 | 1750000 | 500 | 0 | 500 | 3.2.13.1
R.3.1.1.1 | EXE RS A-08.020 | In Progress |  |  | Material | All types of excavation in soil excluding hard rock | 6996300 | 1039065 | 5987235 | 46642 | 6927 | 39915 | 3.1.1.1
R.3.1.1.2 | EX NOTM RS A-08.032 | In Progress |  |  | Material | Fill (Subgrade Performance: CBR > 5%) | 105887500 | 19029005 | 86858495 | 98500 | 17701 | 80799 | 3.2.2.5
R.3.1.1.3 | EX NOTM RS A-08.042 | Not Started |  |  | Material | Fill (Subgrade Performance: CBR > 15%) | 57500 | 0 | 57500 | 50 | 0 | 50 | 3.2.2.6
R.3.1.2.1 | EX SR A-13.050 | In Progress |  |  | Material | Crushed aggregate SUBbase course - 0.150m thick | 13905600 | 6721200 | 7184400 | 1738 | 840 | 898 | 3.1.2.1
R.3.1.2.4 | EX SR A-13.060 | In Progress |  |  | Material | Prime coat (1.1 lit/sqm) | 1620000 | 758301 | 861699 | 10800 | 5055 | 5745 | 3.1.2.4
R.3.1.2.2 | EX SR A-13.070 | In Progress |  |  | Material | Plant-Mix Asphalt Base Course - 0.060m thick | 15392000 | 7306240 | 8085760 | 481 | 228 | 253 | 3.1.2.2
R.3.1.2.5 | EX SR A-13.080 | In Progress |  |  | Material | Tack coat (approx 0.6 lit/sqm) | 613440 | 190916.8 | 422523.2 | 7668 | 2386 | 5282 | 3.1.2.5
R.3.1.2.3 | EX SR A-13.090 | In Progress |  |  | Material | Asphalt concrete surface course - 0.060 m thick | 18278000 | 5472760 | 12805240 | 481 | 144 | 337 | 3.1.2.3
R.3.2.11.1 | EX SR A-13.140 | Not Started |  |  | Material | Security Fencing | 13290000 | 0 | 13290000 | 2215 | 0 | 2215 | 3.2.11.1
R.4.3.1 | EXE AGL ALL-15.30 | In Progress |  |  | Material | LED Taxiway Edge Lights: Elevated, Omni-directional, blue | 24850000 | 2625000 | 22225000 | 142 | 15 | 127 | 4.3.1
R.4.3.3 | EXE AGL ALL-15.50 | In Progress |  |  | Material | LED Runway Guard Lights, flashing yellow, elevated lights, uni-directional | 6750000 | 4500000 | 2250000 | 6 | 4 | 2 | 4.3.3
R.4.3.4 | EXE AGL ALL-15.60 | Not Started |  |  | Material | LED Runway Edge Lights, Semi-Flush mounted (Replacement of an existing elevated light) | 0 | 0 | 0 | 0 | 0 | 0 | 4.3.4
R.3.2.2.7 | EXE RE A-05.060 | Completed |  |  | Material | Sub-surface drainage: Supply and laying of Geocomposite Drain (Drain tube 20mm dia mini pipe) | 49940800 | 33292812 | 0 | 17836 | 11890 | 0 | 3.2.2.7
R.3.2.2.8 | EXE RE A-05.070 | Completed |  |  | Material | Sub-surface drainage: Supplying and placing of drainage board wrapped with non-woven geotextiles on both side | 1792000 | 1771689.57 | 0 | 400 | 395 | 0 | 3.2.2.8
R.3.2.8 | EX SR A-13.130 | Not Started |  |  | Material | Pavement marking | 356250 | 0 | 356250 | 750 | 0 | 750 | 3.2.8
R.3.2.2.15 | EXE RE A-05.080 | Completed |  |  | Material | Instrumentation: Providing and installation of instruments to measure deformation and settlement | 640000 | 400000 | 0 | 0 | 0 | 0 | 3.2.2.15
R.4.2.1 | EXE AGL ALL-15.20 | Not Started |  |  | Material | 4 mm² copper core XLPE insulated Secondary Cables | 1188000 | 0 | 1188000 | 1980 | 0 | 1980 | 4.2.1
R.4.6.1.1 | EXE AGL ALL-15.100 | Not Started |  |  | Material | (a) 10 kVA for - TWY1 | 2250000 | 0 | 2250000 | 1 | 0 | 1 | 4.6.1.1
R.4.8 | EXE AGL ALL-15.150 | Not Started |  |  | Material | Cables trays/ conduits: Supply and installation of all necessary equipments for HV, LV, power and control/monitoring cables routes | 270000 | 0 | 270000 | 200 | 0 | 200 | 4.8
R.4.9 | EXE AGL ALL-15.160 | Not Started |  |  | Material | Grounding circuit: inclunding earth pit, bare copper cable, ground bars | 150000 | 0 | 150000 | 1 | 0 | 1 | 4.9
R.4.10 | EXE AGL ALL-15.170 | Not Started |  |  | Material | Electrical Works: for electrical works completion (lighting, sockets….) | 206250 | 0 | 206250 | 1 | 0 | 1 | 4.10
R.4.11.1 | EXE AGL ALL-15.180 | Not Started |  |  | Material | Relocation of the existing UPS units for substations ST07 and ST11 including all batteries and all equipment | 112500 | 0 | 112500 | 2 | 0 | 2 | 4.11.1
R.4.12.1 | EXE AGL ALL-15.210 | Not Started |  |  | Material | Relocation of Control servers from P1 and P2 to ST07 and ST11 | 56250 | 0 | 56250 | 1 | 0 | 1 | 4.12.1
R.4.6.2.1 | EXE AGL ALL-15.110 | Not Started |  |  | Material | (a) 10 mm², 4-core cable | 18740 | 0 | 18740 | 20 | 0 | 20 | 4.6.2.1
R.4.6.3.1 | EXE AGL ALL-15.120 | Not Started |  |  | Material | (a) 16 mm² | 4500 | 0 | 4500 | 1 | 0 | 1 | 4.6.3.1
R.4.7.1 | EXE AGL ALL-15.130 | Not Started |  |  | Material | Complete Power supply distribution board, 500 Amp, 15 kA fault rating complete for CCRs in Substation ST07 | 937500 | 0 | 937500 | 1 | 0 | 1 | 4.7.1
R.4.7.2 | EXE AGL ALL-15.140 | Not Started |  |  | Material | Complete Power supply distribution board, 500 Amp, 15 kA fault rating complete for CCRs in Substation ST11 | 945000 | 0 | 945000 | 1 | 0 | 1 | 4.7.2
R.4.11.2 | EXE AGL ALL-15.190 | Not Started |  |  | Material | Suitable cables required for the connection between the UPS Module and the batteries in a separate room including all connection materials for substations ST07 and ST11 | 120300 | 0 | 120300 | 1 | 0 | 1 | 4.11.2
R.4.11.3 | EXE AGL ALL-15.200 | Not Started |  |  | Material | All materials required for the complete earthing of the UPS units at substations ST07 and ST11 | 56250 | 0 | 56250 | 1 | 0 | 1 | 4.11.3
R.4.12.2 | EXE AGL ALL-15.220 | Not Started |  |  | Material | Suitable cables required for the connection between the | 60000 | 0 | 60000 | 1 | 0 | 1 | 4.12.2
R.3.2.2.5 | EXE TXY P A-02.030 | In Progress |  |  | Material | Ordinary backfill: Embankment (CBR > 5%) | 103791250 | 83104208 | 20687042 | 96550 | 77306 | 19244 | 3.2.2.5
R.3.2.2.6 | EXE TXY P A-02.040 | Not Started |  |  | Material | Subgrade: Embankment (Subgrade Performance: CBR > 15%) | 19550000 | 0 | 19550000 | 17000 | 0 | 17000 | 3.2.2.6
R.3.2.1.5 | EXE CGD 1050 | In Progress |  |  | Material | Clearing and grubbing | 1321346 | 488469 | 832883.61 | 264269 | 97694 | 166577 | 3.2.1.5
R.3.2.1.7 | EXE CGD 1070 | In Progress |  |  | Material | Buildings | 2291338 | 1574580 | 716758 | 2291 | 1575 | 717 | 3.2.1.7
R.3.2.2.5 | EXE TXY P A-01.030 | Completed |  |  | Material | Ordinary backfill: Embankment (CBR > 5%) | 957825 | 958147.5 | 0 | 891 | 891 | 0 | 3.2.2.5
R.3.2.2.6 | EXE TXY P A-01.040 | Completed |  |  | Material | Subgrade: Embankment (Subgrade Performance: CBR > 15%) | 28539090 | 25089090 | 0 | 24817 | 21817 | 0 | 3.2.2.6
R.3.2.1.2 | EXE CGD 1020 | In Progress |  |  | Material | Service Roads | 1387500 | 224750 | 1162750 | 13875 | 2248 | 11628 | 3.2.1.2
R.3.2.1.3 | EXE CGD 1030 | In Progress |  |  | Material | Existing chainlink fence | 870000 | 124040 | 745960 | 2175 | 310 | 1865 | 3.2.1.3
R.3.2.1.4 | EXE CGD 1040 | In Progress |  |  | Material | Existing Drain demolition | 2797750 | 1798237.5 | 999512.5 | 11191 | 7193 | 3998 | 3.2.1.4
R.3.2.1.6 | EXE CGD 1060 | In Progress |  |  | Material | Existing equipments | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.1.6
R.3.2.2.9 | EXE TXY P A-01.170 | Not Started |  |  | Material | Sub-surface drainage below taxiway area (Drain tube 25mm dia mini pipe) | 15861000 | 0 | 15861000 | 6220 | 0 | 6220 | 3.2.2.9
R.3.2.7.4 | EXE TXY P A-01.200 | Not Started |  |  | Material | Prime coat (1.1 lit/sqm) | 900000 | 0 | 900000 | 6000 | 0 | 6000 | 3.2.7.4
R.3.2.7.5 | EXE TXY P A-01.220 | Not Started |  |  | Material | Tack coat (approx 0.6 lit/sqm) | 471040 | 0 | 471040 | 5888 | 0 | 5888 | 3.2.7.5
R.3.2.7.2 | EXE TXY P A-01.210 | Not Started |  |  | Material | Plant-Mix Asphalt Base Course | 15680000 | 0 | 15680000 | 490 | 0 | 490 | 3.2.7.2
R.3.2.7.3 | EXE TXY P A-01.230 | Not Started |  |  | Material | Asphalt concrete surface course | 2850000 | 0 | 2850000 | 75 | 0 | 75 | 3.2.7.3
R.3.2.7.1 | EXE TXY P A-01.190 | Not Started |  |  | Material | Crushed aggregate SUBbase course | 14000000 | 0 | 14000000 | 1750 | 0 | 1750 | 3.2.7.1
R.3.2.2.1 | EXE RE A-06.020 | Completed |  |  | Material | Excavation: Earthwork Excavation below the foundation of Reinforced Earth Structure | 2045016 | 1955290 | 0 | 20450 | 19553 | 0 | 3.2.2.1
R.3.2.2.2 | EXE RE A-06.030 | Completed |  |  | Material | Soil improvement below foundation: Replacement of foundation soil below the Reinforced Earth structure | 20232145 | 18131681 | 0 | 18821 | 16867 | 0 | 3.2.2.2
R.3.2.2.3 | EXE RE A-06.040 | Completed |  |  | Material | Reinforced Earth Structure (Facia Panels, Geostrap, Mechnical Connectors) | 572796000 | 572796000 | 0 | 9092 | 9092 | 0 | 3.2.2.3
R.3.2.2.4 | EXE RE A-06.050 | In Progress |  |  | Material | Technical backfill: Backfilling, grading and compaction with selected granular backfill soil in layers | 370692000 | 347833382.4 | 22858617.6 | 220650 | 207044 | 13606 | 3.2.2.4
R.3.2.2.7 | EXE RE A-06.060 | In Progress |  |  | Material | Sub-surface drainage: Supply and laying of Geocomposite Drain (Drain tube 20mm dia mini pipe) | 61600000 | 44227904 | 17372096 | 22000 | 15796 | 6204 | 3.2.2.7
R.3.2.2.8 | EXE RE A-06.070 | Not Started |  |  | Material | Sub-surface drainage: Supplying and placing of drainage board wrapped with non-woven geotextiles on both side | 896000 | 0 | 896000 | 200 | 0 | 200 | 3.2.2.8
R.3.2.2.15 | EXE RE A-06.080 | Completed |  |  | Material | Instrumentation: Providing and installation of instruments to measure deformation and settlement | 840000 | 300000 | 0 | 0 | 0 | 0 | 3.2.2.15
R.3.2.2.3 | EXE RE A-07.040 | Completed |  |  | Material | Reinforced Earth Structure (Facia Panels, Geostrap, Mechnical Connectors) | 163800000 | 163800000 | 0 | 2600 | 2600 | 0 | 3.2.2.3
R.3.2.2.4 | EXE RE A-07.050 | In Progress |  |  | Material | Technical backfill: Backfilling, grading and compaction with selected granular backfill soil in layers | 57750000 | 51187449.6 | 6562550.4 | 34375 | 30469 | 3906 | 3.2.2.4
R.3.2.2.7 | EXE RE A-07.060 | In Progress |  |  | Material | Sub-surface drainage: Supply and laying of Geocomposite Drain (Drain tube 20mm dia mini pipe) | 18760000 | 12467392 | 6292608 | 6700 | 4453 | 2247 | 3.2.2.7
R.3.2.2.8 | EXE RE A-07.070 | In Progress |  |  | Material | Sub-surface drainage: Supplying and placing of drainage board wrapped with non-woven geotextiles on both side | 739200 | 734968.66 | 4231.34 | 165 | 164 | 1 | 3.2.2.8
R.3.2.2.15 | EXE RE A-07.080 | Completed |  |  | Material | Instrumentation: Providing and installation of instruments to measure deformation and settlement | 520000 | 300000 | 0 | 0 | 0 | 0 | 3.2.2.15
R.3.2.2.1 | EXE RE A-07.020 | Completed |  |  | Material | Excavation: Earthwork Excavation below the foundation of Reinforced Earth Structure | 553384 | 553384 | 0 | 5534 | 5534 | 0 | 3.2.2.1
R.3.2.2.2 | EXE RE A-07.030 | Completed |  |  | Material | Soil improvement below foundation: Replacement of foundation soil below the Reinforced Earth structure | 5962380 | 5962380 | 0 | 5546 | 5546 | 0 | 3.2.2.2
R.3.2.2.6 | EXE TXY P A-03.040 | In Progress |  |  | Material | Subgrade: Embankment (Subgrade Performance: CBR > 15%) | 34710910 | 3310804 | 31400106 | 30183 | 2879 | 27304 | 3.2.2.6
R.3.2.2.5 | EXE TXY P A-03.030 | In Progress |  |  | Material | Ordinary backfill: Embankment (CBR > 5%) | 173081450 | 163384186.75 | 9697263.25 | 161006 | 151985 | 9021 | 3.2.2.5
R.3.2.2.6 | EX SR A-13.040 | In Progress |  |  | Material | Subgrade: Embankment (Subgrade Performance: CBR > 15%) | 28750000 | 15504541.5 | 13245458.5 | 25000 | 13482 | 11518 | 3.2.2.6
R.3.2.2.5 | EX SR A-13.030 | In Progress |  |  | Material | Ordinary backfill: Embankment (CBR > 5%) | 22037500 | 21417053 | 620447 | 20500 | 19923 | 577 | 3.2.2.5
R.4.1.1.1 | EXE AGL ALL-15.10 | Not Started |  |  | Material | (a) TWY-1 : Taxiway Edge Lights and Signs | 3558500 | 0 | 3558500 | 3235 | 0 | 3235 | 4.1.1.1
R.3.2.9 | EXE RS A-08.050 | Completed |  |  | Material | Topsoil of shaped areas to depth of 100 mm | 40460000 | 40460000 | 0 | 28900 | 28900 | 0 | 3.2.9
R.3.2.10 | EXE RS A-08.060 | In Progress |  |  | Material | Grassing of topsoiled areas by hydroseeding | 5490000 | 1555369.2 | 3934630.8 | 54900 | 15554 | 39346 | 3.2.10
R.3.2.2.6 | EXE TXY P A-04.040 | Not Started |  |  | Material | Subgrade: Embankment (Subgrade Performance: CBR > 15%) | 14950000 | 0 | 14950000 | 13000 | 0 | 13000 | 3.2.2.6
R.3.2.2.5 | EXE TXY P A-04.030 | In Progress |  |  | Material | Ordinary backfill: Embankment (CBR > 5%) | 111632521.86 | 76285579.75 | 35346946 | 103844 | 70963 | 32881 | 3.2.2.5
R.3.1.1.1a | EX NOTM TX A-09L.020 | Completed |  |  | Material | All types of excavation in soil excluding hard rock (Runway and Taxiway Strip beyond OFZ area upto RE Wall & Service Road) | 472500 | 467242.5 | 0 | 3150 | 3115 | 0 | 3.1.1.1a
R.3.2.2.5 | EX NOTM TX A-09L.030 | Completed |  |  | Material | Ordinary backfill: Embankment (CBR > 5%) | 107500 | 0 | 0 | 100 | 0 | 0 | 3.2.2.5
R.3.2.2.6 | EX NOTM TX A-09L.040 | Completed |  |  | Material | Subgrade: Embankment (Subgrade Performance: CBR > 15%) | 2875000 | 3952780 | 0 | 2500 | 3437 | 0 | 3.2.2.6
R.3.1.1.1a | EX NOTM TX A-10K.020 | In Progress |  |  | Material | All types of excavation in soil excluding hard rock (Runway and Taxiway Strip beyond OFZ area upto RE Wall & Service Road) | 982500 | 981420 | 1080 | 6550 | 6543 | 7 | 3.1.1.1a
R.3.2.2.5 | EX NOTM TX A-10K.030 | Completed |  |  | Material | Ordinary backfill: Embankment (CBR > 5%) | 107500 | 0 | 0 | 100 | 0 | 0 | 3.2.2.5
R.3.2.2.6 | EX NOTM TX A-10K.040 | Completed |  |  | Material | Subgrade: Embankment (Subgrade Performance: CBR > 15%) | 6440000 | 5868565 | 0 | 5600 | 5103 | 0 | 3.2.2.6
R.3.2.3.1 | EXE TXY P A-04.060 | Not Started |  |  | Material | Crushed aggregate SUBbase course - 0.4m thick | 19200000 | 0 | 19200000 | 2400 | 0 | 2400 | 3.2.3.1
R.3.2.2.9 | EXE TXY P A-04.170 | Not Started |  |  | Material | Sub-surface drainage below taxiway area (Drain tube 25mm dia mini pipe) | 6675900 | 0 | 6675900 | 2618 | 0 | 2618 | 3.2.2.9
R.3.2.2.10 | EXE TXY P A-04.050 | Not Started |  |  | Material | Basal reinforcement below taxiway | 5558000 | 0 | 5558000 | 2800 | 0 | 2800 | 3.2.2.10
R.3.2.1.1 | EXE CGD 1010 | In Progress |  |  | Material | Airside Pavement (Asphalt) | 2415000 | 0 | 2415000 | 6900 | 0 | 6900 | 3.2.1.1
R.3.1.1.1a | EXE TXY P A-01.020 | Completed |  |  | Material | All types of excavation in soil excluding hard rock (Runway and Taxiway Strip beyond OFZ area upto RE Wall & Service Road) | 5045565 | 5045565 | 0 | 33637 | 33637 | 0 | 3.1.1.1a
R.3.1.1.1a | EXE TXY P A-02.020 | Not Started |  |  | Material | All types of excavation in soil excluding hard rock (Runway and Taxiway Strip beyond OFZ area upto RE Wall & Service Road) | 15000 | 0 | 15000 | 100 | 0 | 100 | 3.1.1.1a
R.3.2.3.1 | EXE TXY P A-02.060 | Not Started |  |  | Material | Crushed aggregate SUBbase course - 0.4m thick | 25600000 | 0 | 25600000 | 3200 | 0 | 3200 | 3.2.3.1
R.3.2.2.9 | EXE TXY P A-02.170 | Not Started |  |  | Material | Sub-surface drainage below taxiway area (Drain tube 25mm dia mini pipe) | 13464000 | 0 | 13464000 | 5280 | 0 | 5280 | 3.2.2.9
R.3.2.2.10 | EXE TXY P A-02.050 | Not Started |  |  | Material | Basal reinforcement below taxiway | 16068575 | 0 | 16068575 | 8095 | 0 | 8095 | 3.2.2.10
R.3.2.3.4 | EXE TXY P A-02.070 | Not Started |  |  | Material | Prime coat (1.1 lit/sqm) | 1144800 | 0 | 1144800 | 7632 | 0 | 7632 | 3.2.3.4
R.3.2.3.5 | EXE TXY P A-02.130 | Not Started |  |  | Material | Tack coat (approx 0.6 lit/sqm) | 520000 | 0 | 520000 | 6500 | 0 | 6500 | 3.2.3.5
R.3.2.3.2 | EXE TXY P A-02.080 | Not Started |  |  | Material | Plant-Mix Asphalt Base Course - 0.20m thick | 18080000 | 0 | 18080000 | 565 | 0 | 565 | 3.2.3.2
R.3.2.3.6 | EXE TXY P A-02.150 | Not Started |  |  | Material | Tack coat for subsequent asphalt base and surface layers (approx 0.25 lit/sqm) | 350000 | 0 | 350000 | 7000 | 0 | 7000 | 3.2.3.6
R.3.2.3.3 | EXE TXY P A-02.140 | Not Started |  |  | Material | Asphalt concrete surface course - 0.140 m thick | 17670000 | 0 | 17670000 | 465 | 0 | 465 | 3.2.3.3
R.3.2.7.4 | EXE TXY P A-02.200 | Not Started |  |  | Material | Prime coat (1.1 lit/sqm) | 795000 | 0 | 795000 | 5300 | 0 | 5300 | 3.2.7.4
R.3.2.7.5 | EXE TXY P A-02.220 | Not Started |  |  | Material | Tack coat (approx 0.6 lit/sqm) | 422240 | 0 | 422240 | 5278 | 0 | 5278 | 3.2.7.5
R.3.2.7.2 | EXE TXY P A-02.210 | Not Started |  |  | Material | Plant-Mix Asphalt Base Course | 14240000 | 0 | 14240000 | 445 | 0 | 445 | 3.2.7.2
R.3.2.7.3 | EXE TXY P A-02.230 | Not Started |  |  | Material | Asphalt concrete surface course | 14250000 | 0 | 14250000 | 375 | 0 | 375 | 3.2.7.3
R.3.2.7.1 | EXE TXY P A-02.190 | Not Started |  |  | Material | Crushed aggregate SUBbase course | 12680000 | 0 | 12680000 | 1585 | 0 | 1585 | 3.2.7.1
R.3.1.1.1a | EXE TXY P A-03.020 | Not Started |  |  | Material | All types of excavation in soil excluding hard rock (Runway and Taxiway Strip beyond OFZ area upto RE Wall & Service Road) | 15000 | 0 | 15000 | 100 | 0 | 100 | 3.1.1.1a
R.3.2.3.1 | EXE TXY P A-03.060 | Not Started |  |  | Material | Crushed aggregate SUBbase course - 0.4m thick | 39568000 | 0 | 39568000 | 4946 | 0 | 4946 | 3.2.3.1
R.3.2.2.9 | EXE TXY P A-03.170 | Not Started |  |  | Material | Sub-surface drainage below taxiway area (Drain tube 25mm dia mini pipe) | 16702500 | 0 | 16702500 | 6550 | 0 | 6550 | 3.2.2.9
R.3.2.2.10 | EXE TXY P A-03.050 | Not Started |  |  | Material | Basal reinforcement below taxiway | 27061477.89 | 0 | 27061477.89 | 13633 | 0 | 13633 | 3.2.2.10
R.3.2.3.4 | EXE TXY P A-03.070 | Not Started |  |  | Material | Prime coat (1.1 lit/sqm) | 1950000 | 0 | 1950000 | 13000 | 0 | 13000 | 3.2.3.4
R.3.2.3.5 | EXE TXY P A-03.130 | Not Started |  |  | Material | Tack coat (approx 0.6 lit/sqm) | 960000 | 0 | 960000 | 12000 | 0 | 12000 | 3.2.3.5
R.3.2.3.2 | EXE TXY P A-03.080 | Not Started |  |  | Material | Plant-Mix Asphalt Base Course - 0.20m thick | 28800000 | 0 | 28800000 | 900 | 0 | 900 | 3.2.3.2
R.3.2.3.6 | EXE TXY P A-03.090 | Not Started |  |  | Material | Tack coat for subsequent asphalt base and surface layers (approx 0.25 lit/sqm) | 600000 | 0 | 600000 | 12000 | 0 | 12000 | 3.2.3.6
R.3.2.3.3 | EXE TXY P A-03.140 | Not Started |  |  | Material | Asphalt concrete surface course - 0.140 m thick | 22420000 | 0 | 22420000 | 590 | 0 | 590 | 3.2.3.3
R.3.2.7.4 | EXE TXY P A-03.200 | Not Started |  |  | Material | Prime coat (1.1 lit/sqm) | 982500 | 0 | 982500 | 6550 | 0 | 6550 | 3.2.7.4
R.3.2.7.5 | EXE TXY P A-03.220 | Not Started |  |  | Material | Tack coat (approx 0.6 lit/sqm) | 523840 | 0 | 523840 | 6548 | 0 | 6548 | 3.2.7.5
R.3.2.7.2 | EXE TXY P A-03.210 | Not Started |  |  | Material | Plant-Mix Asphalt Base Course | 17440000 | 0 | 17440000 | 545 | 0 | 545 | 3.2.7.2
R.3.2.7.3 | EXE TXY P A-03.230 | Not Started |  |  | Material | Asphalt concrete surface course | 17670000 | 0 | 17670000 | 465 | 0 | 465 | 3.2.7.3
R.3.2.7.1 | EXE TXY P A-03.190 | Not Started |  |  | Material | Crushed aggregate SUBbase course | 15760000 | 0 | 15760000 | 1970 | 0 | 1970 | 3.2.7.1
R.3.1.1.1a | EXE TXY P A-04.020 | Not Started |  |  | Material | All types of excavation in soil excluding hard rock (Runway and Taxiway Strip beyond OFZ area upto RE Wall & Service Road) | 15000 | 0 | 15000 | 100 | 0 | 100 | 3.1.1.1a
R.3.2.3.4 | EXE TXY P A-04.070 | Not Started |  |  | Material | Prime coat (1.1 lit/sqm) | 750000 | 0 | 750000 | 5000 | 0 | 5000 | 3.2.3.4
R.3.2.3.5 | EXE TXY P A-04.130 | Not Started |  |  | Material | Tack coat (approx 0.6 lit/sqm) | 400000 | 0 | 400000 | 5000 | 0 | 5000 | 3.2.3.5
R.3.2.3.2 | EXE TXY P A-04.080 | Not Started |  |  | Material | Plant-Mix Asphalt Base Course - 0.20m thick | 13120000 | 0 | 13120000 | 410 | 0 | 410 | 3.2.3.2
R.3.2.3.6 | EXE TXY P A-04.090 | Not Started |  |  | Material | Tack coat for subsequent asphalt base and surface layers (approx 0.25 lit/sqm) | 275000 | 0 | 275000 | 5500 | 0 | 5500 | 3.2.3.6
R.3.2.3.3 | EXE TXY P A-04.160 | Not Started |  |  | Material | Asphalt concrete surface course - 0.140 m thick | 12540000 | 0 | 12540000 | 330 | 0 | 330 | 3.2.3.3
R.3.2.7.4 | EXE TXY P A-04.200 | Not Started |  |  | Material | Prime coat (1.1 lit/sqm) | 510000 | 0 | 510000 | 3400 | 0 | 3400 | 3.2.7.4
R.3.2.7.5 | EXE TXY P A-04.220 | Not Started |  |  | Material | Tack coat (approx 0.6 lit/sqm) | 271680 | 0 | 271680 | 3396 | 0 | 3396 | 3.2.7.5
R.3.2.7.2 | EXE TXY P A-04.210 | Not Started |  |  | Material | Plant-Mix Asphalt Base Course | 9600000 | 0 | 9600000 | 300 | 0 | 300 | 3.2.7.2
R.3.2.7.3 | EXE TXY P A-04.230 | Not Started |  |  | Material | Asphalt concrete surface course | 5700000 | 0 | 5700000 | 150 | 0 | 150 | 3.2.7.3
R.3.2.6.4 | EX NOTM TX A-09L.070 | Completed |  |  | Material | Prime coat (1.1 lit/sqm) | 561150 | 648342.9 | 0 | 3741 | 4322 | 0 | 3.2.6.4
R.3.2.6.5 | EX NOTM TX A-09L.130 | Not Started |  |  | Material | Tack coat (approx 0.6 lit/sqm) | 292240 | 0 | 292240 | 3653 | 0 | 3653 | 3.2.6.5
R.3.2.6.2 | EX NOTM TX A-09L.080 | Completed |  |  | Material | Plant-Mix Asphalt Base Course | 8960000 | 9350197.76 | 0 | 280 | 292 | 0 | 3.2.6.2
R.3.2.6.6 | EX NOTM TX A-09L.090 | Completed |  |  | Material | Tack coat for subsequent asphalt base and surface layers (approx 0.25 lit/sqm) | 182500 | 216114.3 | 0 | 3650 | 4322 | 0 | 3.2.6.6
R.3.2.6.3 | EX NOTM TX A-09L.140 | Not Started |  |  | Material | Asphalt concrete surface course | 8284000 | 0 | 8284000 | 218 | 0 | 218 | 3.2.6.3
R.3.2.6.1 | EX NOTM TX A-09L.060 | Completed |  |  | Material | Crushed aggregate SUBbase course | 11968000 | 10389600 | 0 | 1496 | 1299 | 0 | 3.2.6.1
R.3.2.5.4 | EX NOTM TX A-10K.070 | Completed |  |  | Material | Prime coat (1.1 lit/sqm) | 968100 | 906716.1 | 0 | 6454 | 6045 | 0 | 3.2.5.4
R.3.2.5.5 | EX NOTM TX A-10K.130 | Not Started |  |  | Material | Tack coat (approx 0.6 lit/sqm) | 506160 | 0 | 506160 | 6327 | 0 | 6327 | 3.2.5.5
R.3.2.5.2 | EX NOTM TX A-10K.080 | Completed |  |  | Material | Plant-Mix Asphalt Base Course | 16160000 | 16176368.64 | 0 | 505 | 506 | 0 | 3.2.5.2
R.3.2.5.6 | EX NOTM TX A-10K.090 | Completed |  |  | Material | Tack coat for subsequent asphalt base and surface layers (approx 0.25 lit/sqm) | 316300 | 290984.97 | 0 | 6326 | 5820 | 0 | 3.2.5.6
R.3.2.5.3 | EX NOTM TX A-10K.140 | Not Started |  |  | Material | Asphalt concrete surface course | 14440000 | 0 | 14440000 | 380 | 0 | 380 | 3.2.5.3
R.3.2.5.1 | EX NOTM TX A-10K.060 | Completed |  |  | Material | Crushed aggregate SUBbase course | 20648000 | 13735200 | 0 | 2581 | 1717 | 0 | 3.2.5.1
R.3.2.2.9 | EX NOTM TX A-09L.170 | Completed |  |  | Material | Sub-surface drainage below taxiway area (Drain tube 25mm dia mini pipe) | 943500 | 4846861.5 | 0 | 370 | 1901 | 0 | 3.2.2.9
R.3.2.2.10 | EX NOTM TX A-09L.050 | Completed |  |  | Material | Basal reinforcement below taxiway | 3573000 | 2902010.45 | 0 | 1800 | 1462 | 0 | 3.2.2.10
R.3.2.2.9 | EX NOTM TX A-10K.170 | Completed |  |  | Material | Sub-surface drainage below taxiway area (Drain tube 25mm dia mini pipe) | 2703000 | 5756803.5 | 0 | 1060 | 2258 | 0 | 3.2.2.9
R.3.2.2.10 | EX NOTM TX A-10K.050 | Completed |  |  | Material | Basal reinforcement below taxiway | 5955000 | 4827500.15 | 0 | 3000 | 2432 | 0 | 3.2.2.10
R.3.1.1.1a | EX SR A-13.020 | In Progress |  |  | Material | All types of excavation in soil excluding hard rock (Runway and Taxiway Strip beyond OFZ area upto RE Wall & Service Road) | 4314000 | 4313874 | 126 | 28760 | 28759 | 1 | 3.1.1.1a
R.3.2.8 | EXE TXY P A-01.280 | Not Started |  |  | Material | Pavement marking | 213750 | 0 | 213750 | 450 | 0 | 450 | 3.2.8
R.3.2.8 | EXE TXY P A-02.270 | Not Started |  |  | Material | Pavement marking | 166250 | 0 | 166250 | 350 | 0 | 350 | 3.2.8
R.3.2.8 | EXE TXY P A-03.270 | Not Started |  |  | Material | Pavement marking | 237500 | 0 | 237500 | 500 | 0 | 500 | 3.2.8
R.3.2.8 | EXE TXY P A-04.270 | Not Started |  |  | Material | Pavement marking | 213750 | 0 | 213750 | 450 | 0 | 450 | 3.2.8
R.3.2.8 | EX NOTM TX A-09L.290 | Not Started |  |  | Material | Pavement marking | 23750 | 0 | 23750 | 50 | 0 | 50 | 3.2.8
R.3.2.8 | EX NOTM TX A-10K.290 | Not Started |  |  | Material | Pavement marking | 47500 | 0 | 47500 | 100 | 0 | 100 | 3.2.8
R.3.2.7.4 | EX NOTM TX A-09L.200 | Not Started |  |  | Material | Prime coat (1.1 lit/sqm) | 232500 | 0 | 232500 | 1550 | 0 | 1550 | 3.2.7.4
R.3.2.7.5 | EX NOTM TX A-09L.220 | Not Started |  |  | Material | Tack coat (approx 0.6 lit/sqm) | 123520 | 0 | 123520 | 1544 | 0 | 1544 | 3.2.7.5
R.3.2.7.2 | EX NOTM TX A-09L.210 | Not Started |  |  | Material | Plant-Mix Asphalt Base Course | 1920000 | 0 | 1920000 | 60 | 0 | 60 | 3.2.7.2
R.3.2.7.3 | EX NOTM TX A-09L.230 | Not Started |  |  | Material | Asphalt concrete surface course | 3800000 | 0 | 3800000 | 100 | 0 | 100 | 3.2.7.3
R.3.2.7.1 | EX NOTM TX A-09L.190 | Completed |  |  | Material | Crushed aggregate SUBbase course | 2720000 | 3098000 | 0 | 340 | 387 | 0 | 3.2.7.1
R.3.2.7.4 | EX NOTM TX A-10K.200 | Not Started |  |  | Material | Prime coat (1.1 lit/sqm) | 183000 | 0 | 183000 | 1220 | 0 | 1220 | 3.2.7.4
R.3.2.7.5 | EX NOTM TX A-10K.220 | Not Started |  |  | Material | Tack coat (approx 0.6 lit/sqm) | 97200 | 0 | 97200 | 1215 | 0 | 1215 | 3.2.7.5
R.3.2.7.2 | EX NOTM TX A-10K.210 | Not Started |  |  | Material | Plant-Mix Asphalt Base Course | 3520000 | 0 | 3520000 | 110 | 0 | 110 | 3.2.7.2
R.3.2.7.3 | EX NOTM TX A-10K.230 | Not Started |  |  | Material | Asphalt concrete surface course | 3420000 | 0 | 3420000 | 90 | 0 | 90 | 3.2.7.3
R.3.2.7.1 | EX NOTM TX A-10K.190 | Completed |  |  | Material | Crushed aggregate SUBbase course | 4360000 | 3684000 | 0 | 545 | 461 | 0 | 3.2.7.1
R.4.4.1.3 | EXE AGL ALL-15.224 | Not Started |  |  | Material | (c) 65 Watt | 840000 | 0 | 840000 | 28 | 0 | 28 | 4.4.1.3 (c)
R-1.1a | EXE PS1 1010 | Completed |  |  | Material | Relocation of abandoned vehicles from backside of CARGO building to front side | 143750 | 143750 | 0 | 1 | 1 | 0 | 1.1a
R-1.2 | EXE PS2 1010 | Not Started |  |  | Material | Provisionals Sums for Runway strip grading and Ancillary Works (Undefined) | 70600000 | 0 | 70600000 | 1 | 0 | 1 | 1.2
R-1.3 | EXE PS3 1010 | Not Started |  |  | Material | Soil Investigation and laboratory tests (Undefined) | 1721672 | 0 | 1721672 | 1 | 0 | 1 | 1.3
R.3.1.1.1a | EX NOTM TX A-11E.030 | In Progress |  |  | Material | All types of excavation in soil excluding hard rock (Runway and Taxiway Strip beyond OFZ area upto RE Wall & Service Road) | 15000 | 15000 | 0 | 100 | 100 | 0 | 3.1.1.1a
R.3.2.2.5 | EX NOTM TX A-11E.040 | Not Started |  |  | Material | Ordinary backfill: Embankment (CBR > 5%) | 107500 | 0 | 107500 | 100 | 0 | 100 | 3.2.2.5
R.3.2.2.6 | EX NOTM TX A-11E.050 | Not Started |  |  | Material | Subgrade: Embankment (Subgrade Performance: CBR > 15%) | 5635000 | 0 | 5635000 | 4900 | 0 | 4900 | 3.2.2.6
R.3.2.4.4 | EX NOTM TX A-11E.080 | Not Started |  |  | Material | Prime coat (1.1 lit/sqm) | 867000 | 0 | 867000 | 5780 | 0 | 5780 | 3.2.4.4
R.3.2.4.5 | EX NOTM TX A-11E.150 | Not Started |  |  | Material | Tack coat (approx 0.6 lit/sqm) | 454960 | 0 | 454960 | 5687 | 0 | 5687 | 3.2.4.5
R.3.2.4.2 | EX NOTM TX A-11E.090 | Not Started |  |  | Material | Plant-Mix Asphalt Base Course | 13440000 | 0 | 13440000 | 420 | 0 | 420 | 3.2.4.2
R.3.2.4.6 | EX NOTM TX A-11E.100 | Not Started |  |  | Material | Tack coat for subsequent asphalt base and surface layers (approx 0.25 lit/sqm) | 284500 | 0 | 284500 | 5690 | 0 | 5690 | 3.2.4.6
R.3.2.4.3 | EX NOTM TX A-11E.160 | Not Started |  |  | Material | Asphalt concrete surface course | 12958000 | 0 | 12958000 | 341 | 0 | 341 | 3.2.4.3
R.3.2.4.1 | EX NOTM TX A-11E.070 | Not Started |  |  | Material | Crushed aggregate SUBbase course | 18496000 | 0 | 18496000 | 2312 | 0 | 2312 | 3.2.4.1
R.3.2.2.9 | EX NOTM TX A-11E.190 | Not Started |  |  | Material | Sub-surface drainage below taxiway area (Drain tube 25mm dia mini pipe) | 1606500 | 0 | 1606500 | 630 | 0 | 630 | 3.2.2.9
R.3.2.2.10 | EX NOTM TX A-11E.060 | Not Started |  |  | Material | Basal reinforcement below taxiway | 2084250 | 0 | 2084250 | 1050 | 0 | 1050 | 3.2.2.10
R.3.2.8 | EX NOTM TX A-11E.320 | Not Started |  |  | Material | Pavement marking | 47500 | 0 | 47500 | 100 | 0 | 100 | 3.2.8
R.3.2.7.4 | EX NOTM TX A-11E.220 | Not Started |  |  | Material | Prime coat (1.1 lit/sqm) | 97500 | 0 | 97500 | 650 | 0 | 650 | 3.2.7.4
R.3.2.7.5 | EX NOTM TX A-11E.240 | Not Started |  |  | Material | Tack coat (approx 0.6 lit/sqm) | 50480 | 0 | 50480 | 631 | 0 | 631 | 3.2.7.5
R.3.2.7.2 | EX NOTM TX A-11E.230 | Not Started |  |  | Material | Plant-Mix Asphalt Base Course | 2560000 | 0 | 2560000 | 80 | 0 | 80 | 3.2.7.2
R.3.2.7.3 | EX NOTM TX A-11E.250 | Not Started |  |  | Material | Asphalt concrete surface course | 2850000 | 0 | 2850000 | 75 | 0 | 75 | 3.2.7.3
R.3.2.7.1 | EX NOTM TX A-11E.210 | Not Started |  |  | Material | Crushed aggregate SUBbase course | 2720000 | 0 | 2720000 | 340 | 0 | 340 | 3.2.7.1
R.3.1.1.1a | NOTM TX-New A-12.020 | In Progress |  |  | Material | All types of excavation in soil excluding hard rock (Runway and Taxiway Strip beyond OFZ area upto RE Wall & Service Road) | 15000 | 15000 | 0 | 100 | 100 | 0 | 3.1.1.1a
R.3.2.2.5 | NOTM TX-New A-12.030 | Not Started |  |  | Material | Ordinary backfill: Embankment (CBR > 5%) | 53750 | 0 | 53750 | 50 | 0 | 50 | 3.2.2.5
R.3.2.2.6 | NOTM TX-New A-12.040 | Not Started |  |  | Material | Subgrade: Embankment (Subgrade Performance: CBR > 15%) | 4419634.55 | 0 | 4419634.55 | 3843 | 0 | 3843 | 3.2.2.6
R.3.2.2.9 | NOTM TX-New A-12.170 | Not Started |  |  | Material | Sub-surface drainage below taxiway area (Drain tube 25mm dia mini pipe) | 4284000 | 0 | 4284000 | 1680 | 0 | 1680 | 3.2.2.9
R.3.2.2.10 | NOTM TX-New A-12.050 | Not Started |  |  | Material | Basal reinforcement below taxiway | 2633328.11 | 0 | 2633328.11 | 1327 | 0 | 1327 | 3.2.2.10
R.3.2.8 | NOTM TX-New A-12.260 | Not Started |  |  | Material | Pavement marking | 47500 | 0 | 47500 | 100 | 0 | 100 | 3.2.8
R.3.2.3.2 | EXE TXY P A-02.100 | Not Started |  |  | Material | Plant-Mix Asphalt Base Course - 0.20m thick | 18080000 | 0 | 18080000 | 565 | 0 | 565 | 3.2.3.2
R.3.2.3.2 | EXE TXY P A-02.120 | Not Started |  |  | Material | Plant-Mix Asphalt Base Course - 0.20m thick | 15520000 | 0 | 15520000 | 485 | 0 | 485 | 3.2.3.2
R.3.2.3.3 | EXE TXY P A-02.160 | Not Started |  |  | Material | Asphalt concrete surface course - 0.140 m thick | 17670000 | 0 | 17670000 | 465 | 0 | 465 | 3.2.3.3
R.3.2.3.6 | EXE TXY P A-02.090 | Not Started |  |  | Material | Tack coat for subsequent asphalt base and surface layers (approx 0.25 lit/sqm) | 350000 | 0 | 350000 | 7000 | 0 | 7000 | 3.2.3.6
R.3.2.3.6 | EXE TXY P A-02.110 | Not Started |  |  | Material | Tack coat for subsequent asphalt base and surface layers (approx 0.25 lit/sqm) | 350000 | 0 | 350000 | 7000 | 0 | 7000 | 3.2.3.6
R.3.2.3.2 | EXE TXY P A-03.100 | Not Started |  |  | Material | Plant-Mix Asphalt Base Course - 0.20m thick | 29728000 | 0 | 29728000 | 929 | 0 | 929 | 3.2.3.2
R.3.2.3.2 | EXE TXY P A-03.120 | Not Started |  |  | Material | Plant-Mix Asphalt Base Course - 0.20m thick | 27680000 | 0 | 27680000 | 865 | 0 | 865 | 3.2.3.2
R.3.2.3.6 | EXE TXY P A-03.110 | Not Started |  |  | Material | Tack coat for subsequent asphalt base and surface layers (approx 0.25 lit/sqm) | 600000 | 0 | 600000 | 12000 | 0 | 12000 | 3.2.3.6
R.3.2.3.6 | EXE TXY P A-03.150 | Not Started |  |  | Material | Tack coat for subsequent asphalt base and surface layers (approx 0.25 lit/sqm) | 600000 | 0 | 600000 | 12000 | 0 | 12000 | 3.2.3.6
R.3.2.3.3 | EXE TXY P A-03.160 | Not Started |  |  | Material | Asphalt concrete surface course - 0.140 m thick | 20900000 | 0 | 20900000 | 550 | 0 | 550 | 3.2.3.3
R.3.2.2.6 | EXE TXY P A-01.180 | Not Started |  |  | Material | Subgrade: Embankment (Subgrade Performance: CBR > 15%) | 1150000 | 0 | 1150000 | 1000 | 0 | 1000 | 3.2.2.6
R.3.2.2.6 | EXE TXY P A-02.180 | Not Started |  |  | Material | Subgrade: Embankment (Subgrade Performance: CBR > 15%) | 977500 | 0 | 977500 | 850 | 0 | 850 | 3.2.2.6
R.3.2.3.2 | EXE TXY P A-04.100 | Not Started |  |  | Material | Plant-Mix Asphalt Base Course - 0.20m thick | 13120000 | 0 | 13120000 | 410 | 0 | 410 | 3.2.3.2
R.3.2.3.2 | EXE TXY P A-04.120 | Not Started |  |  | Material | Plant-Mix Asphalt Base Course - 0.20m thick | 11200000 | 0 | 11200000 | 350 | 0 | 350 | 3.2.3.2
R.3.2.3.3 | EXE TXY P A-04.140 | Not Started |  |  | Material | Asphalt concrete surface course - 0.140 m thick | 12540000 | 0 | 12540000 | 330 | 0 | 330 | 3.2.3.3
R.3.2.3.6 | EXE TXY P A-04.110 | Not Started |  |  | Material | Tack coat for subsequent asphalt base and surface layers (approx 0.25 lit/sqm) | 275000 | 0 | 275000 | 5500 | 0 | 5500 | 3.2.3.6
R.3.2.3.6 | EXE TXY P A-04.150 | Not Started |  |  | Material | Tack coat for subsequent asphalt base and surface layers (approx 0.25 lit/sqm) | 275000 | 0 | 275000 | 5500 | 0 | 5500 | 3.2.3.6
R.3.2.7.1 | EXE TXY P A-04.190 | Not Started |  |  | Material | Crushed aggregate SUBbase course | 8160000 | 0 | 8160000 | 1020 | 0 | 1020 | 3.2.7.1
R.3.2.2.6 | EXE TXY P A-03.180 | Not Started |  |  | Material | Subgrade: Embankment (Subgrade Performance: CBR > 15%) | 1150000 | 0 | 1150000 | 1000 | 0 | 1000 | 3.2.2.6
R.3.2.2.6 | EXE TXY P A-04.180 | Not Started |  |  | Material | Subgrade: Embankment (Subgrade Performance: CBR > 15%) | 575000 | 0 | 575000 | 500 | 0 | 500 | 3.2.2.6
R.3.2.2.6 | EX NOTM TX A-09L.180 | Completed |  |  | Material | Subgrade: Embankment (Subgrade Performance: CBR > 15%) | 115000 | 310500 | 0 | 100 | 270 | 0 | 3.2.2.6
R.3.2.6.2 | EX NOTM TX A-09L.100 | Completed |  |  | Material | Plant-Mix Asphalt Base Course | 8640000 | 9349688.32 | 0 | 270 | 292 | 0 | 3.2.6.2
R.3.2.6.2 | EX NOTM TX A-09L.120 | Completed |  |  | Material | Plant-Mix Asphalt Base Course | 8096000 | 7011720.96 | 0 | 253 | 219 | 0 | 3.2.6.2
R.3.2.6.3 | EX NOTM TX A-09L.160 | Not Started |  |  | Material | Asphalt concrete surface course | 8360000 | 0 | 8360000 | 220 | 0 | 220 | 3.2.6.3
R.3.2.6.6 | EX NOTM TX A-09L.110 | Completed |  |  | Material | Tack coat for subsequent asphalt base and surface layers (approx 0.25 lit/sqm) | 182500 | 194505.55 | 0 | 3650 | 3890 | 0 | 3.2.6.6
R.3.2.6.6 | EX NOTM TX A-09L.150 | Not Started |  |  | Material | Tack coat for subsequent asphalt base and surface layers (approx 0.25 lit/sqm) | 183050 | 0 | 183050 | 3661 | 0 | 3661 | 3.2.6.6
R.3.2.2.6 | EX NOTM TX A-10K.180 | Completed |  |  | Material | Subgrade: Embankment (Subgrade Performance: CBR > 15%) | 230000 | 327750 | 0 | 200 | 285 | 0 | 3.2.2.6
R.3.2.5.3 | EX NOTM TX A-10K.160 | Not Started |  |  | Material | Asphalt concrete surface course | 14364000 | 0 | 14364000 | 378 | 0 | 378 | 3.2.5.3
R.3.2.5.2 | EX NOTM TX A-10K.100 | Completed |  |  | Material | Plant-Mix Asphalt Base Course | 16160000 | 16194831.36 | 0 | 505 | 506 | 0 | 3.2.5.2
R.3.2.5.2 | EX NOTM TX A-10K.120 | Completed |  |  | Material | Plant-Mix Asphalt Base Course | 12160000 | 12147200 | 0 | 380 | 380 | 0 | 3.2.5.2
R.3.2.5.6 | EX NOTM TX A-10K.110 | Completed |  |  | Material | Tack coat for subsequent asphalt base and surface layers (approx 0.25 lit/sqm) | 316300 | 290984.97 | 0 | 6326 | 5820 | 0 | 3.2.5.6
R.3.2.5.6 | EX NOTM TX A-10K.150 | Not Started |  |  | Material | Tack coat for subsequent asphalt base and surface layers (approx 0.25 lit/sqm) | 316300 | 0 | 316300 | 6326 | 0 | 6326 | 3.2.5.6
R.3.2.2.6 | EX NOTM TX A-11E.200 | Not Started |  |  | Material | Subgrade: Embankment (Subgrade Performance: CBR > 15%) | 115000 | 0 | 115000 | 100 | 0 | 100 | 3.2.2.6
R.3.2.4.3 | EX NOTM TX A-11E.180 | Not Started |  |  | Material | Asphalt concrete surface course | 12958000 | 0 | 12958000 | 341 | 0 | 341 | 3.2.4.3
R.3.2.4.2 | EX NOTM TX A-11E.110 | Not Started |  |  | Material | Plant-Mix Asphalt Base Course | 13280000 | 0 | 13280000 | 415 | 0 | 415 | 3.2.4.2
R.3.2.4.2 | EX NOTM TX A-11E.130 | Not Started |  |  | Material | Plant-Mix Asphalt Base Course | 13312000 | 0 | 13312000 | 416 | 0 | 416 | 3.2.4.2
R.3.2.4.6 | EX NOTM TX A-11E.120 | Not Started |  |  | Material | Tack coat for subsequent asphalt base and surface layers (approx 0.25 lit/sqm) | 284500 | 0 | 284500 | 5690 | 0 | 5690 | 3.2.4.6
R.3.2.4.6 | EX NOTM TX A-11E.170 | Not Started |  |  | Material | Tack coat for subsequent asphalt base and surface layers (approx 0.25 lit/sqm) | 284300 | 0 | 284300 | 5686 | 0 | 5686 | 3.2.4.6
R.3.2.2.6 | NOTM TX-New A-12.180 | Not Started |  |  | Material | Subgrade: Embankment (Subgrade Performance: CBR > 15%) | 172500 | 0 | 172500 | 150 | 0 | 150 | 3.2.2.6
R.3.2.3.4 | NOTM TX-New A-12.070 | Not Started |  |  | Material | Prime coat (1.1 lit/sqm) | 226200 | 0 | 226200 | 1508 | 0 | 1508 | 3.2.3.4
R.3.2.3.5 | NOTM TX-New A-12.130 | Not Started |  |  | Material | Tack coat (approx 0.6 lit/sqm) | 122160 | 0 | 122160 | 1527 | 0 | 1527 | 3.2.3.5
R.3.2.3.2 | NOTM TX-New A-12.080 | Not Started |  |  | Material | Plant-Mix Asphalt Base Course - 0.20m thick | 2560000 | 0 | 2560000 | 80 | 0 | 80 | 3.2.3.2
R.3.2.3.6 | NOTM TX-New A-12.090 | Not Started |  |  | Material | Tack coat for subsequent asphalt base and surface layers (approx 0.25 lit/sqm) | 75600 | 0 | 75600 | 1512 | 0 | 1512 | 3.2.3.6
R.3.2.3.3 | NOTM TX-New A-12.160 | Not Started |  |  | Material | Asphalt concrete surface course - 0.140 m thick | 3762000 | 0 | 3762000 | 99 | 0 | 99 | 3.2.3.3
R.3.2.3.2 | NOTM TX-New A-12.100 | Not Started |  |  | Material | Plant-Mix Asphalt Base Course - 0.20m thick | 2560000 | 0 | 2560000 | 80 | 0 | 80 | 3.2.3.2
R.3.2.3.2 | NOTM TX-New A-12.120 | Not Started |  |  | Material | Plant-Mix Asphalt Base Course - 0.20m thick | 1760000 | 0 | 1760000 | 55 | 0 | 55 | 3.2.3.2
R.3.2.3.3 | NOTM TX-New A-12.140 | Not Started |  |  | Material | Asphalt concrete surface course - 0.140 m thick | 3800000 | 0 | 3800000 | 100 | 0 | 100 | 3.2.3.3
R.3.2.3.6 | NOTM TX-New A-12.110 | Not Started |  |  | Material | Tack coat for subsequent asphalt base and surface layers (approx 0.25 lit/sqm) | 75600 | 0 | 75600 | 1512 | 0 | 1512 | 3.2.3.6
R.3.2.3.6 | NOTM TX-New A-12.150 | Not Started |  |  | Material | Tack coat for subsequent asphalt base and surface layers (approx 0.25 lit/sqm) | 57650 | 0 | 57650 | 1153 | 0 | 1153 | 3.2.3.6
R.3.2.7.4 | NOTM TX-New A-12.200 | Not Started |  |  | Material | Prime coat (1.1 lit/sqm) | 362550 | 0 | 362550 | 2417 | 0 | 2417 | 3.2.7.4
R.3.2.7.5 | NOTM TX-New A-12.220 | Not Started |  |  | Material | Tack coat (approx 0.6 lit/sqm) | 53760 | 0 | 53760 | 672 | 0 | 672 | 3.2.7.5
R.3.2.7.2 | NOTM TX-New A-12.210 | Not Started |  |  | Material | Plant-Mix Asphalt Base Course | 7520000 | 0 | 7520000 | 235 | 0 | 235 | 3.2.7.2
R.3.2.7.3 | NOTM TX-New A-12.230 | Not Started |  |  | Material | Asphalt concrete surface course | 3230000 | 0 | 3230000 | 85 | 0 | 85 | 3.2.7.3
R.3.2.7.1 | NOTM TX-New A-12.190 | Not Started |  |  | Material | Crushed aggregate SUBbase course | 4608000 | 0 | 4608000 | 576 | 0 | 576 | 3.2.7.1
R.3.2.2.10 | EXE TXY P A-01.050 | Completed |  |  | Material | Basal reinforcement below taxiway | 29655900 | 18359304.7 | 0 | 14940 | 9249 | 0 | 3.2.2.10
R.3.2.3.4 | EXE TXY P A-01.070 | Completed |  |  | Material | Prime coat (1.1 lit/sqm) | 1950000 | 1259160 | 0 | 13000 | 8394 | 0 | 3.2.3.4
R.3.2.3.5 | EXE TXY P A-01.130 | Not Started |  |  | Material | Tack coat (approx 0.6 lit/sqm) | 960000 | 0 | 960000 | 12000 | 0 | 12000 | 3.2.3.5
R.3.2.3.2 | EXE TXY P A-01.080 | In Progress |  |  | Material | Plant-Mix Asphalt Base Course - 0.20m thick | 28320000 | 19116480 | 9203520 | 885 | 597 | 288 | 3.2.3.2
R.3.2.3.6 | EXE TXY P A-01.090 | Not Started |  |  | Material | Tack coat for subsequent asphalt base and surface layers (approx 0.25 lit/sqm) | 600000 | 0 | 600000 | 12000 | 0 | 12000 | 3.2.3.6
R.3.2.3.3 | EXE TXY P A-01.160 | Not Started |  |  | Material | Asphalt concrete surface course - 0.140 m thick | 28500000 | 0 | 28500000 | 750 | 0 | 750 | 3.2.3.3
R.3.2.3.2 | EXE TXY P A-01.100 | Not Started |  |  | Material | Plant-Mix Asphalt Base Course - 0.20m thick | 28320000 | 0 | 28320000 | 885 | 0 | 885 | 3.2.3.2
R.3.2.3.2 | EXE TXY P A-01.120 | Not Started |  |  | Material | Plant-Mix Asphalt Base Course - 0.20m thick | 27040000 | 0 | 27040000 | 845 | 0 | 845 | 3.2.3.2
R.3.2.3.3 | EXE TXY P A-01.140 | Not Started |  |  | Material | Asphalt concrete surface course - 0.140 m thick | 28500000 | 0 | 28500000 | 750 | 0 | 750 | 3.2.3.3
R.3.2.3.6 | EXE TXY P A-01.110 | Not Started |  |  | Material | Tack coat for subsequent asphalt base and surface layers (approx 0.25 lit/sqm) | 600000 | 0 | 600000 | 12000 | 0 | 12000 | 3.2.3.6
R.3.2.3.6 | EXE TXY P A-01.150 | Not Started |  |  | Material | Tack coat for subsequent asphalt base and surface layers (approx 0.25 lit/sqm) | 600000 | 0 | 600000 | 12000 | 0 | 12000 | 3.2.3.6
R.3.2.3.1 | EXE TXY P A-01.060 | Completed |  |  | Material | Crushed aggregate SUBbase course - 0.4m thick | 38640000 | 29106880 | 0 | 4830 | 3638 | 0 | 3.2.3.1
R.3.2.3.1 | NOTM TX-New A-12.060 | Not Started |  |  | Material | Crushed aggregate SUBbase course - 0.4m thick | 5440000 | 0 | 5440000 | 680 | 0 | 680 | 3.2.3.1
R.3.2.3.6a | EX NOTM TX A-11P.020 | Not Started |  |  | Material | Milling of existing Pavement | 1998500 | 0 | 1998500 | 571 | 0 | 571 | 3.2.3.6a
R.3.2.3.6b | EX NOTM TX A-11P.140 | Not Started |  |  | Material | Supply and Laying Hatelit Asphalt Reinforced at pavement connection | 8539800 | 0 | 8539800 | 993 | 0 | 993 | 3.2.3.6b
R-1.1i | EXE TXY P A-01.240 | Not Started |  |  | Material | Sub surface Drainage work under Taxiway | 0 | 0 | 0 | 0 | 0 | 0 | 1.1i
R.4.14.2 | EXE TXY P A-01.260 | Completed |  |  | Material | Ø100mm Galvanized Iron Pipe, primary ducting under pavement | 805000 | 1324800 | 0 | 350 | 576 | 0 | 4.14.2
R-1.1i | EXE TXY P A-02.240 | Not Started |  |  | Material | Sub surface Drainage work under Taxiway | 0 | 0 | 0 | 0 | 0 | 0 | 1.1i
R-1.1i | EXE TXY P A-03.240 | Not Started |  |  | Material | Sub surface Drainage work under Taxiway | 0 | 0 | 0 | 0 | 0 | 0 | 1.1i
R-1.1i | EXE TXY P A-04.240 | Not Started |  |  | Material | Sub surface Drainage work under Taxiway | 0 | 0 | 0 | 0 | 0 | 0 | 1.1i
R.3.2.13.2 | EXE RS A-08.140 | Not Started |  |  | Material | 0.55 m x 0.30 m concrete trapezoidal ditch (for drain outflow from reinforced wall to outlet drains) | 2205000 | 0 | 2205000 | 294 | 0 | 294 | 3.2.13.2
R.3.2.13.5 | EXE RS A-08.210 | Completed |  |  | Material | with connecting pipe size 1200-1600 mm | 2500000 | 2500000 | 0 | 4 | 4 | 0 | 3.2.13.5
R 3.2.13.5a | EXE RS A-08.220 | Completed |  |  | Material | with connecting pipe size 1000-1000-1000 mm (MH-03) | 547504 | 547504 | 0 | 1 | 1 | 0 | 3.2.13.5a
R 3.2.13.5b | EXE RS A-08.230 | Completed |  |  | Material | With connecting Pipe size 1200 - 1000mm (Double cell) (MH-09) | 1228707 | 1228707 | 0 | 1 | 1 | 0 | 3.2.13.5b
R 3.2.13.6a | EXE RS A-08.270 | Not Started |  |  | Material | Connection between double cell hume pipe and existing box culvert at south east of RWY 02 | 56800 | 0 | 56800 | 1 | 0 | 1 | 3.2.13.6a
R.3.2.13.3 | EX NOTM RS C-08.110 | Not Started |  |  | Material | with connecting pipe culvert size 800-1000 mm | 1200000 | 0 | 1200000 | 4 | 0 | 4 | 3.2.13.3
R 3.2.13.5c | EXE RS A-08.240 | Completed |  |  | Material | with connectin Pipe size 1000mm(double cell) - 1000mm (Double cell) (MH-10) | 987203 | 987203 | 0 | 1 | 1 | 0 | 3.2.13.5c
R 3.2.13.5d | EXE RS A-08.250 | Completed |  |  | Material | With connecting pipe size 1000mm (double cell) - 1200mm (double cell) (MH-11) | 1211053 | 1211053 | 0 | 1 | 1 | 0 | 3.2.13.5d
R-1.1i | EXE RS A-08.070 | Not Started |  |  | Material | Sub surface Drainage work under Taxiway | 0 | 0 | 0 | 0 | 0 | 0 | 1.1i
R-1.1i | EX NOTM TX A-09L.240 | Not Started |  |  | Material | Sub surface Drainage work under Taxiway | 0 | 0 | 0 | 0 | 0 | 0 | 1.1i
R-1.1i | EX NOTM TX A-10K.240 | Not Started |  |  | Material | Sub surface Drainage work under Taxiway | 0 | 0 | 0 | 0 | 0 | 0 | 1.1i
R-1.1i | EX NOTM TX A-11E.260 | Not Started |  |  | Material | Sub surface Drainage work under Taxiway | 0 | 0 | 0 | 0 | 0 | 0 | 1.1i
R-1.1b | EXE PS1 1020 | Completed |  |  | Material | Maintenance of existing building to relocate Hazard House | 175000 | 175000 | 0 | 1 | 1 | 0 | 1.1b
R-1.1c | EXE PS1 1030 | Completed |  |  | Material | Construction of Interlocking block pavement to relocate Tent House | 700000 | 700000 | 0 | 1 | 1 | 0 | 1.1c
R-1.1d | EXE PS1 1040 | Completed |  |  | Material | Relocation of Nepal Army's Camp | 15703934.08 | 14389988.79 | 0 | 1 | 1 | 0 | 1.1d
R-1.1e | EXE PS1 1050 | Completed |  |  | Material | Material Shifting at RWY02 end on South-west side of TIA | 2297985.8 | 2297985.8 | 0 | 1 | 1 | 0 | 1.1e
R-1.1f | EXE PS1 1060 | Completed |  |  | Material | Cargo Approach Road Construction | 3034909.34 | 3028740.85 | 0 | 1 | 1 | 0 | 1.1f
R-1.1g | EXE PS1 1070 | Completed |  |  | Material | CGI fencing near cargo building | 1732556.2 | 1677456.07 | 0 | 1 | 1 | 0 | 1.1g
R-1.1h | EXE PS1 1080 | Completed |  |  | Material | Laying of Hume pipe for the outlet of sub-surface drain below RE wall | 3610092.47 | 3609424.8 | 0 | 1 | 1 | 0 | 1.1h
R-1.1i | EXE PS1 1090 | Not Started |  |  | Material | Sub surface Drainage work under Taxiway | 17007671.05 | 0 | 17007671.05 | 1 | 0 | 1 | 1.1i
R-1.1j | EXE PS1 1100 | Completed |  |  | Material | Replacement of unsuitable material with sand in taxiway and service road. | 2833272 | 2833271 | 0 | 1 | 1 | 0 | 1.1j
R-1.1k | EXE PS1 1110 | Not Started |  |  | Material | Relocation of Fire Hydrant pipe from parallel taxiway working area to side of the future service road. | 388200 | 0 | 388200 | 1 | 0 | 1 | 1.1k
R-1.1l | EXE PS1 1120 | Completed |  |  | Material | Sub-surface drainage in RE wall segment II | 1179827 | 1155736.5 | 0 | 1 | 1 | 0 | 1.1l
R-1.1m | EXE PS1 1130 | Not Started |  |  | Material | Construction of Spring Water Intake near OCB01 Asphalt Plant | 23804311.33 | 0 | 23804311.33 | 1 | 0 | 1 | 1.1m
R-1.2a | EXE PS2 1020 | In Progress |  |  | Material | Survey works for Runway Strip Grading | 1400000 | 1372000 | 28000 | 1 | 1 | 0 | 1.2a
R-1.3a | EXE PS3 1020 | Completed |  |  | Material | Geophysical Investigation work (RE Wall) | 1323328 | 1323328 | 0 | 1 | 1 | 0 | 1.3a
R-1.3b | EXE PS3 1030 | Completed |  |  | Material | Geotechnical Investigation work (Taxiway ) | 1955000 | 1955000 | 0 | 1 | 1 | 0 | 1.3b
R.3.1.1.1a | EX TS A-14.020 | Not Started |  |  | Material | All types of excavation in soil excluding hard rock (Runway and Taxiway Strip beyond OFZ area upto RE Wall & Service Road) | 15000 | 0 | 15000 | 100 | 0 | 100 | 3.1.1.1a
R.3.2.2.5 | EX TS A-14.030 | Not Started |  |  | Material | Ordinary backfill: Embankment (CBR > 5%) | 5513675 | 0 | 5513675 | 5129 | 0 | 5129 | 3.2.2.5
R.3.2.2.6 | EX TS A-14.040 | Not Started |  |  | Material | Subgrade: Embankment (Subgrade Performance: CBR > 15%) | 2012500 | 0 | 2012500 | 1750 | 0 | 1750 | 3.2.2.6
R.3.2.9 | EX TS A-14.050 | Not Started |  |  | Material | Topsoil of shaped areas to depth of 100 mm | 30800000 | 0 | 30800000 | 22000 | 0 | 22000 | 3.2.9
R.3.2.10 | EX TS A-14.060 | Not Started |  |  | Material | Grassing of topsoiled areas by hydroseeding | 2100000 | 0 | 2100000 | 21000 | 0 | 21000 | 3.2.10
R-1.1i | EX TS A-14.070 | Not Started |  |  | Material | Sub surface Drainage work under Taxiway | 0 | 0 | 0 | 0 | 0 | 0 | 1.1i
R 3.2.12.6b | EX NOTM RS C-08.070 | Not Started |  |  | Material | 400 mm dia concrete pipe culvert | 1354500 | 0 | 1354500 | 215 | 0 | 215 | 3.2.12.6b
R 3.2.12.6d | EX SR A-13.100 | In Progress |  |  | Material | 600 mm dia concrete pipe culvert, (Service Road Crossing) | 2352000 | 1608000 | 744000 | 245 | 168 | 78 | 3.2.12.6d
R 3.2.13.2e | EXE RE A-05.120 | Not Started |  |  | Material | RE Wall Top Drain, M35 PCC ( 3x0.45m) W shaped Drain | 4600000 | 0 | 4600000 | 500 | 0 | 500 | 3.2.13.2e
R 3.2.13.2f | EXE RE A-05.130 | Not Started |  |  | Material | RE Wall Berm Drain for overflow, M35 PCC ( 0.2* 0.15) | 666000 | 0 | 666000 | 360 | 0 | 360 | 3.2.13.2f
R-3.2.13.1h | EXE RE A-05.140 | Completed |  |  | Material | RE Wall Bottom Drain, M35 PCC (0.3*0.5 One side Trapezoidal) (In Segment- 3) | 962500 | 962500 | 0 | 175 | 175 | 0 | 3.2.13.2h
R 3.2.13.2e | EXE RE A-06.120 | Not Started |  |  | Material | RE Wall Top Drain, M35 PCC ( 3x0.45m) W shaped Drain | 4140000 | 0 | 4140000 | 450 | 0 | 450 | 3.2.13.2e
R 3.2.13.2f | EXE RE A-06.130 | Not Started |  |  | Material | RE Wall Berm Drain for overflow, M35 PCC ( 0.2* 0.15) | 740000 | 0 | 740000 | 400 | 0 | 400 | 3.2.13.2f
R 3.2.13.2g | EXE RE A-06.140 | In Progress |  |  | Material | RE Wall Bottom Drain, M35 PCC (0.3*0.5 One side Trapezoidal) (In Segment- 1 and Segment- 2) | 2115000 | 1974000 | 141000 | 450 | 420 | 30 | 3.2.13.2g
R 3.2.13.2e | EXE RE A-07.120 | Not Started |  |  | Material | RE Wall Top Drain, M35 PCC ( 3x0.45m) W shaped Drain | 7452000 | 0 | 7452000 | 810 | 0 | 810 | 3.2.13.2e
R 3.2.13.2f | EXE RE A-07.130 | Not Started |  |  | Material | RE Wall Berm Drain for overflow, M35 PCC ( 0.2* 0.15) | 27750 | 0 | 27750 | 15 | 0 | 15 | 3.2.13.2f
R 3.2.13.2g | EXE RE A-07.140 | Completed |  |  | Material | RE Wall Bottom Drain, M35 PCC (0.3*0.5 One side Trapezoidal) (In Segment- 1 and Segment- 2) | 2256000 | 2256000 | 0 | 480 | 480 | 0 | 3.2.13.2g
R.3.2.2.11 | EXE RE A-05.090 | Completed |  |  | Material | Berm Protection: Supply and laying of Geosynthetic Clay Liner as a waterproof membrane | 1234800 | 1300558 | 0 | 630 | 664 | 0 | 3.2.2.11
R.3.2.2.12 | EXE RE A-05.100 | Not Started |  |  | Material | Berm Protection: Supply and laying of M15 grade of plain cement concrete on the berm | 496000 | 0 | 496000 | 31 | 0 | 31 | 3.2.2.12
R.3.2.2.13 | EXE RE A-05.110 | Not Started |  |  | Material | Coping beam: M35 grade of concrete for Coping beam above the Reinfirced Earth panel top | 5520000 | 0 | 5520000 | 230 | 0 | 230 | 3.2.2.13
R.3.2.2.11 | EXE RE A-06.090 | Completed |  |  | Material | Berm Protection: Supply and laying of Geosynthetic Clay Liner as a waterproof membrane | 980000 | 328711.6 | 0 | 500 | 168 | 0 | 3.2.2.11
R.3.2.2.12 | EXE RE A-06.100 | Not Started |  |  | Material | Berm Protection: Supply and laying of M15 grade of plain cement concrete on the berm | 400000 | 0 | 400000 | 25 | 0 | 25 | 3.2.2.12
R.3.2.2.11 | EXE RE A-07.090 | Completed |  |  | Material | Berm Protection: Supply and laying of Geosynthetic Clay Liner as a waterproof membrane | 98000 | 36730.4 | 0 | 50 | 19 | 0 | 3.2.2.11
R.3.2.2.12 | EXE RE A-07.100 | Not Started |  |  | Material | Berm Protection: Supply and laying of M15 grade of plain cement concrete on the berm | 48000 | 0 | 48000 | 3 | 0 | 3 | 3.2.2.12
R.3.1.1.1 | EX NOTM RS B-08.020 | Completed |  |  | Material | All types of excavation in soil excluding hard rock | 15000 | 0 | 0 | 100 | 0 | 0 | 3.1.1.1
R.3.1.1.2 | EX NOTM RS B-08.030 | Completed |  |  | Material | Fill (Subgrade Performance: CBR > 5%) | 13295600 | 13133167.5 | 0 | 12368 | 12217 | 0 | 3.1.1.2
R.3.1.1.3 | EX NOTM RS B-08.040 | Not Started |  |  | Material | Fill (Subgrade Performance: CBR > 15%) | 9591000 | 0 | 9591000 | 8340 | 0 | 8340 | 3.1.1.3
R.3.2.9 | EX NOTM RS B-08.050 | Completed |  |  | Material | Topsoil of shaped areas to depth of 100 mm | 56000000 | 56000000 | 0 | 40000 | 40000 | 0 | 3.2.9
R.3.2.10 | EX NOTM RS B-08.060 | Completed |  |  | Material | Grassing of topsoiled areas by hydroseeding | 4200000 | 4200000 | 0 | 42000 | 42000 | 0 | 3.2.10
R.3.2.2.14 | EXE RE A-05.115 | Not Started |  |  | Material | Coping beam: Supply, cutting, bending, binding and fixing Fe500 grade steel reinforcement for coping beam. | 1197000 | 0 | 1197000 | 9 | 0 | 9 | 3.2.2.14
R.3.2.2.13 | EXE RE A-06.112 | Not Started |  |  | Material | Coping beam: M35 grade of concrete for Coping beam above the Reinfirced Earth panel top | 2880000 | 0 | 2880000 | 120 | 0 | 120 | 3.2.2.13
R.3.2.2.14 | EXE RE A-06.114 | Not Started |  |  | Material | Coping beam: Supply, cutting, bending, binding and fixing Fe500 grade steel reinforcement for coping beam. | 1533000 | 0 | 1533000 | 11 | 0 | 11 | 3.2.2.14
R.3.2.2.13 | EXE RE A-07.112 | Not Started |  |  | Material | Coping beam: M35 grade of concrete for Coping beam above the Reinfirced Earth panel top | 1560047.28 | 0 | 1560047.28 | 65 | 0 | 65 | 3.2.2.13
R.3.2.2.14 | EXE RE A-07.114 | Not Started |  |  | Material | Coping beam: Supply, cutting, bending, binding and fixing Fe500 grade steel reinforcement for coping beam. | 910000 | 0 | 910000 | 7 | 0 | 7 | 3.2.2.14
R.4.1.1.2 | EXE AGL ALL-15.11 | Not Started |  |  | Material | (b) RGL-1: Runway guard Lights | 4400000 | 0 | 4400000 | 4000 | 0 | 4000 | 4.1.1.2
R.4.1.1.3 | EXE AGL ALL-15.12 | Not Started |  |  | Material | (c) Relocation of existing circuits | 24727200 | 0 | 24727200 | 20606 | 0 | 20606 | 4.1.1.3
R.4.1.2 | EXE AGL ALL-15.13 | Not Started |  |  | Material | Primary Cable Connectors Complete | 918750 | 0 | 918750 | 175 | 0 | 175 | 4.1.2
R.4.1.3 | EXE AGL ALL-15.14 | Not Started |  |  | Material | Primary Cable Joints Complete | 21000 | 0 | 21000 | 4 | 0 | 4 | 4.1.3
R.4.2.2 | EXE AGL ALL-15.21 | Not Started |  |  | Material | Secondary Cable Connectors Complete | 656250 | 0 | 656250 | 175 | 0 | 175 | 4.2.2
R 4.3.5.6a | EXE AGL ALL-15.76 | Not Started |  |  | Material | 600x2900 | 1724088 | 0 | 1724088 | 2 | 0 | 2 | 4.3.5.6a
R4.3.5.6b | EXE AGL ALL-15.77 | Not Started |  |  | Material | 600x2400 | 7847576 | 0 | 7847576 | 11 | 0 | 11 | 4.3.5.6b
R 4.3.5.6c | EXE AGL ALL-15.78 | Not Started |  |  | Material | 800*2900 | 10344528 | 0 | 10344528 | 9 | 0 | 9 | 4.3.5.6c
R 4.3.5.6d | EXE AGL ALL-15.79 | Not Started |  |  | Material | 800x2400 | 3804884 | 0 | 3804884 | 4 | 0 | 4 | 4.3.5.6d
R 4.3.5.6e | EXE AGL ALL-15.81 | Not Started |  |  | Material | 800x1200 | 2853666 | 0 | 2853666 | 6 | 0 | 6 | 4.3.5.6e
R.4.4.1.4 | EXE AGL ALL-15.225 | Not Started |  |  | Material | (d) 45 Watt | 3408000 | 0 | 3408000 | 142 | 0 | 142 | 4.4.1.4 (d)
R.4.6.1.2 | EXE AGL ALL-15.101 | Not Started |  |  | Material | (b) 5,0 kVA for - RGL-1 | 2250000 | 0 | 2250000 | 1 | 0 | 1 | 4.6.1.2
R.4.6.2.2 | EXE AGL ALL-15.111 | Not Started |  |  | Material | (b) 10 mm², 2-core cable | 10340 | 0 | 10340 | 20 | 0 | 20 | 4.6.2.2
R.4.6.3.2 | EXE AGL ALL-15.121 | Not Started |  |  | Material | (b) 6 mm² | 4500 | 0 | 4500 | 1 | 0 | 1 | 4.6.3.2
R.4.6.3.3 | EXE AGL ALL-15.122 | Not Started |  |  | Material | (b) 4 mm² | 4500 | 0 | 4500 | 1 | 0 | 1 | 4.6.3.3
R-1.1 | EXE PS1 1000 | In Progress |  |  | Material | Provisional sum (Undefined) | 70929556.2 | 0 | 70929556.2 | 1 | 0 | 1 | 1.1
R.3.2.2.8 | EXE RE A-05.071 | Completed |  |  | Material | Sub-surface drainage: Supplying and placing of drainage board wrapped with non-woven geotextiles on both side | 448000 | 138781.77 | 0 | 100 | 31 | 0 | 3.2.2.8
R.3.2.2.8 | EXE RE A-06.071 | Not Started |  |  | Material | Sub-surface drainage: Supplying and placing of drainage board wrapped with non-woven geotextiles on both side | 896000 | 0 | 896000 | 200 | 0 | 200 | 3.2.2.8
R.3.2.2.8 | EXE RE A-07.071 | In Progress |  |  | Material | Sub-surface drainage: Supplying and placing of drainage board wrapped with non-woven geotextiles on both side | 940800 | 940800 | 0 | 210 | 210 | 0 | 3.2.2.8
R.3.2.12.6 | EXE RS A-08.055 | In Progress |  |  | Material | 1000 mm dia concrete pipe culvert | 850000 | 807500 | 42500 | 50 | 48 | 3 | 3.2.12.6
R.3.2.12.7 | EXE RS A-08.058 | In Progress |  |  | Material | 1200 mm dia concrete pipe culvert | 16500000 | 16280000 | 220000 | 750 | 740 | 10 | 3.2.12.7
R.3.2.12.6 | EXE RS A-08.057 | In Progress |  |  | Material | 1000 mm dia concrete pipe culvert | 1700000 | 1530000 | 170000 | 100 | 90 | 10 | 3.2.12.6
R.3.2.12.7 | EXE RS A-08.59 | In Progress |  |  | Material | 1200 mm dia concrete pipe culvert | 5280000 | 5170000 | 110000 | 240 | 235 | 5 | 3.2.12.7
R.3.1.1.1 | EX NOTM RS C-08.020 | Not Started |  |  | Material | All types of excavation in soil excluding hard rock | 15000 | 0 | 15000 | 100 | 0 | 100 | 3.1.1.1
R.3.1.1.2 | EX NOTM RS C-08.030 | Not Started |  |  | Material | Fill (Subgrade Performance: CBR > 5%) | 1353925.81 | 0 | 1353925.81 | 1259 | 0 | 1259 | 3.2.2.5
R.3.1.1.3 | EX NOTM RS C-08.040 | Not Started |  |  | Material | Fill (Subgrade Performance: CBR > 15%) | 57500 | 0 | 57500 | 50 | 0 | 50 | 3.2.2.6
R.3.2.9 | EX NOTM RS C-08.050 | In Progress |  |  | Material | Topsoil of shaped areas to depth of 100 mm | 44800000 | 28480578 | 16319422 | 32000 | 20343 | 11657 | 3.2.9
R.3.2.10 | EX NOTM RS C-08.060 | Not Started |  |  | Material | Grassing of topsoiled areas by hydroseeding | 500000 | 0 | 500000 | 5000 | 0 | 5000 | 3.2.10
R.3.2.13.4 | EX NOTM RS C-08.120 | Completed |  |  | Material | with connecting pipe size 1000-1200 mm | 950000 | 950000 | 0 | 2 | 2 | 0 | 3.2.13.4
R.4.14.3 | EXE TXY P A-01.270 | Not Started |  |  | Material | Ø50mm Galvanized Iron Pipe, secondary ducting | 290000 | 0 | 290000 | 250 | 0 | 250 | 4.14.3
R.4.3.1 | EXE TXY P A-01.250 | Not Started |  |  | Material | LED Taxiway Edge Lights: Elevated, Omni-directional, blue | 0 | 0 | 0 | 0 | 0 | 0 | 4.3.1
R.4.14.3 | EXE TXY P A-02.260 | Not Started |  |  | Material | Ø50mm Galvanized Iron Pipe, secondary ducting | 290000 | 0 | 290000 | 250 | 0 | 250 | 4.14.3
R.4.3.1 | EXE TXY P A-02.250 | Not Started |  |  | Material | LED Taxiway Edge Lights: Elevated, Omni-directional, blue | 0 | 0 | 0 | 0 | 0 | 0 | 4.3.1
R.4.14.3 | EXE TXY P A-03.260 | Not Started |  |  | Material | Ø50mm Galvanized Iron Pipe, secondary ducting | 290000 | 0 | 290000 | 250 | 0 | 250 | 4.14.3
R.4.3.1 | EXE TXY P A-03.250 | Not Started |  |  | Material | LED Taxiway Edge Lights: Elevated, Omni-directional, blue | 0 | 0 | 0 | 0 | 0 | 0 | 4.3.1
R.4.14.3 | EXE TXY P A-04.260 | Not Started |  |  | Material | Ø50mm Galvanized Iron Pipe, secondary ducting | 156600 | 0 | 156600 | 135 | 0 | 135 | 4.14.3
R.4.3.1 | EXE TXY P A-04.250 | Not Started |  |  | Material | LED Taxiway Edge Lights: Elevated, Omni-directional, blue | 0 | 0 | 0 | 0 | 0 | 0 | 4.3.1
R.4.14.2 | EX NOTM TX A-09L.270 | In Progress |  |  | Material | Ø100mm Galvanized Iron Pipe, primary ducting under pavement | 805000 | 1004640 | 0 | 350 | 437 | 0 | 4.14.2
R.4.14.3 | EX NOTM TX A-09L.280 | In Progress |  |  | Material | Ø50mm Galvanized Iron Pipe, secondary ducting | 110200 | 34800 | 75400 | 95 | 30 | 65 | 4.14.3
R.4.3.1 | EX NOTM TX A-09L.260 | Not Started |  |  | Material | LED Taxiway Edge Lights: Elevated, Omni-directional, blue | 0 | 0 | 0 | 0 | 0 | 0 | 4.3.1
R.4.14.2 | EX NOTM TX A-10K.270 | In Progress |  |  | Material | Ø100mm Galvanized Iron Pipe, primary ducting under pavement | 805000 | 948060 | 0 | 350 | 412 | 0 | 4.14.2
R.4.14.3 | EX NOTM TX A-10K.280 | In Progress |  |  | Material | Ø50mm Galvanized Iron Pipe, secondary ducting | 52200 | 23200 | 29000 | 45 | 20 | 25 | 4.14.3
R.4.3.1 | EX NOTM TX A-10K.260 | Not Started |  |  | Material | LED Taxiway Edge Lights: Elevated, Omni-directional, blue | 0 | 0 | 0 | 0 | 0 | 0 | 4.3.1
R.4.14.2 | EX NOTM TX A-11E.300 | Not Started |  |  | Material | Ø100mm Galvanized Iron Pipe, primary ducting under pavement | 805000 | 0 | 805000 | 350 | 0 | 350 | 4.14.2
R.4.14.3 | EX NOTM TX A-11E.310 | Not Started |  |  | Material | Ø50mm Galvanized Iron Pipe, secondary ducting | 110200 | 0 | 110200 | 95 | 0 | 95 | 4.14.3
R.4.3.1 | EX NOTM TX A-11E.290 | Not Started |  |  | Material | LED Taxiway Edge Lights: Elevated, Omni-directional, blue | 0 | 0 | 0 | 0 | 0 | 0 | 4.3.1
R.4.14.3 | NOTM TX-New A-12.250 | Not Started |  |  | Material | Ø50mm Galvanized Iron Pipe, secondary ducting | 92800 | 0 | 92800 | 80 | 0 | 80 | 4.14.3
R.4.3.1 | NOTM TX-New A-12.240 | Not Started |  |  | Material | LED Taxiway Edge Lights: Elevated, Omni-directional, blue | 0 | 0 | 0 | 0 | 0 | 0 | 4.3.1
R.3.1.1.1a | EXE RE A-05.015 | Completed |  |  | Material | All types of excavation in soil excluding hard rock (Runway and Taxiway Strip beyond OFZ area upto RE Wall & Service Road) | 4500000 | 4497771 | 0 | 30000 | 29985 | 0 | 3.1.1.1a
R.3.1.1.1a | EXE RE A-06.015 | Completed |  |  | Material | All types of excavation in soil excluding hard rock (Runway and Taxiway Strip beyond OFZ area upto RE Wall & Service Road) | 2951764.5 | 2579406 | 0 | 19678 | 17196 | 0 | 3.1.1.1a
R.3.1.1.1a | EXE RE A-07.015 | Completed |  |  | Material | All types of excavation in soil excluding hard rock (Runway and Taxiway Strip beyond OFZ area upto RE Wall & Service Road) | 798750 | 798882 | 0 | 5325 | 5326 | 0 | 3.1.1.1a
R-1.1d.1 | EXE PS1 1041 | Completed |  |  | Material | Additional work for Nepal Army's Camp | 1000000 | 949423.36 | 0 | 1 | 1 | 0 | 1.1d.1
R.4.14.1 | EXE AGL ALL-15.010 | In Progress |  |  | Material | Ø100mm PVC Ducts, primary ducting under grass | 30768000 | 18000 | 30750000 | 10256 | 6 | 10250 | 4.14.1
R.4.5.1.1 | EXE AGL ALL-15.030 | Not Started |  |  | Material | (1) 16 mm² Bare Stranded Copper Earth Conductor to be laid above the Primary Cables as specified | 3379590 | 0 | 3379590 | 12517 | 0 | 12517 | 4.5.1.1
R.4.5.1.2 | EXE AGL ALL-15.040 | Not Started |  |  | Material | (2) 1.2 metre Earthing Electrodes for each Manhole Earthing, including all 16 mm² Bare Stranded Copper Earth Conductors for the earth connection | 187200 | 0 | 187200 | 32 | 0 | 32 | 4.5.1.2
R.4.13.1 | EXE AGL ALL-15.050 | Not Started |  |  | Material | Yellow Cable Marking Tape (Plastic Strip) for laying over primary cables | 26200 | 0 | 26200 | 200 | 0 | 200 | 4.13.1
R.4.13.2 | EXE AGL ALL-15.060 | Not Started |  |  | Material | Cable markers | 105000 | 0 | 105000 | 40 | 0 | 40 | 4.13.2
R-4.15.2a | EXE AGL ALL-15.070 | In Progress |  |  | Material | HH-B 600mm x 600mm x 800mm (E600KN) | 14510592 | 4114944 | 10395648 | 134 | 38 | 96 | 4.15.2a
R 4.15.3a | EXE AGL ALL-15.080 | Not Started |  |  | Material | HH-A 900mm x 900mm x 900mm (F900KN) | 2792277.88 | 0 | 2792277.88 | 7 | 0 | 7 | 4.15.3a
R.3.2.13.1 | EX SR A-13.120 | In Progress |  |  | Material | 0.30 m x 0.30 m concrete trapezoidal ditch | 4998000 | 2663500 | 2334500 | 1428 | 761 | 667 | 3.2.13.1
R.4.14.2 | OCB-0111 | In Progress |  |  | Material | Ø100mm Galvanized Iron Pipe, primary ducting under pavement | 828000 | 414000 | 414000 | 360 | 180 | 180 | 4.14.2
R 3.2.13.5e | EX NOTM D-08.080 | Completed |  |  | Material | With connecting pipe size1200mm (double cell) - 1200mm (double cell) (MH-12) | 1614999 | 1614999 | 0 | 1 | 1 | 0 | 3.2.13.5e
R.3.2.12.7 | EX NOTM D-08.060 | Completed |  |  | Material | 1200 mm dia concrete pipe culvert | 7370000 | 7370000 | 0 | 335 | 335 | 0 | 3.2.12.7
R.3.2.12.7 | EX NOTM D-08.070 | Completed |  |  | Material | 1200 mm dia concrete pipe culvert | 5830000 | 5610000 | 0 | 265 | 255 | 0 | 3.2.12.7
R.3.2.2.9 | EXE RE A-06.061 | In Progress |  |  | Material | Sub-surface drainage below taxiway area (Drain tube 25mm dia mini pipe) | 79774200 | 45037462.5 | 60236737.5 | 31284 | 17662 | 23622 | 3.2.2.9
R-8 4.3.5.6f | EXE AGL ALL-15.82 | Not Started |  |  | Material | 600x1500 | 891770 | 0 | 891770 | 2 | 0 | 2 | 4.3.5.6f
R.4.4.1.2 | EXE AGL ALL-15.223 | Not Started |  |  | Material | (b) 100 Watt | 0 | 0 | 0 | 0 | 0 | 0 | 4.4.1.2 (b)
R.4.4.1.1 | EXE AGL ALL-15.222 | Not Started |  |  | Material | (a) 150 Watt | 0 | 0 | 0 | 0 | 0 | 0 | 4.4.1.1 (a)
R-8 4.14.3a | NOTM TX-New A-12.261 | Not Started |  |  | Material | Concrete Pipe Encasement for secondary ducting and foundation Concrete for metrological equipment footings (M30 Grade) | 786500 | 0 | 786500 | 55 | 0 | 55 | 4.14.3a
R.3.2.11.2 | EX SR A-13.141 | Not Started |  |  | Material | Crash Gates | 400000 | 0 | 400000 | 2 | 0 | 2 | 3.2.11.2
R.3.2.2.15a | EXE RE A-05.116 | Not Started |  |  | Material | Providing and erecting a "W" metal beam crash barrier for RW Wall Top (Single layer beam sheet) | 3200000 | 0 | 3200000 | 400 | 0 | 400 | 3.2.2.15a
R.3.2.2.15c | EXE RE A-05.118 | Not Started |  |  | Material | Providing and laying Tarfelt over Technical backfill | 2240000 | 0 | 2240000 | 8000 | 0 | 8000 | 3.2.2.15c
R.3.2.2.15a | EXE RE A-06.115 | Not Started |  |  | Material | Providing and erecting a "W" metal beam crash barrier for RW Wall Top (Single layer beam sheet) | 3600000 | 0 | 3600000 | 450 | 0 | 450 | 3.2.2.15a
R.3.2.2.15b | EXE RE A-06.116 | Not Started |  |  | Material | Providing and erecting a "W" metal beam crash barrier RW Wall Protection infront of Cargo Area (Two layer beam Sheet) | 3900000 | 0 | 3900000 | 300 | 0 | 300 | 3.2.2.15b
R.3.2.2.15c | EXE RE A-06.117 | Not Started |  |  | Material | Providing and laying Tarfelt over Technical backfill | 3360000 | 0 | 3360000 | 12000 | 0 | 12000 | 3.2.2.15c
R.3.2.2.15a | EXE RE A-07.115 | Not Started |  |  | Material | Providing and erecting a "W" metal beam crash barrier for RW Wall Top (Single layer beam sheet) | 3280000 | 0 | 3280000 | 410 | 0 | 410 | 3.2.2.15a
R.3.2.2.15c | EXE RE A-07.117 | Not Started |  |  | Material | Providing and laying Tarfelt over Technical backfill | 1560160 | 0 | 1560160 | 5572 | 0 | 5572 | 3.2.2.15c
R 3.2.13.5f | EX NOTM D-08.081 | Completed |  |  | Material | With connecting pipe size 1200mm (double cell) to 1200mm (double cell) ( MH-13) | 4531152 | 4531152 | 0 | 1 | 1 | 0 | 3.2.13.5f
i | EXE RS A-08.251 | In Progress |  |  | Material | M15 PCC work for bedding | 390666 | 160000 | 230720 | 24 | 10 | 14 | 3.2.13.5f (i)
ii | EXE RS A-08.252 | In Progress |  |  | Material | Stone Masonary Work with Pointing (1:4) | 2934800 | 1160000 | 1774800 | 253 | 100 | 153 | 3.2.13.5f (ii)
iii | EXE RS A-08.253 | Not Started |  |  | Material | M30 RCC work for cover slab | 300300 | 0 | 300300 | 21 | 0 | 21 | 3.2.13.5f (iii)
iv | EXE RS A-08.254 | Not Started |  |  | Material | Manhole cover | 124200 | 0 | 124200 | 9 | 0 | 9 | 3.2.13.5f (iv)
v | EXE RS A-08.255 | Not Started |  |  | Material | Reinforcment | 302911.87 | 0 | 302911.87 | 2 | 0 | 2 | 3.2.13.5f (v)
3.2.13.5g | EXE TXY P A-01.241 | Not Started |  |  | Material | Concrete work for fire hydrant pipe crossing under TWY- J (P) | 945000 | 0 | 945000 | 135 | 0 | 135 | 3.2.13.5g
3.2.13.5h | EXE RE A-07.118 | Not Started |  |  | Material | Providing and laying Gabion structure | 3108000 | 0 | 3108000 | 420 | 0 | 420 | 3.2.13.5h
3.2.13.5i | EXE RE A-07.119 | Not Started |  |  | Material | Providing and laying geotextile in the back side of the gabion wall | 38400 | 0 | 38400 | 384 | 0 | 384 | 3.2.13.5i
R-3.2.13.6b | EXE RS A-08.271 | Not Started |  |  | Material | Connection of right side drain of service road to existing approach drain | 1550000 | 0 | 1550000 | 1 | 0 | 1 | 3.2.13.6b
R.3.2.12.6c | EX NOTM RS C-08.071 | Not Started |  |  | Material | Concrete Pipe Encasement | 450240 | 0 | 450240 | 28 | 0 | 28 | 3.2.12.6c
R.3.2.12.6a | EXE RS A-08.107 | Completed |  |  | Material | Concrete Pipe Encasement | 7129496 | 4496800 | 0 | 446 | 281 | 0 | 3.2.12.6a
R.3.2.12.7a | EXE RS A-08.108 | Completed |  |  | Material | Concrete Pipe Encasement | 6852800 | 6852800 | 0 | 428 | 428 | 0 | 3.2.12.7a
R.3.2.12.7b | EXE RS A-08.109 | Completed |  |  | Material | Sub Surface drain size 500x500 with gravel packed with geotextile along the drainage humepipe ( MH-07 to MH-09) | 510000 | 425000 | 0 | 300 | 250 | 0 | 3.2.12.7b
R.3.2.12.7c | EXE RS A-08.110 | Completed |  |  | Material | Sub Surface drain size 300x300 with gravel packed with geotextile along theHume Pipe (MH03-MH07), (MH12-Existing Manhole) | 490000 | 385000 | 0 | 700 | 550 | 0 | 3.2.12.7c
R.3.2.12.7d | EXE RS A-08.111 | Completed |  |  | Material | Subsurface Drainage work from MH-08 to outlet using 160mm Dia HDPE pipe | 336000 | 240000 | 0 | 140 | 100 | 0 | 3.2.12.7d
R.3.2.12.7e | EXE RS A-08.112 | Completed |  |  | Material | Subsurface Drainage work from MH-09 to outlet using 200mm Dia HDPE pipe | 822500 | 350000 | 0 | 235 | 100 | 0 | 3.2.12.7e
R 3.2.13.2a | EXE RS A-08.141 | Not Started |  |  | Material | 0.55 m x 0.35 m Open Trapezoidal Drain,M35 PCC ( Between MH10 and MH11) | 247500 | 0 | 247500 | 45 | 0 | 45 | 3.2.13.2a
R 3.2.13.2b | EXE RS A-08.142 | Not Started |  |  | Material | 0.30 m x 0.30 m Covered Trapezoidal Drain, M35 RCC ( Between Twy (J) and Twy (E) ) | 1537000 | 0 | 1537000 | 145 | 0 | 145 | 3.2.13.2b
R 3.2.13.2c | EXE RS A-08.143 | Not Started |  |  | Material | 0.20 m x 0.20 m Covered Trapezoidal Drain, M35 RCC (From exisitng Drain to MH-01) | 560000 | 0 | 560000 | 80 | 0 | 80 | 3.2.13.2c
R.3.2.5.6a | EX NOTM TX A-10K.021 | Completed |  |  | Material | Filling rockfill material at required depth as bridging Layer | 833000 | 833000 | 0 | 245 | 245 | 0 | 3.2.5.6a
R.3.2.6.6a | EX NOTM TX A-09L.021 | Completed |  |  | Material | Filling rockfill material at required depth as bridging Layer | 4923200 | 4923200 | 0 | 1448 | 1448 | 0 | 3.2.6.6a
R.3.2.6.6b | EX NOTM TX A-09L.022 | Completed |  |  | Material | Laying of Geotextile material 1.5mm to 3mm | 1125020 | 1125020 | 0 | 4327 | 4327 | 0 | 3.2.6.6b
R.3.2.6.6c | EX NOTM TX A-09L.023 | Completed |  |  | Material | Laying of Geocompoite Material | 45000 | 45000 | 0 | 4500 | 4500 | 0 | 3.2.6.6c
R-4.15.1a | EXE AGL ALL-15.071 | In Progress |  |  | Material | MH-D 1200mm x 1200mm x 1700mm (E600KN) | 16568028 | 4142007 | 12426021 | 18 | 5 | 14 | 4.15.1a
R.3.2.2.9 | EXE RE A-05.062 | Completed |  |  | Material | Sub-surface drainage below taxiway area (Drain tube 25mm dia mini pipe) | 25500000 | 22913203.5 | 0 | 10000 | 8986 | 0 | 3.2.2.9
OCB EQP -1 | EXE RS A-08.020 | In Progress |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 80 | 0 | 1 | 3.1.1.1 |  |  | 46642 | 6927 | 39915 | hydraulic excavator | 0.025 | 1166.05 | 173.175 | 997.875 | TRUE
OCB EQP -9 | EXE RS A-08.020 | In Progress |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 80 | 0 | 2 | 3.1.1.1 |  |  | 46642 | 6927 | 39915 | Tipper | 0.044 | 2052.248 | 304.788 | 1756.26 | TRUE
OCB EQP -3 | EX NOTM RS A-08.032 | In Progress |  |  | Nonlabor | Grader | 0 | 0 | 0 | 80 | 0 | 1 | 3.2.2.5 |  |  | 98500 | 17701 | 80799 | motor grader | 0.01 | 985 | 177.01 | 807.99 | TRUE
OCB EQP -1 | EX NOTM RS A-08.032 | In Progress |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 80 | 0 | 2 | 3.2.2.5 |  |  | 98500 | 17701 | 80799 | hydraulic excavator | 0.02 | 1970 | 354.02 | 1615.98 | TRUE
OCB EQP -9 | EX NOTM RS A-08.032 | In Progress |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 80 | 0 | 10 | 3.2.2.5 |  |  | 98500 | 17701 | 80799 | Tipper | 0.083333 | 8208.3333 | 1475.0833 | 6733.25 | TRUE
OCB EQP -12 | EX NOTM RS A-08.032 | In Progress |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 80 | 0 | 2 | 3.2.2.5 |  |  | 98500 | 17701 | 80799 | Water Bowser | 0.02 | 1970 | 354.02 | 1615.98 | TRUE
OCB EQP -2 | EX NOTM RS A-08.032 | In Progress |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 80 | 0 | 1 | 3.2.2.5 |  |  | 98500 | 17701 | 80799 | dozer | 0.01 | 985 | 177.01 | 807.99 | TRUE
OCB EQP -4 | EX NOTM RS A-08.032 | In Progress |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 80 | 0 | 2 | 3.2.2.5 |  |  | 98500 | 17701 | 80799 | vibratory road roller | 0.02 | 1970 | 354.02 | 1615.98 | TRUE
OCB EQP -3 | EX NOTM RS A-08.042 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 50 | 0 | 50 | motor grader | 0.01 | 0.5 | 0 | 0.5 | TRUE
OCB EQP -1 | EX NOTM RS A-08.042 | Not Started |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 50 | 0 | 50 | hydraulic excavator | 0.02 | 1 | 0 | 1 | TRUE
OCB EQP -9 | EX NOTM RS A-08.042 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 5 | 0 | 5 | 3.2.2.6 |  |  | 50 | 0 | 50 | Tipper | 0.083333 | 4.1667 | 0 | 4.1667 | TRUE
OCB EQP -12 | EX NOTM RS A-08.042 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 50 | 0 | 50 | Water Bowser | 0.02 | 1 | 0 | 1 | TRUE
OCB EQP -2 | EX NOTM RS A-08.042 | Not Started |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 50 | 0 | 50 | dozer | 0.01 | 0.5 | 0 | 0.5 | TRUE
OCB EQP -4 | EX NOTM RS A-08.042 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 50 | 0 | 50 | vibratory road roller | 0.02 | 1 | 0 | 1 | TRUE
OCB EQP -3 | EX SR A-13.050 | In Progress |  |  | Nonlabor | Grader | 0 | 0 | 0 | 240 | 0 | 2 | 3.1.2.1 |  |  | 1738 | 840 | 898 | motor grader | 0.02 | 34.76 | 16.8 | 17.96 | TRUE
OCB EQP -9 | EX SR A-13.050 | In Progress |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 240 | 0 | 10 | 3.1.2.1 |  |  | 1738 | 840 | 898 | Tipper | 0.083333 | 144.8333 | 70 | 74.8333 | TRUE
OCB EQP -12 | EX SR A-13.050 | In Progress |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 240 | 0 | 4 | 3.1.2.1 |  |  | 1738 | 840 | 898 | Water Bowser | 0.033 | 57.354 | 27.72 | 29.634 | TRUE
OCB EQP -8 | EX SR A-13.050 | In Progress |  |  | Nonlabor | Loader | 0 | 0 | 0 | 240 | 0 | 5 | 3.1.2.1 |  |  | 1738 | 840 | 898 | Loader | 0.04 | 69.52 | 33.6 | 35.92 | TRUE
OCB EQP -4 | EX SR A-13.050 | In Progress |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 240 | 0 | 5 | 3.1.2.1 |  |  | 1738 | 840 | 898 | vibratory road roller | 0.04 | 69.52 | 33.6 | 35.92 | TRUE
OCB EQP -17 | EX SR A-13.060 | In Progress |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 32 | 0 | 0 | 3.1.2.4 |  |  | 10800 | 5055 | 5745 | Air compressor | 0.0016 | 17.28 | 8.088 | 9.192 | TRUE
OCB EQP -16 | EX SR A-13.060 | In Progress |  |  | Nonlabor | Mechanical Broom | 0 | 0 | 0 | 32 | 0 | 0 | 3.1.2.4 |  |  | 10800 | 5055 | 5745 | Mechanical Broom | 0.0016 | 17.28 | 8.088 | 9.192 | TRUE
OCB EQP -19 | EX SR A-13.060 | In Progress |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 32 | 0 | 0 | 3.1.2.4 |  |  | 10800 | 5055 | 5745 | Boiler | 0.0016 | 17.28 | 8.088 | 9.192 | TRUE
OCB EQP -18 | EX SR A-13.060 | In Progress |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 32 | 0 | 0 | 3.1.2.4 |  |  | 10800 | 5055 | 5745 | [5 empty] | FALSE
OCB EQP -15 | EX SR A-13.060 | In Progress |  |  | Nonlabor | Generator | 0 | 0 | 0 | 32 | 0 | 0 | 3.1.2.4 |  |  | 10800 | 5055 | 5745 | Generator | 0.0016 | 17.28 | 8.088 | 9.192 | TRUE
OCB EQP -9 | EX SR A-13.070 | In Progress |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 48 | 0 | 4 | 3.1.2.2 |  |  | 481 | 228 | 253 | Tipper | 0.083333 | 40.0833 | 19 | 21.0833 | TRUE
OCB EQP -5 | EX SR A-13.070 | In Progress |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 48 | 0 | 3 | 3.1.2.2 |  |  | 481 | 228 | 253 | Pneumatic Roller | 0.062827 | 30.2199 | 14.3246 | 15.8953 | TRUE
OCB EQP -13 | EX SR A-13.070 | In Progress |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 48 | 0 | 3 | 3.1.2.2 |  |  | 481 | 228 | 253 | [5 empty] | FALSE
OCB EQP -14 | EX SR A-13.070 | In Progress |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 48 | 0 | 3 | 3.1.2.2 |  |  | 481 | 228 | 253 | [5 empty] | FALSE
OCB EQP -15 | EX SR A-13.070 | In Progress |  |  | Nonlabor | Generator | 0 | 0 | 0 | 48 | 0 | 3 | 3.1.2.2 |  |  | 481 | 228 | 253 | Generator | 0.062827 | 30.2199 | 14.3246 | 15.8953 | TRUE
OCB EQP -6 | EX SR A-13.070 | In Progress |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 48 | 0 | 6 | 3.1.2.2 |  |  | 481 | 228 | 253 | Smooth wheel tandem roller | 0.12565 | 60.4398 | 28.6492 | 31.7906 | TRUE
OCB EQP -17 | EX SR A-13.080 | In Progress |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 64 | 0 | 0 | 3.1.2.5 |  |  | 7668 | 2386 | 5282 | Air compressor | 0.0012 | 9.2016 | 2.8632 | 6.3384 | TRUE
OCB EQP -19 | EX SR A-13.080 | In Progress |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 64 | 0 | 0 | 3.1.2.5 |  |  | 7668 | 2386 | 5282 | Boiler | 0.0012 | 9.2016 | 2.8632 | 6.3384 | TRUE
OCB EQP -18 | EX SR A-13.080 | In Progress |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 64 | 0 | 0 | 3.1.2.5 |  |  | 7668 | 2386 | 5282 | [5 empty] | FALSE
OCB EQP -15 | EX SR A-13.080 | In Progress |  |  | Nonlabor | Generator | 0 | 0 | 0 | 64 | 0 | 0 | 3.1.2.5 |  |  | 7668 | 2386 | 5282 | Generator | 0.0012 | 9.2016 | 2.8632 | 6.3384 | TRUE
OCB EQP -9 | EX SR A-13.090 | In Progress |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 96 | 0 | 8 | 3.1.2.3 |  |  | 481 | 144 | 337 | Tipper | 0.083333 | 40.0833 | 12 | 28.0833 | TRUE
OCB EQP -5 | EX SR A-13.090 | In Progress |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 96 | 0 | 6 | 3.1.2.3 |  |  | 481 | 144 | 337 | Pneumatic Roller | 0.062827 | 30.2199 | 9.0471 | 21.1728 | TRUE
OCB EQP -13 | EX SR A-13.090 | In Progress |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 96 | 0 | 6 | 3.1.2.3 |  |  | 481 | 144 | 337 | [5 empty] | FALSE
OCB EQP -14 | EX SR A-13.090 | In Progress |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 96 | 0 | 6 | 3.1.2.3 |  |  | 481 | 144 | 337 | [5 empty] | FALSE
OCB EQP -15 | EX SR A-13.090 | In Progress |  |  | Nonlabor | Generator | 0 | 0 | 0 | 96 | 0 | 6 | 3.1.2.3 |  |  | 481 | 144 | 337 | Generator | 0.062827 | 30.2199 | 9.0471 | 21.1728 | TRUE
OCB EQP -6 | EX SR A-13.090 | In Progress |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 96 | 0 | 12 | 3.1.2.3 |  |  | 481 | 144 | 337 | Smooth wheel tandem roller | 0.12565 | 60.4398 | 18.0942 | 42.3455 | TRUE
OCB EQP -3 | EXE TXY P A-02.030 | In Progress |  |  | Nonlabor | Grader | 0 | 0 | 0 | 3744 | 0 | 0 | 3.2.2.5 |  |  | 96550 | 77306 | 19244 | motor grader | 0.01 | 965.5 | 773.06 | 192.44 | TRUE
OCB EQP -1 | EXE TXY P A-02.030 | In Progress |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 3744 | 0 | 1 | 3.2.2.5 |  |  | 96550 | 77306 | 19244 | hydraulic excavator | 0.02 | 1931 | 1546.12 | 384.88 | TRUE
OCB EQP -9 | EXE TXY P A-02.030 | In Progress |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3744 | 0 | 3 | 3.2.2.5 |  |  | 96550 | 77306 | 19244 | Tipper | 0.083333 | 8045.8333 | 6442.1667 | 1603.6667 | TRUE
OCB EQP -12 | EXE TXY P A-02.030 | In Progress |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 3744 | 0 | 1 | 3.2.2.5 |  |  | 96550 | 77306 | 19244 | Water Bowser | 0.02 | 1931 | 1546.12 | 384.88 | TRUE
OCB EQP -2 | EXE TXY P A-02.030 | In Progress |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 3744 | 0 | 0 | 3.2.2.5 |  |  | 96550 | 77306 | 19244 | dozer | 0.01 | 965.5 | 773.06 | 192.44 | TRUE
OCB EQP -4 | EXE TXY P A-02.030 | In Progress |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 3744 | 0 | 1 | 3.2.2.5 |  |  | 96550 | 77306 | 19244 | vibratory road roller | 0.02 | 1931 | 1546.12 | 384.88 | TRUE
OCB EQP -3 | EXE TXY P A-02.040 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 17000 | 0 | 17000 | motor grader | 0.01 | 170 | 0 | 170 | TRUE
OCB EQP -1 | EXE TXY P A-02.040 | Not Started |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.6 |  |  | 17000 | 0 | 17000 | hydraulic excavator | 0.02 | 340 | 0 | 340 | TRUE
OCB EQP -9 | EXE TXY P A-02.040 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 10 | 0 | 10 | 3.2.2.6 |  |  | 17000 | 0 | 17000 | Tipper | 0.083333 | 1416.6667 | 0 | 1416.6667 | TRUE
OCB EQP -12 | EXE TXY P A-02.040 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.6 |  |  | 17000 | 0 | 17000 | Water Bowser | 0.02 | 340 | 0 | 340 | TRUE
OCB EQP -2 | EXE TXY P A-02.040 | Not Started |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 17000 | 0 | 17000 | dozer | 0.01 | 170 | 0 | 170 | TRUE
OCB EQP -4 | EXE TXY P A-02.040 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.6 |  |  | 17000 | 0 | 17000 | vibratory road roller | 0.02 | 340 | 0 | 340 | TRUE
OCB EQP -11 | EXE CGD 1050 | In Progress |  |  | Nonlabor | Tractor / Trolley | 0 | 0 | 0 | 1680 | 0 | 0 | 3.2.1.5 |  |  | 264269 | 97694 | 166577 | tractor-trolly | 0.0012 | 317.1228 | 117.2328 | 199.8924 | TRUE
OCB EQP -3 | EXE TXY P A-01.030 | Completed |  |  | Nonlabor | Grader | 0 | 0 | 0 | 176 | 0 | 0 | 3.2.2.5 |  |  | 891 | 891 | 0 | motor grader | 0.01 | 8.91 | 8.91 | 0 | TRUE
OCB EQP -1 | EXE TXY P A-01.030 | Completed |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 176 | 0 | 0 | 3.2.2.5 |  |  | 891 | 891 | 0 | hydraulic excavator | 0.02 | 17.82 | 17.82 | 0 | TRUE
OCB EQP -9 | EXE TXY P A-01.030 | Completed |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 176 | 0 | 0 | 3.2.2.5 |  |  | 891 | 891 | 0 | Tipper | 0.083333 | 74.25 | 74.25 | 0 | TRUE
OCB EQP -12 | EXE TXY P A-01.030 | Completed |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 176 | 0 | 0 | 3.2.2.5 |  |  | 891 | 891 | 0 | Water Bowser | 0.02 | 17.82 | 17.82 | 0 | TRUE
OCB EQP -2 | EXE TXY P A-01.030 | Completed |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 176 | 0 | 0 | 3.2.2.5 |  |  | 891 | 891 | 0 | dozer | 0.01 | 8.91 | 8.91 | 0 | TRUE
OCB EQP -4 | EXE TXY P A-01.030 | Completed |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 176 | 0 | 0 | 3.2.2.5 |  |  | 891 | 891 | 0 | vibratory road roller | 0.02 | 17.82 | 17.82 | 0 | TRUE
OCB EQP -3 | EXE TXY P A-01.040 | Completed |  |  | Nonlabor | Grader | 0 | 0 | 0 | 208 | 0 | 0 | 3.2.2.6 |  |  | 24817 | 21817 | 0 | motor grader | 0.01 | 248.17 | 218.17 | 0 | TRUE
OCB EQP -1 | EXE TXY P A-01.040 | Completed |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 2781 | 0 | 0 | 3.2.2.6 |  |  | 24817 | 21817 | 0 | hydraulic excavator | 0.02 | 496.34 | 436.34 | 0 | TRUE
OCB EQP -9 | EXE TXY P A-01.040 | Completed |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 208 | 0 | 0 | 3.2.2.6 |  |  | 24817 | 21817 | 0 | Tipper | 0.083333 | 2068.0833 | 1818.0833 | 0 | TRUE
OCB EQP -12 | EXE TXY P A-01.040 | Completed |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 208 | 0 | 0 | 3.2.2.6 |  |  | 24817 | 21817 | 0 | Water Bowser | 0.02 | 496.34 | 436.34 | 0 | TRUE
OCB EQP -2 | EXE TXY P A-01.040 | Completed |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 208 | 0 | 0 | 3.2.2.6 |  |  | 24817 | 21817 | 0 | dozer | 0.01 | 248.17 | 218.17 | 0 | TRUE
OCB EQP -4 | EXE TXY P A-01.040 | Completed |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 208 | 0 | 0 | 3.2.2.6 |  |  | 24817 | 21817 | 0 | vibratory road roller | 0.02 | 496.34 | 436.34 | 0 | TRUE
OCB EQP -10 | EXE CGD 1020 | In Progress |  |  | Nonlabor | Tractor with Ripper | 0 | 0 | 0 | 168 | 0 | 2 | 3.2.1.2 |  |  | 13875 | 2248 | 11628 | Tractor with ripper | 0.01 | 138.75 | 22.48 | 116.28 | TRUE
OCB EQP -11 | EXE CGD 1030 | In Progress |  |  | Nonlabor | Tractor / Trolley | 0 | 0 | 0 | 104 | 0 | 12 | 3.2.1.3 |  |  | 2175 | 310 | 1865 | [5 empty] | FALSE
OCB EQP -11 | EXE CGD 1040 | In Progress |  |  | Nonlabor | Tractor / Trolley | 0 | 0 | 0 | 40 | 0 | 60 | 3.2.1.4 |  |  | 11191 | 7193 | 3998 | [5 empty] | FALSE
OCB EQP -17 | EXE TXY P A-01.200 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 6000 | 0 | 6000 | [5 empty] | FALSE
OCB EQP -16 | EXE TXY P A-01.200 | Not Started |  |  | Nonlabor | Mechanical Broom | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 6000 | 0 | 6000 | [5 empty] | FALSE
OCB EQP -19 | EXE TXY P A-01.200 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 6000 | 0 | 6000 | [5 empty] | FALSE
OCB EQP -18 | EXE TXY P A-01.200 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 6000 | 0 | 6000 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-01.200 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 6000 | 0 | 6000 | [5 empty] | FALSE
OCB EQP -17 | EXE TXY P A-01.220 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 5888 | 0 | 5888 | [5 empty] | FALSE
OCB EQP -19 | EXE TXY P A-01.220 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 5888 | 0 | 5888 | [5 empty] | FALSE
OCB EQP -18 | EXE TXY P A-01.220 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 5888 | 0 | 5888 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-01.220 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 5888 | 0 | 5888 | [5 empty] | FALSE
OCB EQP -9 | EXE TXY P A-01.210 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 5 | 0 | 5 | 3.2.7.2 |  |  | 490 | 0 | 490 | [5 empty] | FALSE
OCB EQP -5 | EXE TXY P A-01.210 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.7.2 |  |  | 490 | 0 | 490 | [5 empty] | FALSE
OCB EQP -13 | EXE TXY P A-01.210 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.7.2 |  |  | 490 | 0 | 490 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-01.210 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.7.2 |  |  | 490 | 0 | 490 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-01.210 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.7.2 |  |  | 490 | 0 | 490 | [5 empty] | FALSE
OCB EQP -6 | EXE TXY P A-01.210 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 7 | 0 | 7 | 3.2.7.2 |  |  | 490 | 0 | 490 | [5 empty] | FALSE
OCB EQP -9 | EXE TXY P A-01.230 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 5 | 0 | 5 | 3.2.7.3 |  |  | 75 | 0 | 75 | [5 empty] | FALSE
OCB EQP -5 | EXE TXY P A-01.230 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.7.3 |  |  | 75 | 0 | 75 | [5 empty] | FALSE
OCB EQP -13 | EXE TXY P A-01.230 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.7.3 |  |  | 75 | 0 | 75 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-01.230 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.7.3 |  |  | 75 | 0 | 75 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-01.230 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.7.3 |  |  | 75 | 0 | 75 | [5 empty] | FALSE
OCB EQP -6 | EXE TXY P A-01.230 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 7 | 0 | 7 | 3.2.7.3 |  |  | 75 | 0 | 75 | [5 empty] | FALSE
OCB EQP -3 | EXE TXY P A-01.190 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.7.1 |  |  | 1750 | 0 | 1750 | [5 empty] | FALSE
OCB EQP -9 | EXE TXY P A-01.190 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 7 | 0 | 7 | 3.2.7.1 |  |  | 1750 | 0 | 1750 | [5 empty] | FALSE
OCB EQP -12 | EXE TXY P A-01.190 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.7.1 |  |  | 1750 | 0 | 1750 | [5 empty] | FALSE
OCB EQP -8 | EXE TXY P A-01.190 | Not Started |  |  | Nonlabor | Loader | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.7.1 |  |  | 1750 | 0 | 1750 | [5 empty] | FALSE
OCB EQP -4 | EXE TXY P A-01.190 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.7.1 |  |  | 1750 | 0 | 1750 | [5 empty] | FALSE
OCB EQP -3 | EXE TXY P A-03.040 | In Progress |  |  | Nonlabor | Grader | 0 | 0 | 0 | 360 | 0 | 4 | 3.2.2.6 |  |  | 30183 | 2879 | 27304 | motor grader | 0.01 | 301.83 | 28.79 | 273.04 | TRUE
OCB EQP -1 | EXE TXY P A-03.040 | In Progress |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 360 | 0 | 7 | 3.2.2.6 |  |  | 30183 | 2879 | 27304 | hydraulic excavator | 0.02 | 603.66 | 57.58 | 546.08 | TRUE
OCB EQP -9 | EXE TXY P A-03.040 | In Progress |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 360 | 0 | 30 | 3.2.2.6 |  |  | 30183 | 2879 | 27304 | Tipper | 0.083333 | 2515.25 | 239.9167 | 2275.3333 | TRUE
OCB EQP -12 | EXE TXY P A-03.040 | In Progress |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 360 | 0 | 7 | 3.2.2.6 |  |  | 30183 | 2879 | 27304 | Water Bowser | 0.02 | 603.66 | 57.58 | 546.08 | TRUE
OCB EQP -2 | EXE TXY P A-03.040 | In Progress |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 360 | 0 | 4 | 3.2.2.6 |  |  | 30183 | 2879 | 27304 | dozer | 0.01 | 301.83 | 28.79 | 273.04 | TRUE
OCB EQP -4 | EXE TXY P A-03.040 | In Progress |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 360 | 0 | 7 | 3.2.2.6 |  |  | 30183 | 2879 | 27304 | vibratory road roller | 0.02 | 603.66 | 57.58 | 546.08 | TRUE
OCB EQP -3 | EXE TXY P A-03.030 | In Progress |  |  | Nonlabor | Grader | 0 | 0 | 0 | 160 | 0 | 1 | 3.2.2.5 |  |  | 161006 | 151985 | 9021 | motor grader | 0.01 | 1610.06 | 1519.85 | 90.21 | TRUE
OCB EQP -1 | EXE TXY P A-03.030 | In Progress |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 160 | 0 | 2 | 3.2.2.5 |  |  | 161006 | 151985 | 9021 | hydraulic excavator | 0.02 | 3220.12 | 3039.7 | 180.42 | TRUE
OCB EQP -9 | EXE TXY P A-03.030 | In Progress |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 160 | 0 | 10 | 3.2.2.5 |  |  | 161006 | 151985 | 9021 | Tipper | 0.083333 | 13417.1667 | 12665.4167 | 751.75 | TRUE
OCB EQP -12 | EXE TXY P A-03.030 | In Progress |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 160 | 0 | 2 | 3.2.2.5 |  |  | 161006 | 151985 | 9021 | Water Bowser | 0.02 | 3220.12 | 3039.7 | 180.42 | TRUE
OCB EQP -2 | EXE TXY P A-03.030 | In Progress |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 160 | 0 | 1 | 3.2.2.5 |  |  | 161006 | 151985 | 9021 | dozer | 0.01 | 1610.06 | 1519.85 | 90.21 | TRUE
OCB EQP -4 | EXE TXY P A-03.030 | In Progress |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 160 | 0 | 2 | 3.2.2.5 |  |  | 161006 | 151985 | 9021 | vibratory road roller | 0.02 | 3220.12 | 3039.7 | 180.42 | TRUE
OCB EQP -3 | EX SR A-13.040 | In Progress |  |  | Nonlabor | Grader | 0 | 0 | 0 | 480 | 0 | 2 | 3.2.2.6 |  |  | 25000 | 13482 | 11518 | motor grader | 0.01 | 250 | 134.82 | 115.18 | TRUE
OCB EQP -1 | EX SR A-13.040 | In Progress |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 480 | 0 | 4 | 3.2.2.6 |  |  | 25000 | 13482 | 11518 | hydraulic excavator | 0.02 | 500 | 269.64 | 230.36 | TRUE
OCB EQP -9 | EX SR A-13.040 | In Progress |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 480 | 0 | 17 | 3.2.2.6 |  |  | 25000 | 13482 | 11518 | Tipper | 0.083333 | 2083.3333 | 1123.5 | 959.8333 | TRUE
OCB EQP -12 | EX SR A-13.040 | In Progress |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 480 | 0 | 4 | 3.2.2.6 |  |  | 25000 | 13482 | 11518 | Water Bowser | 0.02 | 500 | 269.64 | 230.36 | TRUE
OCB EQP -2 | EX SR A-13.040 | In Progress |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 480 | 0 | 2 | 3.2.2.6 |  |  | 25000 | 13482 | 11518 | dozer | 0.01 | 250 | 134.82 | 115.18 | TRUE
OCB EQP -4 | EX SR A-13.040 | In Progress |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 480 | 0 | 4 | 3.2.2.6 |  |  | 25000 | 13482 | 11518 | vibratory road roller | 0.02 | 500 | 269.64 | 230.36 | TRUE
OCB EQP -3 | EX SR A-13.030 | In Progress |  |  | Nonlabor | Grader | 0 | 0 | 0 | 80 | 0 | 2 | 3.2.2.5 |  |  | 20500 | 19923 | 577 | motor grader | 0.01 | 205 | 199.23 | 5.77 | TRUE
OCB EQP -1 | EX SR A-13.030 | In Progress |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 80 | 0 | 3 | 3.2.2.5 |  |  | 20500 | 19923 | 577 | hydraulic excavator | 0.02 | 410 | 398.46 | 11.54 | TRUE
OCB EQP -9 | EX SR A-13.030 | In Progress |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 80 | 0 | 13 | 3.2.2.5 |  |  | 20500 | 19923 | 577 | Tipper | 0.083333 | 1708.3333 | 1660.25 | 48.0833 | TRUE
OCB EQP -12 | EX SR A-13.030 | In Progress |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 80 | 0 | 3 | 3.2.2.5 |  |  | 20500 | 19923 | 577 | Water Bowser | 0.02 | 410 | 398.46 | 11.54 | TRUE
OCB EQP -2 | EX SR A-13.030 | In Progress |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 80 | 0 | 2 | 3.2.2.5 |  |  | 20500 | 19923 | 577 | dozer | 0.01 | 205 | 199.23 | 5.77 | TRUE
OCB EQP -4 | EX SR A-13.030 | In Progress |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 80 | 0 | 3 | 3.2.2.5 |  |  | 20500 | 19923 | 577 | vibratory road roller | 0.02 | 410 | 398.46 | 11.54 | TRUE
OCB EQP -3 | EXE TXY P A-04.040 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.2.6 |  |  | 13000 | 0 | 13000 | motor grader | 0.01 | 130 | 0 | 130 | TRUE
OCB EQP -1 | EXE TXY P A-04.040 | Not Started |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 6 | 0 | 6 | 3.2.2.6 |  |  | 13000 | 0 | 13000 | hydraulic excavator | 0.02 | 260 | 0 | 260 | TRUE
OCB EQP -9 | EXE TXY P A-04.040 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 23 | 0 | 23 | 3.2.2.6 |  |  | 13000 | 0 | 13000 | Tipper | 0.083333 | 1083.3333 | 0 | 1083.3333 | TRUE
OCB EQP -12 | EXE TXY P A-04.040 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 6 | 0 | 6 | 3.2.2.6 |  |  | 13000 | 0 | 13000 | Water Bowser | 0.02 | 260 | 0 | 260 | TRUE
OCB EQP -2 | EXE TXY P A-04.040 | Not Started |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.2.6 |  |  | 13000 | 0 | 13000 | dozer | 0.01 | 130 | 0 | 130 | TRUE
OCB EQP -4 | EXE TXY P A-04.040 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 6 | 0 | 6 | 3.2.2.6 |  |  | 13000 | 0 | 13000 | vibratory road roller | 0.02 | 260 | 0 | 260 | TRUE
OCB EQP -3 | EXE TXY P A-04.030 | In Progress |  |  | Nonlabor | Grader | 0 | 0 | 0 | 160 | 0 | 1 | 3.2.2.5 |  |  | 103844 | 70963 | 32881 | motor grader | 0.01 | 1038.44 | 709.63 | 328.81 | TRUE
OCB EQP -1 | EXE TXY P A-04.030 | In Progress |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 160 | 0 | 2 | 3.2.2.5 |  |  | 103844 | 70963 | 32881 | hydraulic excavator | 0.02 | 2076.88 | 1419.26 | 657.62 | TRUE
OCB EQP -9 | EXE TXY P A-04.030 | In Progress |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 160 | 0 | 10 | 3.2.2.5 |  |  | 103844 | 70963 | 32881 | Tipper | 0.083333 | 8653.6667 | 5913.5833 | 2740.0833 | TRUE
OCB EQP -12 | EXE TXY P A-04.030 | In Progress |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 160 | 0 | 2 | 3.2.2.5 |  |  | 103844 | 70963 | 32881 | Water Bowser | 0.02 | 2076.88 | 1419.26 | 657.62 | TRUE
OCB EQP -2 | EXE TXY P A-04.030 | In Progress |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 160 | 0 | 1 | 3.2.2.5 |  |  | 103844 | 70963 | 32881 | dozer | 0.01 | 1038.44 | 709.63 | 328.81 | TRUE
OCB EQP -4 | EXE TXY P A-04.030 | In Progress |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 160 | 0 | 2 | 3.2.2.5 |  |  | 103844 | 70963 | 32881 | vibratory road roller | 0.02 | 2076.88 | 1419.26 | 657.62 | TRUE
OCB EQP -1 | EX NOTM TX A-09L.020 | Completed |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 480 | 0 | 0 | 3.1.1.1a |  |  | 3150 | 3115 | 0 | hydraulic excavator | 0.025 | 78.75 | 77.875 | 0 | TRUE
OCB EQP -9 | EX NOTM TX A-09L.020 | Completed |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 480 | 0 | 0 | 3.1.1.1a |  |  | 3150 | 3115 | 0 | Tipper | 0.044 | 138.6 | 137.06 | 0 | TRUE
OCB EQP -3 | EX NOTM TX A-09L.030 | Completed |  |  | Nonlabor | Grader | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.2.5 |  |  | 100 | 0 | 0 | motor grader | 0.01 | 1 | 0 | 0 | TRUE
OCB EQP -1 | EX NOTM TX A-09L.030 | Completed |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.2.5 |  |  | 100 | 0 | 0 | hydraulic excavator | 0.02 | 2 | 0 | 0 | TRUE
OCB EQP -9 | EX NOTM TX A-09L.030 | Completed |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.2.5 |  |  | 100 | 0 | 0 | Tipper | 0.083333 | 8.3333 | 0 | 0 | TRUE
OCB EQP -12 | EX NOTM TX A-09L.030 | Completed |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.2.5 |  |  | 100 | 0 | 0 | Water Bowser | 0.02 | 2 | 0 | 0 | TRUE
OCB EQP -2 | EX NOTM TX A-09L.030 | Completed |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.2.5 |  |  | 100 | 0 | 0 | dozer | 0.01 | 1 | 0 | 0 | TRUE
OCB EQP -4 | EX NOTM TX A-09L.030 | Completed |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.2.5 |  |  | 100 | 0 | 0 | vibratory road roller | 0.02 | 2 | 0 | 0 | TRUE
OCB EQP -3 | EX NOTM TX A-09L.040 | Completed |  |  | Nonlabor | Grader | 0 | 0 | 0 | 480 | 0 | 0 | 3.2.2.6 |  |  | 2500 | 3437 | 0 | motor grader | 0.01 | 25 | 34.37 | 0 | TRUE
OCB EQP -1 | EX NOTM TX A-09L.040 | Completed |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 480 | 0 | 0 | 3.2.2.6 |  |  | 2500 | 3437 | 0 | hydraulic excavator | 0.02 | 50 | 68.74 | 0 | TRUE
OCB EQP -9 | EX NOTM TX A-09L.040 | Completed |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 480 | 0 | 0 | 3.2.2.6 |  |  | 2500 | 3437 | 0 | Tipper | 0.083333 | 208.3333 | 286.4167 | 0 | TRUE
OCB EQP -12 | EX NOTM TX A-09L.040 | Completed |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 480 | 0 | 0 | 3.2.2.6 |  |  | 2500 | 3437 | 0 | Water Bowser | 0.02 | 50 | 68.74 | 0 | TRUE
OCB EQP -2 | EX NOTM TX A-09L.040 | Completed |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 480 | 0 | 0 | 3.2.2.6 |  |  | 2500 | 3437 | 0 | dozer | 0.01 | 25 | 34.37 | 0 | TRUE
OCB EQP -4 | EX NOTM TX A-09L.040 | Completed |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 480 | 0 | 0 | 3.2.2.6 |  |  | 2500 | 3437 | 0 | vibratory road roller | 0.02 | 50 | 68.74 | 0 | TRUE
OCB EQP -1 | EX NOTM TX A-10K.020 | In Progress |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 480 | 0 | 1 | 3.1.1.1a |  |  | 6550 | 6543 | 7 | hydraulic excavator | 0.025 | 163.75 | 163.575 | 0.175 | TRUE
OCB EQP -9 | EX NOTM TX A-10K.020 | In Progress |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 480 | 0 | 2 | 3.1.1.1a |  |  | 6550 | 6543 | 7 | Tipper | 0.044 | 288.2 | 287.892 | 0.308 | TRUE
OCB EQP -3 | EX NOTM TX A-10K.030 | Completed |  |  | Nonlabor | Grader | 0 | 0 | 0 | 480 | 0 | 0 | 3.2.2.5 |  |  | 100 | 0 | 0 | motor grader | 0.01 | 1 | 0 | 0 | TRUE
OCB EQP -1 | EX NOTM TX A-10K.030 | Completed |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 480 | 0 | 0 | 3.2.2.5 |  |  | 100 | 0 | 0 | hydraulic excavator | 0.02 | 2 | 0 | 0 | TRUE
OCB EQP -9 | EX NOTM TX A-10K.030 | Completed |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 480 | 0 | 0 | 3.2.2.5 |  |  | 100 | 0 | 0 | Tipper | 0.083333 | 8.3333 | 0 | 0 | TRUE
OCB EQP -12 | EX NOTM TX A-10K.030 | Completed |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 480 | 0 | 0 | 3.2.2.5 |  |  | 100 | 0 | 0 | Water Bowser | 0.02 | 2 | 0 | 0 | TRUE
OCB EQP -2 | EX NOTM TX A-10K.030 | Completed |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 480 | 0 | 0 | 3.2.2.5 |  |  | 100 | 0 | 0 | dozer | 0.01 | 1 | 0 | 0 | TRUE
OCB EQP -4 | EX NOTM TX A-10K.030 | Completed |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 480 | 0 | 0 | 3.2.2.5 |  |  | 100 | 0 | 0 | vibratory road roller | 0.02 | 2 | 0 | 0 | TRUE
OCB EQP -3 | EX NOTM TX A-10K.040 | Completed |  |  | Nonlabor | Grader | 0 | 0 | 0 | 480 | 0 | 0 | 3.2.2.6 |  |  | 5600 | 5103 | 0 | motor grader | 0.01 | 56 | 51.03 | 0 | TRUE
OCB EQP -1 | EX NOTM TX A-10K.040 | Completed |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 480 | 0 | 0 | 3.2.2.6 |  |  | 5600 | 5103 | 0 | hydraulic excavator | 0.02 | 112 | 102.06 | 0 | TRUE
OCB EQP -9 | EX NOTM TX A-10K.040 | Completed |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 480 | 0 | 0 | 3.2.2.6 |  |  | 5600 | 5103 | 0 | Tipper | 0.083333 | 466.6667 | 425.25 | 0 | TRUE
OCB EQP -12 | EX NOTM TX A-10K.040 | Completed |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 480 | 0 | 0 | 3.2.2.6 |  |  | 5600 | 5103 | 0 | Water Bowser | 0.02 | 112 | 102.06 | 0 | TRUE
OCB EQP -2 | EX NOTM TX A-10K.040 | Completed |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 480 | 0 | 0 | 3.2.2.6 |  |  | 5600 | 5103 | 0 | dozer | 0.01 | 56 | 51.03 | 0 | TRUE
OCB EQP -4 | EX NOTM TX A-10K.040 | Completed |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 480 | 0 | 0 | 3.2.2.6 |  |  | 5600 | 5103 | 0 | vibratory road roller | 0.02 | 112 | 102.06 | 0 | TRUE
OCB EQP -3 | EXE TXY P A-04.060 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.1 |  |  | 2400 | 0 | 2400 | motor grader | 0.02 | 48 | 0 | 48 | TRUE
OCB EQP -9 | EXE TXY P A-04.060 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 17 | 0 | 17 | 3.2.3.1 |  |  | 2400 | 0 | 2400 | Tipper | 0.083333 | 200 | 0 | 200 | TRUE
OCB EQP -12 | EXE TXY P A-04.060 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 7 | 0 | 7 | 3.2.3.1 |  |  | 2400 | 0 | 2400 | Water Bowser | 0.033 | 79.2 | 0 | 79.2 | TRUE
OCB EQP -8 | EXE TXY P A-04.060 | Not Started |  |  | Nonlabor | Loader | 0 | 0 | 0 | 8 | 0 | 8 | 3.2.3.1 |  |  | 2400 | 0 | 2400 | Loader | 0.04 | 96 | 0 | 96 | TRUE
OCB EQP -4 | EXE TXY P A-04.060 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 8 | 0 | 8 | 3.2.3.1 |  |  | 2400 | 0 | 2400 | vibratory road roller | 0.04 | 96 | 0 | 96 | TRUE
OCB EQP -9 | EXE CGD 1010 | In Progress |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 200 | 0 | 0 | 3.2.1.1 |  |  | 6900 | 0 | 6900 | Tipper | 0.002 | 13.8 | 0 | 13.8 | TRUE
OCB EQP -8 | EXE CGD 1010 | In Progress |  |  | Nonlabor | Loader | 0 | 0 | 0 | 200 | 0 | 0 | 3.2.1.1 |  |  | 6900 | 0 | 6900 | Loader | 0.002 | 13.8 | 0 | 13.8 | TRUE
OCB EQP -10 | EXE CGD 1010 | In Progress |  |  | Nonlabor | Tractor with Ripper | 0 | 0 | 0 | 200 | 0 | 0 | 3.2.1.1 |  |  | 6900 | 0 | 6900 | Tractor with ripper | 0.002 | 13.8 | 0 | 13.8 | TRUE
OCB EQP -1 | EXE TXY P A-01.020 | Completed |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 488 | 0 | 0 | 3.1.1.1a |  |  | 33637 | 33637 | 0 | hydraulic excavator | 0.025 | 840.925 | 840.925 | 0 | TRUE
OCB EQP -9 | EXE TXY P A-01.020 | Completed |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 488 | 0 | 0 | 3.1.1.1a |  |  | 33637 | 33637 | 0 | Tipper | 0.044 | 1480.028 | 1480.028 | 0 | TRUE
OCB EQP -1 | EXE TXY P A-02.020 | Not Started |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 1 | 0 | 1 | 3.1.1.1a |  |  | 100 | 0 | 100 | hydraulic excavator | 0.025 | 2.5 | 0 | 2.5 | TRUE
OCB EQP -9 | EXE TXY P A-02.020 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 2 | 0 | 2 | 3.1.1.1a |  |  | 100 | 0 | 100 | Tipper | 0.044 | 4.4 | 0 | 4.4 | TRUE
OCB EQP -3 | EXE TXY P A-02.060 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.1 |  |  | 3200 | 0 | 3200 | motor grader | 0.02 | 64 | 0 | 64 | TRUE
OCB EQP -9 | EXE TXY P A-02.060 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 7 | 0 | 7 | 3.2.3.1 |  |  | 3200 | 0 | 3200 | Tipper | 0.083333 | 266.6667 | 0 | 266.6667 | TRUE
OCB EQP -12 | EXE TXY P A-02.060 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.1 |  |  | 3200 | 0 | 3200 | Water Bowser | 0.033 | 105.6 | 0 | 105.6 | TRUE
OCB EQP -8 | EXE TXY P A-02.060 | Not Started |  |  | Nonlabor | Loader | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.1 |  |  | 3200 | 0 | 3200 | Loader | 0.04 | 128 | 0 | 128 | TRUE
OCB EQP -4 | EXE TXY P A-02.060 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.1 |  |  | 3200 | 0 | 3200 | vibratory road roller | 0.04 | 128 | 0 | 128 | TRUE
OCB EQP -17 | EXE TXY P A-02.070 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.4 |  |  | 7632 | 0 | 7632 | Air compressor | 0.0016 | 12.2112 | 0 | 12.2112 | TRUE
OCB EQP -16 | EXE TXY P A-02.070 | Not Started |  |  | Nonlabor | Mechanical Broom | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.4 |  |  | 7632 | 0 | 7632 | Mechanical Broom | 0.0016 | 12.2112 | 0 | 12.2112 | TRUE
OCB EQP -19 | EXE TXY P A-02.070 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.4 |  |  | 7632 | 0 | 7632 | Boiler | 0.0016 | 12.2112 | 0 | 12.2112 | TRUE
OCB EQP -18 | EXE TXY P A-02.070 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.4 |  |  | 7632 | 0 | 7632 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-02.070 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.4 |  |  | 7632 | 0 | 7632 | Generator | 0.0016 | 12.2112 | 0 | 12.2112 | TRUE
OCB EQP -17 | EXE TXY P A-02.130 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.5 |  |  | 6500 | 0 | 6500 | Air compressor | 0.0012 | 7.8 | 0 | 7.8 | TRUE
OCB EQP -19 | EXE TXY P A-02.130 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.5 |  |  | 6500 | 0 | 6500 | Boiler | 0.0012 | 7.8 | 0 | 7.8 | TRUE
OCB EQP -18 | EXE TXY P A-02.130 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.5 |  |  | 6500 | 0 | 6500 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-02.130 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.5 |  |  | 6500 | 0 | 6500 | Generator | 0.0012 | 7.8 | 0 | 7.8 | TRUE
OCB EQP -9 | EXE TXY P A-02.080 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.2 |  |  | 565 | 0 | 565 | Tipper | 0.083333 | 47.0833 | 0 | 47.0833 | TRUE
OCB EQP -5 | EXE TXY P A-02.080 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 565 | 0 | 565 | Pneumatic Roller | 0.062827 | 35.4974 | 0 | 35.4974 | TRUE
OCB EQP -13 | EXE TXY P A-02.080 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 565 | 0 | 565 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-02.080 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 565 | 0 | 565 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-02.080 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 565 | 0 | 565 | Generator | 0.062827 | 35.4974 | 0 | 35.4974 | TRUE
OCB EQP -6 | EXE TXY P A-02.080 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.2 |  |  | 565 | 0 | 565 | Smooth wheel tandem roller | 0.12565 | 70.9948 | 0 | 70.9948 | TRUE
OCB EQP -17 | EXE TXY P A-02.150 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 7000 | 0 | 7000 | Air compressor | 0.0012 | 8.4 | 0 | 8.4 | TRUE
OCB EQP -19 | EXE TXY P A-02.150 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 7000 | 0 | 7000 | Boiler | 0.0012 | 8.4 | 0 | 8.4 | TRUE
OCB EQP -18 | EXE TXY P A-02.150 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 7000 | 0 | 7000 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-02.150 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 7000 | 0 | 7000 | Generator | 0.0012 | 8.4 | 0 | 8.4 | TRUE
OCB EQP -9 | EXE TXY P A-02.140 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.3 |  |  | 465 | 0 | 465 | Tipper | 0.083333 | 38.75 | 0 | 38.75 | TRUE
OCB EQP -5 | EXE TXY P A-02.140 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 465 | 0 | 465 | Pneumatic Roller | 0.062827 | 29.2147 | 0 | 29.2147 | TRUE
OCB EQP -13 | EXE TXY P A-02.140 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 465 | 0 | 465 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-02.140 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 465 | 0 | 465 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-02.140 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 465 | 0 | 465 | Generator | 0.062827 | 29.2147 | 0 | 29.2147 | TRUE
OCB EQP -6 | EXE TXY P A-02.140 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.3 |  |  | 465 | 0 | 465 | Smooth wheel tandem roller | 0.12565 | 58.4293 | 0 | 58.4293 | TRUE
OCB EQP -17 | EXE TXY P A-02.200 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 5300 | 0 | 5300 | [5 empty] | FALSE
OCB EQP -16 | EXE TXY P A-02.200 | Not Started |  |  | Nonlabor | Mechanical Broom | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 5300 | 0 | 5300 | [5 empty] | FALSE
OCB EQP -19 | EXE TXY P A-02.200 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 5300 | 0 | 5300 | [5 empty] | FALSE
OCB EQP -18 | EXE TXY P A-02.200 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 5300 | 0 | 5300 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-02.200 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 5300 | 0 | 5300 | [5 empty] | FALSE
OCB EQP -17 | EXE TXY P A-02.220 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 5278 | 0 | 5278 | [5 empty] | FALSE
OCB EQP -19 | EXE TXY P A-02.220 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 5278 | 0 | 5278 | [5 empty] | FALSE
OCB EQP -18 | EXE TXY P A-02.220 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 5278 | 0 | 5278 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-02.220 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 5278 | 0 | 5278 | [5 empty] | FALSE
OCB EQP -9 | EXE TXY P A-02.210 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.7.2 |  |  | 445 | 0 | 445 | [5 empty] | FALSE
OCB EQP -5 | EXE TXY P A-02.210 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.2 |  |  | 445 | 0 | 445 | [5 empty] | FALSE
OCB EQP -13 | EXE TXY P A-02.210 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.2 |  |  | 445 | 0 | 445 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-02.210 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.2 |  |  | 445 | 0 | 445 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-02.210 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.2 |  |  | 445 | 0 | 445 | [5 empty] | FALSE
OCB EQP -6 | EXE TXY P A-02.210 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.7.2 |  |  | 445 | 0 | 445 | [5 empty] | FALSE
OCB EQP -9 | EXE TXY P A-02.230 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.7.3 |  |  | 375 | 0 | 375 | [5 empty] | FALSE
OCB EQP -5 | EXE TXY P A-02.230 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.3 |  |  | 375 | 0 | 375 | [5 empty] | FALSE
OCB EQP -13 | EXE TXY P A-02.230 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.3 |  |  | 375 | 0 | 375 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-02.230 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.3 |  |  | 375 | 0 | 375 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-02.230 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.3 |  |  | 375 | 0 | 375 | [5 empty] | FALSE
OCB EQP -6 | EXE TXY P A-02.230 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.7.3 |  |  | 375 | 0 | 375 | [5 empty] | FALSE
OCB EQP -3 | EXE TXY P A-02.190 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.1 |  |  | 1585 | 0 | 1585 | [5 empty] | FALSE
OCB EQP -9 | EXE TXY P A-02.190 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 7 | 0 | 7 | 3.2.7.1 |  |  | 1585 | 0 | 1585 | [5 empty] | FALSE
OCB EQP -12 | EXE TXY P A-02.190 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.7.1 |  |  | 1585 | 0 | 1585 | [5 empty] | FALSE
OCB EQP -8 | EXE TXY P A-02.190 | Not Started |  |  | Nonlabor | Loader | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.7.1 |  |  | 1585 | 0 | 1585 | [5 empty] | FALSE
OCB EQP -4 | EXE TXY P A-02.190 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.7.1 |  |  | 1585 | 0 | 1585 | [5 empty] | FALSE
OCB EQP -1 | EXE TXY P A-03.020 | Not Started |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 2 | 0 | 2 | 3.1.1.1a |  |  | 100 | 0 | 100 | hydraulic excavator | 0.025 | 2.5 | 0 | 2.5 | TRUE
OCB EQP -9 | EXE TXY P A-03.020 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 4 | 0 | 4 | 3.1.1.1a |  |  | 100 | 0 | 100 | Tipper | 0.044 | 4.4 | 0 | 4.4 | TRUE
OCB EQP -3 | EXE TXY P A-03.060 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.1 |  |  | 4946 | 0 | 4946 | motor grader | 0.02 | 98.92 | 0 | 98.92 | TRUE
OCB EQP -9 | EXE TXY P A-03.060 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 10 | 0 | 10 | 3.2.3.1 |  |  | 4946 | 0 | 4946 | Tipper | 0.083333 | 412.1667 | 0 | 412.1667 | TRUE
OCB EQP -12 | EXE TXY P A-03.060 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.1 |  |  | 4946 | 0 | 4946 | Water Bowser | 0.033 | 163.218 | 0 | 163.218 | TRUE
OCB EQP -8 | EXE TXY P A-03.060 | Not Started |  |  | Nonlabor | Loader | 0 | 0 | 0 | 5 | 0 | 5 | 3.2.3.1 |  |  | 4946 | 0 | 4946 | Loader | 0.04 | 197.84 | 0 | 197.84 | TRUE
OCB EQP -4 | EXE TXY P A-03.060 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 5 | 0 | 5 | 3.2.3.1 |  |  | 4946 | 0 | 4946 | vibratory road roller | 0.04 | 197.84 | 0 | 197.84 | TRUE
OCB EQP -17 | EXE TXY P A-03.070 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.4 |  |  | 13000 | 0 | 13000 | Air compressor | 0.0016 | 20.8 | 0 | 20.8 | TRUE
OCB EQP -16 | EXE TXY P A-03.070 | Not Started |  |  | Nonlabor | Mechanical Broom | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.4 |  |  | 13000 | 0 | 13000 | Mechanical Broom | 0.0016 | 20.8 | 0 | 20.8 | TRUE
OCB EQP -19 | EXE TXY P A-03.070 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.4 |  |  | 13000 | 0 | 13000 | Boiler | 0.0016 | 20.8 | 0 | 20.8 | TRUE
OCB EQP -18 | EXE TXY P A-03.070 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.4 |  |  | 13000 | 0 | 13000 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-03.070 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.4 |  |  | 13000 | 0 | 13000 | Generator | 0.0016 | 20.8 | 0 | 20.8 | TRUE
OCB EQP -17 | EXE TXY P A-03.130 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.5 |  |  | 12000 | 0 | 12000 | Air compressor | 0.0012 | 14.4 | 0 | 14.4 | TRUE
OCB EQP -19 | EXE TXY P A-03.130 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.5 |  |  | 12000 | 0 | 12000 | Boiler | 0.0012 | 14.4 | 0 | 14.4 | TRUE
OCB EQP -18 | EXE TXY P A-03.130 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.5 |  |  | 12000 | 0 | 12000 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-03.130 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.5 |  |  | 12000 | 0 | 12000 | Generator | 0.0012 | 14.4 | 0 | 14.4 | TRUE
OCB EQP -9 | EXE TXY P A-03.080 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.2 |  |  | 900 | 0 | 900 | Tipper | 0.083333 | 75 | 0 | 75 | TRUE
OCB EQP -5 | EXE TXY P A-03.080 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 900 | 0 | 900 | Pneumatic Roller | 0.062827 | 56.5445 | 0 | 56.5445 | TRUE
OCB EQP -13 | EXE TXY P A-03.080 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 900 | 0 | 900 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-03.080 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 900 | 0 | 900 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-03.080 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 900 | 0 | 900 | Generator | 0.062827 | 56.5445 | 0 | 56.5445 | TRUE
OCB EQP -6 | EXE TXY P A-03.080 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.2 |  |  | 900 | 0 | 900 | Smooth wheel tandem roller | 0.12565 | 113.089 | 0 | 113.089 | TRUE
OCB EQP -17 | EXE TXY P A-03.090 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 12000 | 0 | 12000 | Air compressor | 0.0012 | 14.4 | 0 | 14.4 | TRUE
OCB EQP -19 | EXE TXY P A-03.090 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 12000 | 0 | 12000 | Boiler | 0.0012 | 14.4 | 0 | 14.4 | TRUE
OCB EQP -18 | EXE TXY P A-03.090 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 12000 | 0 | 12000 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-03.090 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 12000 | 0 | 12000 | Generator | 0.0012 | 14.4 | 0 | 14.4 | TRUE
OCB EQP -9 | EXE TXY P A-03.140 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.3 |  |  | 590 | 0 | 590 | Tipper | 0.083333 | 49.1667 | 0 | 49.1667 | TRUE
OCB EQP -5 | EXE TXY P A-03.140 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 590 | 0 | 590 | Pneumatic Roller | 0.062827 | 37.0681 | 0 | 37.0681 | TRUE
OCB EQP -13 | EXE TXY P A-03.140 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 590 | 0 | 590 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-03.140 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 590 | 0 | 590 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-03.140 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 590 | 0 | 590 | Generator | 0.062827 | 37.0681 | 0 | 37.0681 | TRUE
OCB EQP -6 | EXE TXY P A-03.140 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.3 |  |  | 590 | 0 | 590 | Smooth wheel tandem roller | 0.12565 | 74.1361 | 0 | 74.1361 | TRUE
OCB EQP -17 | EXE TXY P A-03.200 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 6550 | 0 | 6550 | [5 empty] | FALSE
OCB EQP -16 | EXE TXY P A-03.200 | Not Started |  |  | Nonlabor | Mechanical Broom | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 6550 | 0 | 6550 | [5 empty] | FALSE
OCB EQP -19 | EXE TXY P A-03.200 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 6550 | 0 | 6550 | [5 empty] | FALSE
OCB EQP -18 | EXE TXY P A-03.200 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 6550 | 0 | 6550 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-03.200 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 6550 | 0 | 6550 | [5 empty] | FALSE
OCB EQP -17 | EXE TXY P A-03.220 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 6548 | 0 | 6548 | [5 empty] | FALSE
OCB EQP -19 | EXE TXY P A-03.220 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 6548 | 0 | 6548 | [5 empty] | FALSE
OCB EQP -18 | EXE TXY P A-03.220 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 6548 | 0 | 6548 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-03.220 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 6548 | 0 | 6548 | [5 empty] | FALSE
OCB EQP -9 | EXE TXY P A-03.210 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.7.2 |  |  | 545 | 0 | 545 | [5 empty] | FALSE
OCB EQP -5 | EXE TXY P A-03.210 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.2 |  |  | 545 | 0 | 545 | [5 empty] | FALSE
OCB EQP -13 | EXE TXY P A-03.210 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.2 |  |  | 545 | 0 | 545 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-03.210 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.2 |  |  | 545 | 0 | 545 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-03.210 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.2 |  |  | 545 | 0 | 545 | [5 empty] | FALSE
OCB EQP -6 | EXE TXY P A-03.210 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.7.2 |  |  | 545 | 0 | 545 | [5 empty] | FALSE
OCB EQP -9 | EXE TXY P A-03.230 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.7.3 |  |  | 465 | 0 | 465 | [5 empty] | FALSE
OCB EQP -5 | EXE TXY P A-03.230 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.3 |  |  | 465 | 0 | 465 | [5 empty] | FALSE
OCB EQP -13 | EXE TXY P A-03.230 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.3 |  |  | 465 | 0 | 465 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-03.230 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.3 |  |  | 465 | 0 | 465 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-03.230 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.3 |  |  | 465 | 0 | 465 | [5 empty] | FALSE
OCB EQP -6 | EXE TXY P A-03.230 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.7.3 |  |  | 465 | 0 | 465 | [5 empty] | FALSE
OCB EQP -3 | EXE TXY P A-03.190 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.7.1 |  |  | 1970 | 0 | 1970 | [5 empty] | FALSE
OCB EQP -9 | EXE TXY P A-03.190 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 13 | 0 | 13 | 3.2.7.1 |  |  | 1970 | 0 | 1970 | [5 empty] | FALSE
OCB EQP -12 | EXE TXY P A-03.190 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 5 | 0 | 5 | 3.2.7.1 |  |  | 1970 | 0 | 1970 | [5 empty] | FALSE
OCB EQP -8 | EXE TXY P A-03.190 | Not Started |  |  | Nonlabor | Loader | 0 | 0 | 0 | 6 | 0 | 6 | 3.2.7.1 |  |  | 1970 | 0 | 1970 | [5 empty] | FALSE
OCB EQP -4 | EXE TXY P A-03.190 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 6 | 0 | 6 | 3.2.7.1 |  |  | 1970 | 0 | 1970 | [5 empty] | FALSE
OCB EQP -1 | EXE TXY P A-04.020 | Not Started |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 1 | 0 | 1 | 3.1.1.1a |  |  | 100 | 0 | 100 | hydraulic excavator | 0.025 | 2.5 | 0 | 2.5 | TRUE
OCB EQP -9 | EXE TXY P A-04.020 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 2 | 0 | 2 | 3.1.1.1a |  |  | 100 | 0 | 100 | Tipper | 0.044 | 4.4 | 0 | 4.4 | TRUE
OCB EQP -17 | EXE TXY P A-04.070 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.4 |  |  | 5000 | 0 | 5000 | Air compressor | 0.0016 | 8 | 0 | 8 | TRUE
OCB EQP -16 | EXE TXY P A-04.070 | Not Started |  |  | Nonlabor | Mechanical Broom | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.4 |  |  | 5000 | 0 | 5000 | Mechanical Broom | 0.0016 | 8 | 0 | 8 | TRUE
OCB EQP -19 | EXE TXY P A-04.070 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.4 |  |  | 5000 | 0 | 5000 | Boiler | 0.0016 | 8 | 0 | 8 | TRUE
OCB EQP -18 | EXE TXY P A-04.070 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.4 |  |  | 5000 | 0 | 5000 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-04.070 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.4 |  |  | 5000 | 0 | 5000 | Generator | 0.0016 | 8 | 0 | 8 | TRUE
OCB EQP -17 | EXE TXY P A-04.130 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.5 |  |  | 5000 | 0 | 5000 | Air compressor | 0.0012 | 6 | 0 | 6 | TRUE
OCB EQP -19 | EXE TXY P A-04.130 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.5 |  |  | 5000 | 0 | 5000 | Boiler | 0.0012 | 6 | 0 | 6 | TRUE
OCB EQP -18 | EXE TXY P A-04.130 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.5 |  |  | 5000 | 0 | 5000 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-04.130 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.5 |  |  | 5000 | 0 | 5000 | Generator | 0.0012 | 6 | 0 | 6 | TRUE
OCB EQP -9 | EXE TXY P A-04.080 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.2 |  |  | 410 | 0 | 410 | Tipper | 0.083333 | 34.1667 | 0 | 34.1667 | TRUE
OCB EQP -5 | EXE TXY P A-04.080 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 410 | 0 | 410 | Pneumatic Roller | 0.062827 | 25.7592 | 0 | 25.7592 | TRUE
OCB EQP -13 | EXE TXY P A-04.080 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 410 | 0 | 410 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-04.080 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 410 | 0 | 410 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-04.080 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 410 | 0 | 410 | Generator | 0.062827 | 25.7592 | 0 | 25.7592 | TRUE
OCB EQP -6 | EXE TXY P A-04.080 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.2 |  |  | 410 | 0 | 410 | Smooth wheel tandem roller | 0.12565 | 51.5183 | 0 | 51.5183 | TRUE
OCB EQP -17 | EXE TXY P A-04.090 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 5500 | 0 | 5500 | Air compressor | 0.0012 | 6.6 | 0 | 6.6 | TRUE
OCB EQP -19 | EXE TXY P A-04.090 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 5500 | 0 | 5500 | Boiler | 0.0012 | 6.6 | 0 | 6.6 | TRUE
OCB EQP -18 | EXE TXY P A-04.090 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 5500 | 0 | 5500 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-04.090 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 5500 | 0 | 5500 | Generator | 0.0012 | 6.6 | 0 | 6.6 | TRUE
OCB EQP -9 | EXE TXY P A-04.160 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.3 |  |  | 330 | 0 | 330 | Tipper | 0.083333 | 27.5 | 0 | 27.5 | TRUE
OCB EQP -5 | EXE TXY P A-04.160 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 330 | 0 | 330 | Pneumatic Roller | 0.062827 | 20.733 | 0 | 20.733 | TRUE
OCB EQP -13 | EXE TXY P A-04.160 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 330 | 0 | 330 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-04.160 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 330 | 0 | 330 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-04.160 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 330 | 0 | 330 | Generator | 0.062827 | 20.733 | 0 | 20.733 | TRUE
OCB EQP -6 | EXE TXY P A-04.160 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.3 |  |  | 330 | 0 | 330 | Smooth wheel tandem roller | 0.12565 | 41.466 | 0 | 41.466 | TRUE
OCB EQP -17 | EXE TXY P A-04.200 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 3400 | 0 | 3400 | [5 empty] | FALSE
OCB EQP -16 | EXE TXY P A-04.200 | Not Started |  |  | Nonlabor | Mechanical Broom | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 3400 | 0 | 3400 | [5 empty] | FALSE
OCB EQP -19 | EXE TXY P A-04.200 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 3400 | 0 | 3400 | [5 empty] | FALSE
OCB EQP -18 | EXE TXY P A-04.200 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 3400 | 0 | 3400 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-04.200 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 3400 | 0 | 3400 | [5 empty] | FALSE
OCB EQP -17 | EXE TXY P A-04.220 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 3396 | 0 | 3396 | [5 empty] | FALSE
OCB EQP -19 | EXE TXY P A-04.220 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 3396 | 0 | 3396 | [5 empty] | FALSE
OCB EQP -18 | EXE TXY P A-04.220 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 3396 | 0 | 3396 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-04.220 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 3396 | 0 | 3396 | [5 empty] | FALSE
OCB EQP -9 | EXE TXY P A-04.210 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.7.2 |  |  | 300 | 0 | 300 | [5 empty] | FALSE
OCB EQP -5 | EXE TXY P A-04.210 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.2 |  |  | 300 | 0 | 300 | [5 empty] | FALSE
OCB EQP -13 | EXE TXY P A-04.210 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.2 |  |  | 300 | 0 | 300 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-04.210 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.2 |  |  | 300 | 0 | 300 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-04.210 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.2 |  |  | 300 | 0 | 300 | [5 empty] | FALSE
OCB EQP -6 | EXE TXY P A-04.210 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.7.2 |  |  | 300 | 0 | 300 | [5 empty] | FALSE
OCB EQP -9 | EXE TXY P A-04.230 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.7.3 |  |  | 150 | 0 | 150 | [5 empty] | FALSE
OCB EQP -5 | EXE TXY P A-04.230 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.3 |  |  | 150 | 0 | 150 | [5 empty] | FALSE
OCB EQP -13 | EXE TXY P A-04.230 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.3 |  |  | 150 | 0 | 150 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-04.230 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.3 |  |  | 150 | 0 | 150 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-04.230 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.3 |  |  | 150 | 0 | 150 | [5 empty] | FALSE
OCB EQP -6 | EXE TXY P A-04.230 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.7.3 |  |  | 150 | 0 | 150 | [5 empty] | FALSE
OCB EQP -17 | EX NOTM TX A-09L.070 | Completed |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 8 | 0 | 0 | 3.2.6.4 |  |  | 3741 | 4322 | 0 | [5 empty] | FALSE
OCB EQP -16 | EX NOTM TX A-09L.070 | Completed |  |  | Nonlabor | Mechanical Broom | 0 | 0 | 0 | 8 | 0 | 0 | 3.2.6.4 |  |  | 3741 | 4322 | 0 | [5 empty] | FALSE
OCB EQP -19 | EX NOTM TX A-09L.070 | Completed |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 8 | 0 | 0 | 3.2.6.4 |  |  | 3741 | 4322 | 0 | [5 empty] | FALSE
OCB EQP -18 | EX NOTM TX A-09L.070 | Completed |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 8 | 0 | 0 | 3.2.6.4 |  |  | 3741 | 4322 | 0 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-09L.070 | Completed |  |  | Nonlabor | Generator | 0 | 0 | 0 | 8 | 0 | 0 | 3.2.6.4 |  |  | 3741 | 4322 | 0 | [5 empty] | FALSE
OCB EQP -17 | EX NOTM TX A-09L.130 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.6.5 |  |  | 3653 | 0 | 3653 | [5 empty] | FALSE
OCB EQP -19 | EX NOTM TX A-09L.130 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.6.5 |  |  | 3653 | 0 | 3653 | [5 empty] | FALSE
OCB EQP -18 | EX NOTM TX A-09L.130 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.6.5 |  |  | 3653 | 0 | 3653 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-09L.130 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.6.5 |  |  | 3653 | 0 | 3653 | [5 empty] | FALSE
OCB EQP -9 | EX NOTM TX A-09L.080 | Completed |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.6.2 |  |  | 280 | 292 | 0 | [5 empty] | FALSE
OCB EQP -5 | EX NOTM TX A-09L.080 | Completed |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.6.2 |  |  | 280 | 292 | 0 | [5 empty] | FALSE
OCB EQP -13 | EX NOTM TX A-09L.080 | Completed |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.6.2 |  |  | 280 | 292 | 0 | [5 empty] | FALSE
OCB EQP -14 | EX NOTM TX A-09L.080 | Completed |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.6.2 |  |  | 280 | 292 | 0 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-09L.080 | Completed |  |  | Nonlabor | Generator | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.6.2 |  |  | 280 | 292 | 0 | [5 empty] | FALSE
OCB EQP -6 | EX NOTM TX A-09L.080 | Completed |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.6.2 |  |  | 280 | 292 | 0 | [5 empty] | FALSE
OCB EQP -17 | EX NOTM TX A-09L.090 | Completed |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 8 | 0 | 0 | 3.2.6.6 |  |  | 3650 | 4322 | 0 | [5 empty] | FALSE
OCB EQP -19 | EX NOTM TX A-09L.090 | Completed |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 8 | 0 | 0 | 3.2.6.6 |  |  | 3650 | 4322 | 0 | [5 empty] | FALSE
OCB EQP -18 | EX NOTM TX A-09L.090 | Completed |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 8 | 0 | 0 | 3.2.6.6 |  |  | 3650 | 4322 | 0 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-09L.090 | Completed |  |  | Nonlabor | Generator | 0 | 0 | 0 | 8 | 0 | 0 | 3.2.6.6 |  |  | 3650 | 4322 | 0 | [5 empty] | FALSE
OCB EQP -9 | EX NOTM TX A-09L.140 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.6.3 |  |  | 218 | 0 | 218 | [5 empty] | FALSE
OCB EQP -5 | EX NOTM TX A-09L.140 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.6.3 |  |  | 218 | 0 | 218 | [5 empty] | FALSE
OCB EQP -13 | EX NOTM TX A-09L.140 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.6.3 |  |  | 218 | 0 | 218 | [5 empty] | FALSE
OCB EQP -14 | EX NOTM TX A-09L.140 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.6.3 |  |  | 218 | 0 | 218 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-09L.140 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.6.3 |  |  | 218 | 0 | 218 | [5 empty] | FALSE
OCB EQP -6 | EX NOTM TX A-09L.140 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.6.3 |  |  | 218 | 0 | 218 | [5 empty] | FALSE
OCB EQP -3 | EX NOTM TX A-09L.060 | Completed |  |  | Nonlabor | Grader | 0 | 0 | 0 | 240 | 0 | 0 | 3.2.6.1 |  |  | 1496 | 1299 | 0 | [5 empty] | FALSE
OCB EQP -9 | EX NOTM TX A-09L.060 | Completed |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 240 | 0 | 0 | 3.2.6.1 |  |  | 1496 | 1299 | 0 | [5 empty] | FALSE
OCB EQP -12 | EX NOTM TX A-09L.060 | Completed |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 240 | 0 | 0 | 3.2.6.1 |  |  | 1496 | 1299 | 0 | [5 empty] | FALSE
OCB EQP -8 | EX NOTM TX A-09L.060 | Completed |  |  | Nonlabor | Loader | 0 | 0 | 0 | 240 | 0 | 0 | 3.2.6.1 |  |  | 1496 | 1299 | 0 | [5 empty] | FALSE
OCB EQP -4 | EX NOTM TX A-09L.060 | Completed |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 240 | 0 | 0 | 3.2.6.1 |  |  | 1496 | 1299 | 0 | [5 empty] | FALSE
OCB EQP -17 | EX NOTM TX A-10K.070 | Completed |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.4 |  |  | 6454 | 6045 | 0 | [5 empty] | FALSE
OCB EQP -16 | EX NOTM TX A-10K.070 | Completed |  |  | Nonlabor | Mechanical Broom | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.4 |  |  | 6454 | 6045 | 0 | [5 empty] | FALSE
OCB EQP -19 | EX NOTM TX A-10K.070 | Completed |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.4 |  |  | 6454 | 6045 | 0 | [5 empty] | FALSE
OCB EQP -18 | EX NOTM TX A-10K.070 | Completed |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.4 |  |  | 6454 | 6045 | 0 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-10K.070 | Completed |  |  | Nonlabor | Generator | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.4 |  |  | 6454 | 6045 | 0 | [5 empty] | FALSE
OCB EQP -17 | EX NOTM TX A-10K.130 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.5.5 |  |  | 6327 | 0 | 6327 | [5 empty] | FALSE
OCB EQP -19 | EX NOTM TX A-10K.130 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.5.5 |  |  | 6327 | 0 | 6327 | [5 empty] | FALSE
OCB EQP -18 | EX NOTM TX A-10K.130 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.5.5 |  |  | 6327 | 0 | 6327 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-10K.130 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.5.5 |  |  | 6327 | 0 | 6327 | [5 empty] | FALSE
OCB EQP -9 | EX NOTM TX A-10K.080 | Completed |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.2 |  |  | 505 | 506 | 0 | [5 empty] | FALSE
OCB EQP -5 | EX NOTM TX A-10K.080 | Completed |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.2 |  |  | 505 | 506 | 0 | [5 empty] | FALSE
OCB EQP -13 | EX NOTM TX A-10K.080 | Completed |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.2 |  |  | 505 | 506 | 0 | [5 empty] | FALSE
OCB EQP -14 | EX NOTM TX A-10K.080 | Completed |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.2 |  |  | 505 | 506 | 0 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-10K.080 | Completed |  |  | Nonlabor | Generator | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.2 |  |  | 505 | 506 | 0 | [5 empty] | FALSE
OCB EQP -6 | EX NOTM TX A-10K.080 | Completed |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.2 |  |  | 505 | 506 | 0 | [5 empty] | FALSE
OCB EQP -17 | EX NOTM TX A-10K.090 | Completed |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.6 |  |  | 6326 | 5820 | 0 | [5 empty] | FALSE
OCB EQP -19 | EX NOTM TX A-10K.090 | Completed |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.6 |  |  | 6326 | 5820 | 0 | [5 empty] | FALSE
OCB EQP -18 | EX NOTM TX A-10K.090 | Completed |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.6 |  |  | 6326 | 5820 | 0 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-10K.090 | Completed |  |  | Nonlabor | Generator | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.6 |  |  | 6326 | 5820 | 0 | [5 empty] | FALSE
OCB EQP -9 | EX NOTM TX A-10K.140 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.5.3 |  |  | 380 | 0 | 380 | [5 empty] | FALSE
OCB EQP -5 | EX NOTM TX A-10K.140 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.5.3 |  |  | 380 | 0 | 380 | [5 empty] | FALSE
OCB EQP -13 | EX NOTM TX A-10K.140 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.5.3 |  |  | 380 | 0 | 380 | [5 empty] | FALSE
OCB EQP -14 | EX NOTM TX A-10K.140 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.5.3 |  |  | 380 | 0 | 380 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-10K.140 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.5.3 |  |  | 380 | 0 | 380 | [5 empty] | FALSE
OCB EQP -6 | EX NOTM TX A-10K.140 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.5.3 |  |  | 380 | 0 | 380 | [5 empty] | FALSE
OCB EQP -3 | EX NOTM TX A-10K.060 | Completed |  |  | Nonlabor | Grader | 0 | 0 | 0 | 240 | 0 | 0 | 3.2.5.1 |  |  | 2581 | 1717 | 0 | [5 empty] | FALSE
OCB EQP -9 | EX NOTM TX A-10K.060 | Completed |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 240 | 0 | 0 | 3.2.5.1 |  |  | 2581 | 1717 | 0 | [5 empty] | FALSE
OCB EQP -12 | EX NOTM TX A-10K.060 | Completed |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 240 | 0 | 0 | 3.2.5.1 |  |  | 2581 | 1717 | 0 | [5 empty] | FALSE
OCB EQP -8 | EX NOTM TX A-10K.060 | Completed |  |  | Nonlabor | Loader | 0 | 0 | 0 | 240 | 0 | 0 | 3.2.5.1 |  |  | 2581 | 1717 | 0 | [5 empty] | FALSE
OCB EQP -4 | EX NOTM TX A-10K.060 | Completed |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 240 | 0 | 0 | 3.2.5.1 |  |  | 2581 | 1717 | 0 | [5 empty] | FALSE
OCB EQP -1 | EX SR A-13.020 | In Progress |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 80 | 0 | 3 | 3.1.1.1a |  |  | 28760 | 28759 | 1 | hydraulic excavator | 0.025 | 719 | 718.975 | 0.025 | TRUE
OCB EQP -9 | EX SR A-13.020 | In Progress |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 80 | 0 | 5 | 3.1.1.1a |  |  | 28760 | 28759 | 1 | Tipper | 0.044 | 1265.44 | 1265.396 | 0.044 | TRUE
OCB EQP -17 | EX NOTM TX A-09L.200 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 8 | 0 | 8 | 3.2.7.4 |  |  | 1550 | 0 | 1550 | [5 empty] | FALSE
OCB EQP -16 | EX NOTM TX A-09L.200 | Not Started |  |  | Nonlabor | Mechanical Broom | 0 | 0 | 0 | 8 | 0 | 8 | 3.2.7.4 |  |  | 1550 | 0 | 1550 | [5 empty] | FALSE
OCB EQP -19 | EX NOTM TX A-09L.200 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 8 | 0 | 8 | 3.2.7.4 |  |  | 1550 | 0 | 1550 | [5 empty] | FALSE
OCB EQP -18 | EX NOTM TX A-09L.200 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 8 | 0 | 8 | 3.2.7.4 |  |  | 1550 | 0 | 1550 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-09L.200 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 8 | 0 | 8 | 3.2.7.4 |  |  | 1550 | 0 | 1550 | [5 empty] | FALSE
OCB EQP -17 | EX NOTM TX A-09L.220 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 8 | 0 | 8 | 3.2.7.5 |  |  | 1544 | 0 | 1544 | [5 empty] | FALSE
OCB EQP -19 | EX NOTM TX A-09L.220 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 8 | 0 | 8 | 3.2.7.5 |  |  | 1544 | 0 | 1544 | [5 empty] | FALSE
OCB EQP -18 | EX NOTM TX A-09L.220 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 8 | 0 | 8 | 3.2.7.5 |  |  | 1544 | 0 | 1544 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-09L.220 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 8 | 0 | 8 | 3.2.7.5 |  |  | 1544 | 0 | 1544 | [5 empty] | FALSE
OCB EQP -9 | EX NOTM TX A-09L.210 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 16 | 0 | 16 | 3.2.7.2 |  |  | 60 | 0 | 60 | [5 empty] | FALSE
OCB EQP -5 | EX NOTM TX A-09L.210 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 16 | 0 | 16 | 3.2.7.2 |  |  | 60 | 0 | 60 | [5 empty] | FALSE
OCB EQP -13 | EX NOTM TX A-09L.210 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 16 | 0 | 16 | 3.2.7.2 |  |  | 60 | 0 | 60 | [5 empty] | FALSE
OCB EQP -14 | EX NOTM TX A-09L.210 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 16 | 0 | 16 | 3.2.7.2 |  |  | 60 | 0 | 60 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-09L.210 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 16 | 0 | 16 | 3.2.7.2 |  |  | 60 | 0 | 60 | [5 empty] | FALSE
OCB EQP -6 | EX NOTM TX A-09L.210 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 16 | 0 | 16 | 3.2.7.2 |  |  | 60 | 0 | 60 | [5 empty] | FALSE
OCB EQP -9 | EX NOTM TX A-09L.230 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.7.3 |  |  | 100 | 0 | 100 | [5 empty] | FALSE
OCB EQP -5 | EX NOTM TX A-09L.230 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.7.3 |  |  | 100 | 0 | 100 | [5 empty] | FALSE
OCB EQP -13 | EX NOTM TX A-09L.230 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.7.3 |  |  | 100 | 0 | 100 | [5 empty] | FALSE
OCB EQP -14 | EX NOTM TX A-09L.230 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.7.3 |  |  | 100 | 0 | 100 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-09L.230 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.7.3 |  |  | 100 | 0 | 100 | [5 empty] | FALSE
OCB EQP -6 | EX NOTM TX A-09L.230 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.3 |  |  | 100 | 0 | 100 | [5 empty] | FALSE
OCB EQP -3 | EX NOTM TX A-09L.190 | Completed |  |  | Nonlabor | Grader | 0 | 0 | 0 | 80 | 0 | 0 | 3.2.7.1 |  |  | 340 | 387 | 0 | [5 empty] | FALSE
OCB EQP -9 | EX NOTM TX A-09L.190 | Completed |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 80 | 0 | 0 | 3.2.7.1 |  |  | 340 | 387 | 0 | [5 empty] | FALSE
OCB EQP -12 | EX NOTM TX A-09L.190 | Completed |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 80 | 0 | 0 | 3.2.7.1 |  |  | 340 | 387 | 0 | [5 empty] | FALSE
OCB EQP -8 | EX NOTM TX A-09L.190 | Completed |  |  | Nonlabor | Loader | 0 | 0 | 0 | 80 | 0 | 0 | 3.2.7.1 |  |  | 340 | 387 | 0 | [5 empty] | FALSE
OCB EQP -4 | EX NOTM TX A-09L.190 | Completed |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 80 | 0 | 0 | 3.2.7.1 |  |  | 340 | 387 | 0 | [5 empty] | FALSE
OCB EQP -17 | EX NOTM TX A-10K.200 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 1220 | 0 | 1220 | [5 empty] | FALSE
OCB EQP -16 | EX NOTM TX A-10K.200 | Not Started |  |  | Nonlabor | Mechanical Broom | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 1220 | 0 | 1220 | [5 empty] | FALSE
OCB EQP -19 | EX NOTM TX A-10K.200 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 1220 | 0 | 1220 | [5 empty] | FALSE
OCB EQP -18 | EX NOTM TX A-10K.200 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 1220 | 0 | 1220 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-10K.200 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 1220 | 0 | 1220 | [5 empty] | FALSE
OCB EQP -17 | EX NOTM TX A-10K.220 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 1215 | 0 | 1215 | [5 empty] | FALSE
OCB EQP -19 | EX NOTM TX A-10K.220 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 1215 | 0 | 1215 | [5 empty] | FALSE
OCB EQP -18 | EX NOTM TX A-10K.220 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 1215 | 0 | 1215 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-10K.220 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 1215 | 0 | 1215 | [5 empty] | FALSE
OCB EQP -9 | EX NOTM TX A-10K.210 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.7.2 |  |  | 110 | 0 | 110 | [5 empty] | FALSE
OCB EQP -5 | EX NOTM TX A-10K.210 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.7.2 |  |  | 110 | 0 | 110 | [5 empty] | FALSE
OCB EQP -13 | EX NOTM TX A-10K.210 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.7.2 |  |  | 110 | 0 | 110 | [5 empty] | FALSE
OCB EQP -14 | EX NOTM TX A-10K.210 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.7.2 |  |  | 110 | 0 | 110 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-10K.210 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.7.2 |  |  | 110 | 0 | 110 | [5 empty] | FALSE
OCB EQP -6 | EX NOTM TX A-10K.210 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.2 |  |  | 110 | 0 | 110 | [5 empty] | FALSE
OCB EQP -9 | EX NOTM TX A-10K.230 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.7.3 |  |  | 90 | 0 | 90 | [5 empty] | FALSE
OCB EQP -5 | EX NOTM TX A-10K.230 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.7.3 |  |  | 90 | 0 | 90 | [5 empty] | FALSE
OCB EQP -13 | EX NOTM TX A-10K.230 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.7.3 |  |  | 90 | 0 | 90 | [5 empty] | FALSE
OCB EQP -14 | EX NOTM TX A-10K.230 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.7.3 |  |  | 90 | 0 | 90 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-10K.230 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.7.3 |  |  | 90 | 0 | 90 | [5 empty] | FALSE
OCB EQP -6 | EX NOTM TX A-10K.230 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.3 |  |  | 90 | 0 | 90 | [5 empty] | FALSE
OCB EQP -3 | EX NOTM TX A-10K.190 | Completed |  |  | Nonlabor | Grader | 0 | 0 | 0 | 80 | 0 | 0 | 3.2.7.1 |  |  | 545 | 461 | 0 | [5 empty] | FALSE
OCB EQP -9 | EX NOTM TX A-10K.190 | Completed |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 80 | 0 | 0 | 3.2.7.1 |  |  | 545 | 461 | 0 | [5 empty] | FALSE
OCB EQP -12 | EX NOTM TX A-10K.190 | Completed |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 80 | 0 | 0 | 3.2.7.1 |  |  | 545 | 461 | 0 | [5 empty] | FALSE
OCB EQP -8 | EX NOTM TX A-10K.190 | Completed |  |  | Nonlabor | Loader | 0 | 0 | 0 | 80 | 0 | 0 | 3.2.7.1 |  |  | 545 | 461 | 0 | [5 empty] | FALSE
OCB EQP -4 | EX NOTM TX A-10K.190 | Completed |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 80 | 0 | 0 | 3.2.7.1 |  |  | 545 | 461 | 0 | [5 empty] | FALSE
OCB EQP -1 | EX NOTM TX A-11E.030 | In Progress |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 1 | 0 | 1 | 3.1.1.1a |  |  | 100 | 100 | 0 | hydraulic excavator | 0.025 | 2.5 | 2.5 | 0 | TRUE
OCB EQP -9 | EX NOTM TX A-11E.030 | In Progress |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 2 | 0 | 2 | 3.1.1.1a |  |  | 100 | 100 | 0 | Tipper | 0.044 | 4.4 | 4.4 | 0 | TRUE
OCB EQP -3 | EX NOTM TX A-11E.040 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.5 |  |  | 100 | 0 | 100 | motor grader | 0.01 | 1 | 0 | 1 | TRUE
OCB EQP -1 | EX NOTM TX A-11E.040 | Not Started |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.5 |  |  | 100 | 0 | 100 | hydraulic excavator | 0.02 | 2 | 0 | 2 | TRUE
OCB EQP -9 | EX NOTM TX A-11E.040 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 10 | 0 | 10 | 3.2.2.5 |  |  | 100 | 0 | 100 | Tipper | 0.083333 | 8.3333 | 0 | 8.3333 | TRUE
OCB EQP -12 | EX NOTM TX A-11E.040 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.5 |  |  | 100 | 0 | 100 | Water Bowser | 0.02 | 2 | 0 | 2 | TRUE
OCB EQP -2 | EX NOTM TX A-11E.040 | Not Started |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.5 |  |  | 100 | 0 | 100 | dozer | 0.01 | 1 | 0 | 1 | TRUE
OCB EQP -4 | EX NOTM TX A-11E.040 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.5 |  |  | 100 | 0 | 100 | vibratory road roller | 0.02 | 2 | 0 | 2 | TRUE
OCB EQP -3 | EX NOTM TX A-11E.050 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.6 |  |  | 4900 | 0 | 4900 | motor grader | 0.01 | 49 | 0 | 49 | TRUE
OCB EQP -1 | EX NOTM TX A-11E.050 | Not Started |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.2.6 |  |  | 4900 | 0 | 4900 | hydraulic excavator | 0.02 | 98 | 0 | 98 | TRUE
OCB EQP -9 | EX NOTM TX A-11E.050 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 17 | 0 | 17 | 3.2.2.6 |  |  | 4900 | 0 | 4900 | Tipper | 0.083333 | 408.3333 | 0 | 408.3333 | TRUE
OCB EQP -12 | EX NOTM TX A-11E.050 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.2.6 |  |  | 4900 | 0 | 4900 | Water Bowser | 0.02 | 98 | 0 | 98 | TRUE
OCB EQP -2 | EX NOTM TX A-11E.050 | Not Started |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.6 |  |  | 4900 | 0 | 4900 | dozer | 0.01 | 49 | 0 | 49 | TRUE
OCB EQP -4 | EX NOTM TX A-11E.050 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.2.6 |  |  | 4900 | 0 | 4900 | vibratory road roller | 0.02 | 98 | 0 | 98 | TRUE
OCB EQP -17 | EX NOTM TX A-11E.080 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.4.4 |  |  | 5780 | 0 | 5780 | [5 empty] | FALSE
OCB EQP -16 | EX NOTM TX A-11E.080 | Not Started |  |  | Nonlabor | Mechanical Broom | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.4.4 |  |  | 5780 | 0 | 5780 | [5 empty] | FALSE
OCB EQP -19 | EX NOTM TX A-11E.080 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.4.4 |  |  | 5780 | 0 | 5780 | [5 empty] | FALSE
OCB EQP -18 | EX NOTM TX A-11E.080 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.4.4 |  |  | 5780 | 0 | 5780 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-11E.080 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.4.4 |  |  | 5780 | 0 | 5780 | [5 empty] | FALSE
OCB EQP -17 | EX NOTM TX A-11E.150 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.4.5 |  |  | 5687 | 0 | 5687 | [5 empty] | FALSE
OCB EQP -19 | EX NOTM TX A-11E.150 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.4.5 |  |  | 5687 | 0 | 5687 | [5 empty] | FALSE
OCB EQP -18 | EX NOTM TX A-11E.150 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.4.5 |  |  | 5687 | 0 | 5687 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-11E.150 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.4.5 |  |  | 5687 | 0 | 5687 | [5 empty] | FALSE
OCB EQP -9 | EX NOTM TX A-11E.090 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.4.2 |  |  | 420 | 0 | 420 | [5 empty] | FALSE
OCB EQP -5 | EX NOTM TX A-11E.090 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.4.2 |  |  | 420 | 0 | 420 | [5 empty] | FALSE
OCB EQP -13 | EX NOTM TX A-11E.090 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.4.2 |  |  | 420 | 0 | 420 | [5 empty] | FALSE
OCB EQP -14 | EX NOTM TX A-11E.090 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.4.2 |  |  | 420 | 0 | 420 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-11E.090 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.4.2 |  |  | 420 | 0 | 420 | [5 empty] | FALSE
OCB EQP -6 | EX NOTM TX A-11E.090 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.4.2 |  |  | 420 | 0 | 420 | [5 empty] | FALSE
OCB EQP -17 | EX NOTM TX A-11E.100 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.4.6 |  |  | 5690 | 0 | 5690 | [5 empty] | FALSE
OCB EQP -19 | EX NOTM TX A-11E.100 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.4.6 |  |  | 5690 | 0 | 5690 | [5 empty] | FALSE
OCB EQP -18 | EX NOTM TX A-11E.100 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.4.6 |  |  | 5690 | 0 | 5690 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-11E.100 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.4.6 |  |  | 5690 | 0 | 5690 | [5 empty] | FALSE
OCB EQP -9 | EX NOTM TX A-11E.160 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.4.3 |  |  | 341 | 0 | 341 | [5 empty] | FALSE
OCB EQP -5 | EX NOTM TX A-11E.160 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.4.3 |  |  | 341 | 0 | 341 | [5 empty] | FALSE
OCB EQP -13 | EX NOTM TX A-11E.160 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.4.3 |  |  | 341 | 0 | 341 | [5 empty] | FALSE
OCB EQP -14 | EX NOTM TX A-11E.160 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.4.3 |  |  | 341 | 0 | 341 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-11E.160 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.4.3 |  |  | 341 | 0 | 341 | [5 empty] | FALSE
OCB EQP -6 | EX NOTM TX A-11E.160 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.4.3 |  |  | 341 | 0 | 341 | [5 empty] | FALSE
OCB EQP -3 | EX NOTM TX A-11E.070 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.4.1 |  |  | 2312 | 0 | 2312 | [5 empty] | FALSE
OCB EQP -9 | EX NOTM TX A-11E.070 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 8 | 0 | 8 | 3.2.4.1 |  |  | 2312 | 0 | 2312 | [5 empty] | FALSE
OCB EQP -12 | EX NOTM TX A-11E.070 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.4.1 |  |  | 2312 | 0 | 2312 | [5 empty] | FALSE
OCB EQP -8 | EX NOTM TX A-11E.070 | Not Started |  |  | Nonlabor | Loader | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.4.1 |  |  | 2312 | 0 | 2312 | [5 empty] | FALSE
OCB EQP -4 | EX NOTM TX A-11E.070 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.4.1 |  |  | 2312 | 0 | 2312 | [5 empty] | FALSE
OCB EQP -17 | EX NOTM TX A-11E.220 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 650 | 0 | 650 | [5 empty] | FALSE
OCB EQP -16 | EX NOTM TX A-11E.220 | Not Started |  |  | Nonlabor | Mechanical Broom | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 650 | 0 | 650 | [5 empty] | FALSE
OCB EQP -19 | EX NOTM TX A-11E.220 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 650 | 0 | 650 | [5 empty] | FALSE
OCB EQP -18 | EX NOTM TX A-11E.220 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 650 | 0 | 650 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-11E.220 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 650 | 0 | 650 | [5 empty] | FALSE
OCB EQP -17 | EX NOTM TX A-11E.240 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 631 | 0 | 631 | [5 empty] | FALSE
OCB EQP -19 | EX NOTM TX A-11E.240 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 631 | 0 | 631 | [5 empty] | FALSE
OCB EQP -18 | EX NOTM TX A-11E.240 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 631 | 0 | 631 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-11E.240 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 631 | 0 | 631 | [5 empty] | FALSE
OCB EQP -9 | EX NOTM TX A-11E.230 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.7.2 |  |  | 80 | 0 | 80 | [5 empty] | FALSE
OCB EQP -5 | EX NOTM TX A-11E.230 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.2 |  |  | 80 | 0 | 80 | [5 empty] | FALSE
OCB EQP -13 | EX NOTM TX A-11E.230 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.2 |  |  | 80 | 0 | 80 | [5 empty] | FALSE
OCB EQP -14 | EX NOTM TX A-11E.230 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.2 |  |  | 80 | 0 | 80 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-11E.230 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.2 |  |  | 80 | 0 | 80 | [5 empty] | FALSE
OCB EQP -6 | EX NOTM TX A-11E.230 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.7.2 |  |  | 80 | 0 | 80 | [5 empty] | FALSE
OCB EQP -9 | EX NOTM TX A-11E.250 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.7.3 |  |  | 75 | 0 | 75 | [5 empty] | FALSE
OCB EQP -5 | EX NOTM TX A-11E.250 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.3 |  |  | 75 | 0 | 75 | [5 empty] | FALSE
OCB EQP -13 | EX NOTM TX A-11E.250 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.3 |  |  | 75 | 0 | 75 | [5 empty] | FALSE
OCB EQP -14 | EX NOTM TX A-11E.250 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.3 |  |  | 75 | 0 | 75 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-11E.250 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.3 |  |  | 75 | 0 | 75 | [5 empty] | FALSE
OCB EQP -6 | EX NOTM TX A-11E.250 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.7.3 |  |  | 75 | 0 | 75 | [5 empty] | FALSE
OCB EQP -3 | EX NOTM TX A-11E.210 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.1 |  |  | 340 | 0 | 340 | [5 empty] | FALSE
OCB EQP -9 | EX NOTM TX A-11E.210 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 9 | 0 | 9 | 3.2.7.1 |  |  | 340 | 0 | 340 | [5 empty] | FALSE
OCB EQP -12 | EX NOTM TX A-11E.210 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.7.1 |  |  | 340 | 0 | 340 | [5 empty] | FALSE
OCB EQP -8 | EX NOTM TX A-11E.210 | Not Started |  |  | Nonlabor | Loader | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.7.1 |  |  | 340 | 0 | 340 | [5 empty] | FALSE
OCB EQP -4 | EX NOTM TX A-11E.210 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.7.1 |  |  | 340 | 0 | 340 | [5 empty] | FALSE
OCB EQP -1 | NOTM TX-New A-12.020 | In Progress |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 1 | 0 | 1 | 3.1.1.1a |  |  | 100 | 100 | 0 | hydraulic excavator | 0.025 | 2.5 | 2.5 | 0 | TRUE
OCB EQP -9 | NOTM TX-New A-12.020 | In Progress |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 2 | 0 | 2 | 3.1.1.1a |  |  | 100 | 100 | 0 | Tipper | 0.044 | 4.4 | 4.4 | 0 | TRUE
OCB EQP -3 | NOTM TX-New A-12.030 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.5 |  |  | 50 | 0 | 50 | motor grader | 0.01 | 0.5 | 0 | 0.5 | TRUE
OCB EQP -1 | NOTM TX-New A-12.030 | Not Started |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.5 |  |  | 50 | 0 | 50 | hydraulic excavator | 0.02 | 1 | 0 | 1 | TRUE
OCB EQP -9 | NOTM TX-New A-12.030 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 10 | 0 | 10 | 3.2.2.5 |  |  | 50 | 0 | 50 | Tipper | 0.083333 | 4.1667 | 0 | 4.1667 | TRUE
OCB EQP -12 | NOTM TX-New A-12.030 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.5 |  |  | 50 | 0 | 50 | Water Bowser | 0.02 | 1 | 0 | 1 | TRUE
OCB EQP -2 | NOTM TX-New A-12.030 | Not Started |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.5 |  |  | 50 | 0 | 50 | dozer | 0.01 | 0.5 | 0 | 0.5 | TRUE
OCB EQP -4 | NOTM TX-New A-12.030 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.5 |  |  | 50 | 0 | 50 | vibratory road roller | 0.02 | 1 | 0 | 1 | TRUE
OCB EQP -3 | NOTM TX-New A-12.040 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.6 |  |  | 3843 | 0 | 3843 | motor grader | 0.01 | 38.43 | 0 | 38.43 | TRUE
OCB EQP -1 | NOTM TX-New A-12.040 | Not Started |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.2.6 |  |  | 3843 | 0 | 3843 | hydraulic excavator | 0.02 | 76.86 | 0 | 76.86 | TRUE
OCB EQP -9 | NOTM TX-New A-12.040 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 13 | 0 | 13 | 3.2.2.6 |  |  | 3843 | 0 | 3843 | Tipper | 0.083333 | 320.25 | 0 | 320.25 | TRUE
OCB EQP -12 | NOTM TX-New A-12.040 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.2.6 |  |  | 3843 | 0 | 3843 | Water Bowser | 0.02 | 76.86 | 0 | 76.86 | TRUE
OCB EQP -2 | NOTM TX-New A-12.040 | Not Started |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.6 |  |  | 3843 | 0 | 3843 | dozer | 0.01 | 38.43 | 0 | 38.43 | TRUE
OCB EQP -4 | NOTM TX-New A-12.040 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.2.6 |  |  | 3843 | 0 | 3843 | vibratory road roller | 0.02 | 76.86 | 0 | 76.86 | TRUE
OCB EQP -9 | EXE TXY P A-02.100 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.2 |  |  | 565 | 0 | 565 | Tipper | 0.083333 | 47.0833 | 0 | 47.0833 | TRUE
OCB EQP -5 | EXE TXY P A-02.100 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 565 | 0 | 565 | Pneumatic Roller | 0.062827 | 35.4974 | 0 | 35.4974 | TRUE
OCB EQP -13 | EXE TXY P A-02.100 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 565 | 0 | 565 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-02.100 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 565 | 0 | 565 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-02.100 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 565 | 0 | 565 | Generator | 0.062827 | 35.4974 | 0 | 35.4974 | TRUE
OCB EQP -6 | EXE TXY P A-02.100 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.2 |  |  | 565 | 0 | 565 | Smooth wheel tandem roller | 0.12565 | 70.9948 | 0 | 70.9948 | TRUE
OCB EQP -9 | EXE TXY P A-02.120 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.2 |  |  | 485 | 0 | 485 | Tipper | 0.083333 | 40.4167 | 0 | 40.4167 | TRUE
OCB EQP -5 | EXE TXY P A-02.120 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 485 | 0 | 485 | Pneumatic Roller | 0.062827 | 30.4712 | 0 | 30.4712 | TRUE
OCB EQP -13 | EXE TXY P A-02.120 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 485 | 0 | 485 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-02.120 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 485 | 0 | 485 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-02.120 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 485 | 0 | 485 | Generator | 0.062827 | 30.4712 | 0 | 30.4712 | TRUE
OCB EQP -6 | EXE TXY P A-02.120 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.2 |  |  | 485 | 0 | 485 | Smooth wheel tandem roller | 0.12565 | 60.9424 | 0 | 60.9424 | TRUE
OCB EQP -9 | EXE TXY P A-02.160 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.3 |  |  | 465 | 0 | 465 | Tipper | 0.083333 | 38.75 | 0 | 38.75 | TRUE
OCB EQP -5 | EXE TXY P A-02.160 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 465 | 0 | 465 | Pneumatic Roller | 0.062827 | 29.2147 | 0 | 29.2147 | TRUE
OCB EQP -13 | EXE TXY P A-02.160 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 465 | 0 | 465 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-02.160 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 465 | 0 | 465 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-02.160 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 465 | 0 | 465 | Generator | 0.062827 | 29.2147 | 0 | 29.2147 | TRUE
OCB EQP -6 | EXE TXY P A-02.160 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.3 |  |  | 465 | 0 | 465 | Smooth wheel tandem roller | 0.12565 | 58.4293 | 0 | 58.4293 | TRUE
OCB EQP -17 | EXE TXY P A-02.090 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 7000 | 0 | 7000 | Air compressor | 0.0012 | 8.4 | 0 | 8.4 | TRUE
OCB EQP -19 | EXE TXY P A-02.090 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 7000 | 0 | 7000 | Boiler | 0.0012 | 8.4 | 0 | 8.4 | TRUE
OCB EQP -18 | EXE TXY P A-02.090 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 7000 | 0 | 7000 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-02.090 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 7000 | 0 | 7000 | Generator | 0.0012 | 8.4 | 0 | 8.4 | TRUE
OCB EQP -17 | EXE TXY P A-02.110 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 7000 | 0 | 7000 | Air compressor | 0.0012 | 8.4 | 0 | 8.4 | TRUE
OCB EQP -19 | EXE TXY P A-02.110 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 7000 | 0 | 7000 | Boiler | 0.0012 | 8.4 | 0 | 8.4 | TRUE
OCB EQP -18 | EXE TXY P A-02.110 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 7000 | 0 | 7000 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-02.110 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 7000 | 0 | 7000 | Generator | 0.0012 | 8.4 | 0 | 8.4 | TRUE
OCB EQP -9 | EXE TXY P A-03.100 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.2 |  |  | 929 | 0 | 929 | Tipper | 0.083333 | 77.4167 | 0 | 77.4167 | TRUE
OCB EQP -5 | EXE TXY P A-03.100 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 929 | 0 | 929 | Pneumatic Roller | 0.062827 | 58.3665 | 0 | 58.3665 | TRUE
OCB EQP -13 | EXE TXY P A-03.100 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 929 | 0 | 929 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-03.100 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 929 | 0 | 929 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-03.100 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 929 | 0 | 929 | Generator | 0.062827 | 58.3665 | 0 | 58.3665 | TRUE
OCB EQP -6 | EXE TXY P A-03.100 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.2 |  |  | 929 | 0 | 929 | Smooth wheel tandem roller | 0.12565 | 116.733 | 0 | 116.733 | TRUE
OCB EQP -9 | EXE TXY P A-03.120 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.2 |  |  | 865 | 0 | 865 | Tipper | 0.083333 | 72.0833 | 0 | 72.0833 | TRUE
OCB EQP -5 | EXE TXY P A-03.120 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 865 | 0 | 865 | Pneumatic Roller | 0.062827 | 54.3455 | 0 | 54.3455 | TRUE
OCB EQP -13 | EXE TXY P A-03.120 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 865 | 0 | 865 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-03.120 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 865 | 0 | 865 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-03.120 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 865 | 0 | 865 | Generator | 0.062827 | 54.3455 | 0 | 54.3455 | TRUE
OCB EQP -6 | EXE TXY P A-03.120 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.2 |  |  | 865 | 0 | 865 | Smooth wheel tandem roller | 0.12565 | 108.6911 | 0 | 108.6911 | TRUE
OCB EQP -17 | EXE TXY P A-03.110 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 12000 | 0 | 12000 | Air compressor | 0.0012 | 14.4 | 0 | 14.4 | TRUE
OCB EQP -19 | EXE TXY P A-03.110 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 12000 | 0 | 12000 | Boiler | 0.0012 | 14.4 | 0 | 14.4 | TRUE
OCB EQP -18 | EXE TXY P A-03.110 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 12000 | 0 | 12000 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-03.110 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 12000 | 0 | 12000 | Generator | 0.0012 | 14.4 | 0 | 14.4 | TRUE
OCB EQP -17 | EXE TXY P A-03.150 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 12000 | 0 | 12000 | Air compressor | 0.0012 | 14.4 | 0 | 14.4 | TRUE
OCB EQP -19 | EXE TXY P A-03.150 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 12000 | 0 | 12000 | Boiler | 0.0012 | 14.4 | 0 | 14.4 | TRUE
OCB EQP -18 | EXE TXY P A-03.150 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 12000 | 0 | 12000 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-03.150 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 12000 | 0 | 12000 | Generator | 0.0012 | 14.4 | 0 | 14.4 | TRUE
OCB EQP -9 | EXE TXY P A-03.160 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.3 |  |  | 550 | 0 | 550 | Tipper | 0.083333 | 45.8333 | 0 | 45.8333 | TRUE
OCB EQP -5 | EXE TXY P A-03.160 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 550 | 0 | 550 | Pneumatic Roller | 0.062827 | 34.555 | 0 | 34.555 | TRUE
OCB EQP -13 | EXE TXY P A-03.160 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 550 | 0 | 550 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-03.160 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 550 | 0 | 550 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-03.160 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 550 | 0 | 550 | Generator | 0.062827 | 34.555 | 0 | 34.555 | TRUE
OCB EQP -6 | EXE TXY P A-03.160 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.3 |  |  | 550 | 0 | 550 | Smooth wheel tandem roller | 0.12565 | 69.1099 | 0 | 69.1099 | TRUE
OCB EQP -3 | EXE TXY P A-01.180 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 1000 | 0 | 1000 | motor grader | 0.01 | 10 | 0 | 10 | TRUE
OCB EQP -1 | EXE TXY P A-01.180 | Not Started |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.6 |  |  | 1000 | 0 | 1000 | hydraulic excavator | 0.02 | 20 | 0 | 20 | TRUE
OCB EQP -9 | EXE TXY P A-01.180 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 7 | 0 | 7 | 3.2.2.6 |  |  | 1000 | 0 | 1000 | Tipper | 0.083333 | 83.3333 | 0 | 83.3333 | TRUE
OCB EQP -12 | EXE TXY P A-01.180 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.6 |  |  | 1000 | 0 | 1000 | Water Bowser | 0.02 | 20 | 0 | 20 | TRUE
OCB EQP -2 | EXE TXY P A-01.180 | Not Started |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 1000 | 0 | 1000 | dozer | 0.01 | 10 | 0 | 10 | TRUE
OCB EQP -4 | EXE TXY P A-01.180 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.6 |  |  | 1000 | 0 | 1000 | vibratory road roller | 0.02 | 20 | 0 | 20 | TRUE
OCB EQP -3 | EXE TXY P A-02.180 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 850 | 0 | 850 | motor grader | 0.01 | 8.5 | 0 | 8.5 | TRUE
OCB EQP -1 | EXE TXY P A-02.180 | Not Started |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 850 | 0 | 850 | hydraulic excavator | 0.02 | 17 | 0 | 17 | TRUE
OCB EQP -9 | EXE TXY P A-02.180 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 5 | 0 | 5 | 3.2.2.6 |  |  | 850 | 0 | 850 | Tipper | 0.083333 | 70.8333 | 0 | 70.8333 | TRUE
OCB EQP -12 | EXE TXY P A-02.180 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 850 | 0 | 850 | Water Bowser | 0.02 | 17 | 0 | 17 | TRUE
OCB EQP -2 | EXE TXY P A-02.180 | Not Started |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 850 | 0 | 850 | dozer | 0.01 | 8.5 | 0 | 8.5 | TRUE
OCB EQP -4 | EXE TXY P A-02.180 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 850 | 0 | 850 | vibratory road roller | 0.02 | 17 | 0 | 17 | TRUE
OCB EQP -9 | EXE TXY P A-04.100 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.2 |  |  | 410 | 0 | 410 | Tipper | 0.083333 | 34.1667 | 0 | 34.1667 | TRUE
OCB EQP -5 | EXE TXY P A-04.100 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 410 | 0 | 410 | Pneumatic Roller | 0.062827 | 25.7592 | 0 | 25.7592 | TRUE
OCB EQP -13 | EXE TXY P A-04.100 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 410 | 0 | 410 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-04.100 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 410 | 0 | 410 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-04.100 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 410 | 0 | 410 | Generator | 0.062827 | 25.7592 | 0 | 25.7592 | TRUE
OCB EQP -6 | EXE TXY P A-04.100 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.2 |  |  | 410 | 0 | 410 | Smooth wheel tandem roller | 0.12565 | 51.5183 | 0 | 51.5183 | TRUE
OCB EQP -9 | EXE TXY P A-04.120 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.2 |  |  | 350 | 0 | 350 | Tipper | 0.083333 | 29.1667 | 0 | 29.1667 | TRUE
OCB EQP -5 | EXE TXY P A-04.120 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 350 | 0 | 350 | Pneumatic Roller | 0.062827 | 21.9895 | 0 | 21.9895 | TRUE
OCB EQP -13 | EXE TXY P A-04.120 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 350 | 0 | 350 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-04.120 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 350 | 0 | 350 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-04.120 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 350 | 0 | 350 | Generator | 0.062827 | 21.9895 | 0 | 21.9895 | TRUE
OCB EQP -6 | EXE TXY P A-04.120 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.2 |  |  | 350 | 0 | 350 | Smooth wheel tandem roller | 0.12565 | 43.9791 | 0 | 43.9791 | TRUE
OCB EQP -9 | EXE TXY P A-04.140 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.3 |  |  | 330 | 0 | 330 | Tipper | 0.083333 | 27.5 | 0 | 27.5 | TRUE
OCB EQP -5 | EXE TXY P A-04.140 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 330 | 0 | 330 | Pneumatic Roller | 0.062827 | 20.733 | 0 | 20.733 | TRUE
OCB EQP -13 | EXE TXY P A-04.140 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 330 | 0 | 330 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-04.140 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 330 | 0 | 330 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-04.140 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 330 | 0 | 330 | Generator | 0.062827 | 20.733 | 0 | 20.733 | TRUE
OCB EQP -6 | EXE TXY P A-04.140 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.3 |  |  | 330 | 0 | 330 | Smooth wheel tandem roller | 0.12565 | 41.466 | 0 | 41.466 | TRUE
OCB EQP -17 | EXE TXY P A-04.110 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 5500 | 0 | 5500 | Air compressor | 0.0012 | 6.6 | 0 | 6.6 | TRUE
OCB EQP -19 | EXE TXY P A-04.110 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 5500 | 0 | 5500 | Boiler | 0.0012 | 6.6 | 0 | 6.6 | TRUE
OCB EQP -18 | EXE TXY P A-04.110 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 5500 | 0 | 5500 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-04.110 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 5500 | 0 | 5500 | Generator | 0.0012 | 6.6 | 0 | 6.6 | TRUE
OCB EQP -17 | EXE TXY P A-04.150 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 5500 | 0 | 5500 | Air compressor | 0.0012 | 6.6 | 0 | 6.6 | TRUE
OCB EQP -19 | EXE TXY P A-04.150 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 5500 | 0 | 5500 | Boiler | 0.0012 | 6.6 | 0 | 6.6 | TRUE
OCB EQP -18 | EXE TXY P A-04.150 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 5500 | 0 | 5500 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-04.150 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 5500 | 0 | 5500 | Generator | 0.0012 | 6.6 | 0 | 6.6 | TRUE
OCB EQP -3 | EXE TXY P A-04.190 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.7.1 |  |  | 1020 | 0 | 1020 | [5 empty] | FALSE
OCB EQP -9 | EXE TXY P A-04.190 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 13 | 0 | 13 | 3.2.7.1 |  |  | 1020 | 0 | 1020 | [5 empty] | FALSE
OCB EQP -12 | EXE TXY P A-04.190 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 5 | 0 | 5 | 3.2.7.1 |  |  | 1020 | 0 | 1020 | [5 empty] | FALSE
OCB EQP -8 | EXE TXY P A-04.190 | Not Started |  |  | Nonlabor | Loader | 0 | 0 | 0 | 6 | 0 | 6 | 3.2.7.1 |  |  | 1020 | 0 | 1020 | [5 empty] | FALSE
OCB EQP -4 | EXE TXY P A-04.190 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 6 | 0 | 6 | 3.2.7.1 |  |  | 1020 | 0 | 1020 | [5 empty] | FALSE
OCB EQP -3 | EXE TXY P A-03.180 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 1000 | 0 | 1000 | motor grader | 0.01 | 10 | 0 | 10 | TRUE
OCB EQP -1 | EXE TXY P A-03.180 | Not Started |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.6 |  |  | 1000 | 0 | 1000 | hydraulic excavator | 0.02 | 20 | 0 | 20 | TRUE
OCB EQP -9 | EXE TXY P A-03.180 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 7 | 0 | 7 | 3.2.2.6 |  |  | 1000 | 0 | 1000 | Tipper | 0.083333 | 83.3333 | 0 | 83.3333 | TRUE
OCB EQP -12 | EXE TXY P A-03.180 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.6 |  |  | 1000 | 0 | 1000 | Water Bowser | 0.02 | 20 | 0 | 20 | TRUE
OCB EQP -2 | EXE TXY P A-03.180 | Not Started |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 1000 | 0 | 1000 | dozer | 0.01 | 10 | 0 | 10 | TRUE
OCB EQP -4 | EXE TXY P A-03.180 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.6 |  |  | 1000 | 0 | 1000 | vibratory road roller | 0.02 | 20 | 0 | 20 | TRUE
OCB EQP -3 | EXE TXY P A-04.180 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 500 | 0 | 500 | motor grader | 0.01 | 5 | 0 | 5 | TRUE
OCB EQP -1 | EXE TXY P A-04.180 | Not Started |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.6 |  |  | 500 | 0 | 500 | hydraulic excavator | 0.02 | 10 | 0 | 10 | TRUE
OCB EQP -9 | EXE TXY P A-04.180 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 10 | 0 | 10 | 3.2.2.6 |  |  | 500 | 0 | 500 | Tipper | 0.083333 | 41.6667 | 0 | 41.6667 | TRUE
OCB EQP -12 | EXE TXY P A-04.180 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.6 |  |  | 500 | 0 | 500 | Water Bowser | 0.02 | 10 | 0 | 10 | TRUE
OCB EQP -2 | EXE TXY P A-04.180 | Not Started |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 500 | 0 | 500 | dozer | 0.01 | 5 | 0 | 5 | TRUE
OCB EQP -4 | EXE TXY P A-04.180 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.6 |  |  | 500 | 0 | 500 | vibratory road roller | 0.02 | 10 | 0 | 10 | TRUE
OCB EQP -3 | EX NOTM TX A-09L.180 | Completed |  |  | Nonlabor | Grader | 0 | 0 | 0 | 40 | 0 | 0 | 3.2.2.6 |  |  | 100 | 270 | 0 | motor grader | 0.01 | 1 | 2.7 | 0 | TRUE
OCB EQP -1 | EX NOTM TX A-09L.180 | Completed |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 40 | 0 | 0 | 3.2.2.6 |  |  | 100 | 270 | 0 | hydraulic excavator | 0.02 | 2 | 5.4 | 0 | TRUE
OCB EQP -9 | EX NOTM TX A-09L.180 | Completed |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 40 | 0 | 0 | 3.2.2.6 |  |  | 100 | 270 | 0 | Tipper | 0.083333 | 8.3333 | 22.5 | 0 | TRUE
OCB EQP -12 | EX NOTM TX A-09L.180 | Completed |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 40 | 0 | 0 | 3.2.2.6 |  |  | 100 | 270 | 0 | Water Bowser | 0.02 | 2 | 5.4 | 0 | TRUE
OCB EQP -2 | EX NOTM TX A-09L.180 | Completed |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 40 | 0 | 0 | 3.2.2.6 |  |  | 100 | 270 | 0 | dozer | 0.01 | 1 | 2.7 | 0 | TRUE
OCB EQP -4 | EX NOTM TX A-09L.180 | Completed |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 40 | 0 | 0 | 3.2.2.6 |  |  | 100 | 270 | 0 | vibratory road roller | 0.02 | 2 | 5.4 | 0 | TRUE
OCB EQP -9 | EX NOTM TX A-09L.100 | Completed |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.6.2 |  |  | 270 | 292 | 0 | [5 empty] | FALSE
OCB EQP -5 | EX NOTM TX A-09L.100 | Completed |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.6.2 |  |  | 270 | 292 | 0 | [5 empty] | FALSE
OCB EQP -13 | EX NOTM TX A-09L.100 | Completed |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.6.2 |  |  | 270 | 292 | 0 | [5 empty] | FALSE
OCB EQP -14 | EX NOTM TX A-09L.100 | Completed |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.6.2 |  |  | 270 | 292 | 0 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-09L.100 | Completed |  |  | Nonlabor | Generator | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.6.2 |  |  | 270 | 292 | 0 | [5 empty] | FALSE
OCB EQP -6 | EX NOTM TX A-09L.100 | Completed |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.6.2 |  |  | 270 | 292 | 0 | [5 empty] | FALSE
OCB EQP -9 | EX NOTM TX A-09L.120 | Completed |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.6.2 |  |  | 253 | 219 | 0 | [5 empty] | FALSE
OCB EQP -5 | EX NOTM TX A-09L.120 | Completed |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.6.2 |  |  | 253 | 219 | 0 | [5 empty] | FALSE
OCB EQP -13 | EX NOTM TX A-09L.120 | Completed |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.6.2 |  |  | 253 | 219 | 0 | [5 empty] | FALSE
OCB EQP -14 | EX NOTM TX A-09L.120 | Completed |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.6.2 |  |  | 253 | 219 | 0 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-09L.120 | Completed |  |  | Nonlabor | Generator | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.6.2 |  |  | 253 | 219 | 0 | [5 empty] | FALSE
OCB EQP -6 | EX NOTM TX A-09L.120 | Completed |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.6.2 |  |  | 253 | 219 | 0 | [5 empty] | FALSE
OCB EQP -9 | EX NOTM TX A-09L.160 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.6.3 |  |  | 220 | 0 | 220 | [5 empty] | FALSE
OCB EQP -5 | EX NOTM TX A-09L.160 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.6.3 |  |  | 220 | 0 | 220 | [5 empty] | FALSE
OCB EQP -13 | EX NOTM TX A-09L.160 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.6.3 |  |  | 220 | 0 | 220 | [5 empty] | FALSE
OCB EQP -14 | EX NOTM TX A-09L.160 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.6.3 |  |  | 220 | 0 | 220 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-09L.160 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.6.3 |  |  | 220 | 0 | 220 | [5 empty] | FALSE
OCB EQP -6 | EX NOTM TX A-09L.160 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.6.3 |  |  | 220 | 0 | 220 | [5 empty] | FALSE
OCB EQP -17 | EX NOTM TX A-09L.110 | Completed |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 8 | 0 | 0 | 3.2.6.6 |  |  | 3650 | 3890 | 0 | [5 empty] | FALSE
OCB EQP -19 | EX NOTM TX A-09L.110 | Completed |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 8 | 0 | 0 | 3.2.6.6 |  |  | 3650 | 3890 | 0 | [5 empty] | FALSE
OCB EQP -18 | EX NOTM TX A-09L.110 | Completed |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 8 | 0 | 0 | 3.2.6.6 |  |  | 3650 | 3890 | 0 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-09L.110 | Completed |  |  | Nonlabor | Generator | 0 | 0 | 0 | 8 | 0 | 0 | 3.2.6.6 |  |  | 3650 | 3890 | 0 | [5 empty] | FALSE
OCB EQP -17 | EX NOTM TX A-09L.150 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.6.6 |  |  | 3661 | 0 | 3661 | [5 empty] | FALSE
OCB EQP -19 | EX NOTM TX A-09L.150 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.6.6 |  |  | 3661 | 0 | 3661 | [5 empty] | FALSE
OCB EQP -18 | EX NOTM TX A-09L.150 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.6.6 |  |  | 3661 | 0 | 3661 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-09L.150 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.6.6 |  |  | 3661 | 0 | 3661 | [5 empty] | FALSE
OCB EQP -3 | EX NOTM TX A-10K.180 | Completed |  |  | Nonlabor | Grader | 0 | 0 | 0 | 40 | 0 | 0 | 3.2.2.6 |  |  | 200 | 285 | 0 | motor grader | 0.01 | 2 | 2.85 | 0 | TRUE
OCB EQP -1 | EX NOTM TX A-10K.180 | Completed |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 40 | 0 | 0 | 3.2.2.6 |  |  | 200 | 285 | 0 | hydraulic excavator | 0.02 | 4 | 5.7 | 0 | TRUE
OCB EQP -9 | EX NOTM TX A-10K.180 | Completed |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 40 | 0 | 0 | 3.2.2.6 |  |  | 200 | 285 | 0 | Tipper | 0.083333 | 16.6667 | 23.75 | 0 | TRUE
OCB EQP -12 | EX NOTM TX A-10K.180 | Completed |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 40 | 0 | 0 | 3.2.2.6 |  |  | 200 | 285 | 0 | Water Bowser | 0.02 | 4 | 5.7 | 0 | TRUE
OCB EQP -2 | EX NOTM TX A-10K.180 | Completed |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 40 | 0 | 0 | 3.2.2.6 |  |  | 200 | 285 | 0 | dozer | 0.01 | 2 | 2.85 | 0 | TRUE
OCB EQP -4 | EX NOTM TX A-10K.180 | Completed |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 40 | 0 | 0 | 3.2.2.6 |  |  | 200 | 285 | 0 | vibratory road roller | 0.02 | 4 | 5.7 | 0 | TRUE
OCB EQP -9 | EX NOTM TX A-10K.160 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.5.3 |  |  | 378 | 0 | 378 | [5 empty] | FALSE
OCB EQP -5 | EX NOTM TX A-10K.160 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.5.3 |  |  | 378 | 0 | 378 | [5 empty] | FALSE
OCB EQP -13 | EX NOTM TX A-10K.160 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.5.3 |  |  | 378 | 0 | 378 | [5 empty] | FALSE
OCB EQP -14 | EX NOTM TX A-10K.160 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.5.3 |  |  | 378 | 0 | 378 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-10K.160 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.5.3 |  |  | 378 | 0 | 378 | [5 empty] | FALSE
OCB EQP -6 | EX NOTM TX A-10K.160 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.5.3 |  |  | 378 | 0 | 378 | [5 empty] | FALSE
OCB EQP -9 | EX NOTM TX A-10K.100 | Completed |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.2 |  |  | 505 | 506 | 0 | [5 empty] | FALSE
OCB EQP -5 | EX NOTM TX A-10K.100 | Completed |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.2 |  |  | 505 | 506 | 0 | [5 empty] | FALSE
OCB EQP -13 | EX NOTM TX A-10K.100 | Completed |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.2 |  |  | 505 | 506 | 0 | [5 empty] | FALSE
OCB EQP -14 | EX NOTM TX A-10K.100 | Completed |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.2 |  |  | 505 | 506 | 0 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-10K.100 | Completed |  |  | Nonlabor | Generator | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.2 |  |  | 505 | 506 | 0 | [5 empty] | FALSE
OCB EQP -6 | EX NOTM TX A-10K.100 | Completed |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.2 |  |  | 505 | 506 | 0 | [5 empty] | FALSE
OCB EQP -9 | EX NOTM TX A-10K.120 | Completed |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.2 |  |  | 380 | 380 | 0 | [5 empty] | FALSE
OCB EQP -5 | EX NOTM TX A-10K.120 | Completed |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.2 |  |  | 380 | 380 | 0 | [5 empty] | FALSE
OCB EQP -13 | EX NOTM TX A-10K.120 | Completed |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.2 |  |  | 380 | 380 | 0 | [5 empty] | FALSE
OCB EQP -14 | EX NOTM TX A-10K.120 | Completed |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.2 |  |  | 380 | 380 | 0 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-10K.120 | Completed |  |  | Nonlabor | Generator | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.2 |  |  | 380 | 380 | 0 | [5 empty] | FALSE
OCB EQP -6 | EX NOTM TX A-10K.120 | Completed |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.2 |  |  | 380 | 380 | 0 | [5 empty] | FALSE
OCB EQP -17 | EX NOTM TX A-10K.110 | Completed |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.6 |  |  | 6326 | 5820 | 0 | [5 empty] | FALSE
OCB EQP -19 | EX NOTM TX A-10K.110 | Completed |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.6 |  |  | 6326 | 5820 | 0 | [5 empty] | FALSE
OCB EQP -18 | EX NOTM TX A-10K.110 | Completed |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.6 |  |  | 6326 | 5820 | 0 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-10K.110 | Completed |  |  | Nonlabor | Generator | 0 | 0 | 0 | 16 | 0 | 0 | 3.2.5.6 |  |  | 6326 | 5820 | 0 | [5 empty] | FALSE
OCB EQP -17 | EX NOTM TX A-10K.150 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.5.6 |  |  | 6326 | 0 | 6326 | [5 empty] | FALSE
OCB EQP -19 | EX NOTM TX A-10K.150 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.5.6 |  |  | 6326 | 0 | 6326 | [5 empty] | FALSE
OCB EQP -18 | EX NOTM TX A-10K.150 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.5.6 |  |  | 6326 | 0 | 6326 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-10K.150 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.5.6 |  |  | 6326 | 0 | 6326 | [5 empty] | FALSE
OCB EQP -3 | EX NOTM TX A-11E.200 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 100 | 0 | 100 | motor grader | 0.01 | 1 | 0 | 1 | TRUE
OCB EQP -1 | EX NOTM TX A-11E.200 | Not Started |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 100 | 0 | 100 | hydraulic excavator | 0.02 | 2 | 0 | 2 | TRUE
OCB EQP -9 | EX NOTM TX A-11E.200 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 5 | 0 | 5 | 3.2.2.6 |  |  | 100 | 0 | 100 | Tipper | 0.083333 | 8.3333 | 0 | 8.3333 | TRUE
OCB EQP -12 | EX NOTM TX A-11E.200 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 100 | 0 | 100 | Water Bowser | 0.02 | 2 | 0 | 2 | TRUE
OCB EQP -2 | EX NOTM TX A-11E.200 | Not Started |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 100 | 0 | 100 | dozer | 0.01 | 1 | 0 | 1 | TRUE
OCB EQP -4 | EX NOTM TX A-11E.200 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 100 | 0 | 100 | vibratory road roller | 0.02 | 2 | 0 | 2 | TRUE
OCB EQP -9 | EX NOTM TX A-11E.180 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.4.3 |  |  | 341 | 0 | 341 | [5 empty] | FALSE
OCB EQP -5 | EX NOTM TX A-11E.180 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.4.3 |  |  | 341 | 0 | 341 | [5 empty] | FALSE
OCB EQP -13 | EX NOTM TX A-11E.180 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.4.3 |  |  | 341 | 0 | 341 | [5 empty] | FALSE
OCB EQP -14 | EX NOTM TX A-11E.180 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.4.3 |  |  | 341 | 0 | 341 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-11E.180 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.4.3 |  |  | 341 | 0 | 341 | [5 empty] | FALSE
OCB EQP -6 | EX NOTM TX A-11E.180 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.4.3 |  |  | 341 | 0 | 341 | [5 empty] | FALSE
OCB EQP -9 | EX NOTM TX A-11E.110 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.4.2 |  |  | 415 | 0 | 415 | [5 empty] | FALSE
OCB EQP -5 | EX NOTM TX A-11E.110 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.4.2 |  |  | 415 | 0 | 415 | [5 empty] | FALSE
OCB EQP -13 | EX NOTM TX A-11E.110 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.4.2 |  |  | 415 | 0 | 415 | [5 empty] | FALSE
OCB EQP -14 | EX NOTM TX A-11E.110 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.4.2 |  |  | 415 | 0 | 415 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-11E.110 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.4.2 |  |  | 415 | 0 | 415 | [5 empty] | FALSE
OCB EQP -6 | EX NOTM TX A-11E.110 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.4.2 |  |  | 415 | 0 | 415 | [5 empty] | FALSE
OCB EQP -9 | EX NOTM TX A-11E.130 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.4.2 |  |  | 416 | 0 | 416 | [5 empty] | FALSE
OCB EQP -5 | EX NOTM TX A-11E.130 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.4.2 |  |  | 416 | 0 | 416 | [5 empty] | FALSE
OCB EQP -13 | EX NOTM TX A-11E.130 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.4.2 |  |  | 416 | 0 | 416 | [5 empty] | FALSE
OCB EQP -14 | EX NOTM TX A-11E.130 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.4.2 |  |  | 416 | 0 | 416 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-11E.130 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.4.2 |  |  | 416 | 0 | 416 | [5 empty] | FALSE
OCB EQP -6 | EX NOTM TX A-11E.130 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.4.2 |  |  | 416 | 0 | 416 | [5 empty] | FALSE
OCB EQP -17 | EX NOTM TX A-11E.120 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.4.6 |  |  | 5690 | 0 | 5690 | [5 empty] | FALSE
OCB EQP -19 | EX NOTM TX A-11E.120 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.4.6 |  |  | 5690 | 0 | 5690 | [5 empty] | FALSE
OCB EQP -18 | EX NOTM TX A-11E.120 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.4.6 |  |  | 5690 | 0 | 5690 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-11E.120 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.4.6 |  |  | 5690 | 0 | 5690 | [5 empty] | FALSE
OCB EQP -17 | EX NOTM TX A-11E.170 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.4.6 |  |  | 5686 | 0 | 5686 | [5 empty] | FALSE
OCB EQP -19 | EX NOTM TX A-11E.170 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.4.6 |  |  | 5686 | 0 | 5686 | [5 empty] | FALSE
OCB EQP -18 | EX NOTM TX A-11E.170 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.4.6 |  |  | 5686 | 0 | 5686 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM TX A-11E.170 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.4.6 |  |  | 5686 | 0 | 5686 | [5 empty] | FALSE
OCB EQP -3 | NOTM TX-New A-12.180 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 150 | 0 | 150 | motor grader | 0.01 | 1.5 | 0 | 1.5 | TRUE
OCB EQP -1 | NOTM TX-New A-12.180 | Not Started |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.6 |  |  | 150 | 0 | 150 | hydraulic excavator | 0.02 | 3 | 0 | 3 | TRUE
OCB EQP -9 | NOTM TX-New A-12.180 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 7 | 0 | 7 | 3.2.2.6 |  |  | 150 | 0 | 150 | Tipper | 0.083333 | 12.5 | 0 | 12.5 | TRUE
OCB EQP -12 | NOTM TX-New A-12.180 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.6 |  |  | 150 | 0 | 150 | Water Bowser | 0.02 | 3 | 0 | 3 | TRUE
OCB EQP -2 | NOTM TX-New A-12.180 | Not Started |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 150 | 0 | 150 | dozer | 0.01 | 1.5 | 0 | 1.5 | TRUE
OCB EQP -4 | NOTM TX-New A-12.180 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.6 |  |  | 150 | 0 | 150 | vibratory road roller | 0.02 | 3 | 0 | 3 | TRUE
OCB EQP -17 | NOTM TX-New A-12.070 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.4 |  |  | 1508 | 0 | 1508 | Air compressor | 0.0016 | 2.4128 | 0 | 2.4128 | TRUE
OCB EQP -16 | NOTM TX-New A-12.070 | Not Started |  |  | Nonlabor | Mechanical Broom | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.4 |  |  | 1508 | 0 | 1508 | Mechanical Broom | 0.0016 | 2.4128 | 0 | 2.4128 | TRUE
OCB EQP -19 | NOTM TX-New A-12.070 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.4 |  |  | 1508 | 0 | 1508 | Boiler | 0.0016 | 2.4128 | 0 | 2.4128 | TRUE
OCB EQP -18 | NOTM TX-New A-12.070 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.4 |  |  | 1508 | 0 | 1508 | [5 empty] | FALSE
OCB EQP -15 | NOTM TX-New A-12.070 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.4 |  |  | 1508 | 0 | 1508 | Generator | 0.0016 | 2.4128 | 0 | 2.4128 | TRUE
OCB EQP -17 | NOTM TX-New A-12.130 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.5 |  |  | 1527 | 0 | 1527 | Air compressor | 0.0012 | 1.8324 | 0 | 1.8324 | TRUE
OCB EQP -19 | NOTM TX-New A-12.130 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.5 |  |  | 1527 | 0 | 1527 | Boiler | 0.0012 | 1.8324 | 0 | 1.8324 | TRUE
OCB EQP -18 | NOTM TX-New A-12.130 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.5 |  |  | 1527 | 0 | 1527 | [5 empty] | FALSE
OCB EQP -15 | NOTM TX-New A-12.130 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.5 |  |  | 1527 | 0 | 1527 | Generator | 0.0012 | 1.8324 | 0 | 1.8324 | TRUE
OCB EQP -9 | NOTM TX-New A-12.080 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.2 |  |  | 80 | 0 | 80 | Tipper | 0.083333 | 6.6667 | 0 | 6.6667 | TRUE
OCB EQP -5 | NOTM TX-New A-12.080 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 80 | 0 | 80 | Pneumatic Roller | 0.062827 | 5.0262 | 0 | 5.0262 | TRUE
OCB EQP -13 | NOTM TX-New A-12.080 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 80 | 0 | 80 | [5 empty] | FALSE
OCB EQP -14 | NOTM TX-New A-12.080 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 80 | 0 | 80 | [5 empty] | FALSE
OCB EQP -15 | NOTM TX-New A-12.080 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 80 | 0 | 80 | Generator | 0.062827 | 5.0262 | 0 | 5.0262 | TRUE
OCB EQP -6 | NOTM TX-New A-12.080 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.2 |  |  | 80 | 0 | 80 | Smooth wheel tandem roller | 0.12565 | 10.0524 | 0 | 10.0524 | TRUE
OCB EQP -17 | NOTM TX-New A-12.090 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 1512 | 0 | 1512 | Air compressor | 0.0012 | 1.8144 | 0 | 1.8144 | TRUE
OCB EQP -19 | NOTM TX-New A-12.090 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 1512 | 0 | 1512 | Boiler | 0.0012 | 1.8144 | 0 | 1.8144 | TRUE
OCB EQP -18 | NOTM TX-New A-12.090 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 1512 | 0 | 1512 | [5 empty] | FALSE
OCB EQP -15 | NOTM TX-New A-12.090 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 1512 | 0 | 1512 | Generator | 0.0012 | 1.8144 | 0 | 1.8144 | TRUE
OCB EQP -9 | NOTM TX-New A-12.160 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.3 |  |  | 99 | 0 | 99 | Tipper | 0.083333 | 8.25 | 0 | 8.25 | TRUE
OCB EQP -5 | NOTM TX-New A-12.160 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 99 | 0 | 99 | Pneumatic Roller | 0.062827 | 6.2199 | 0 | 6.2199 | TRUE
OCB EQP -13 | NOTM TX-New A-12.160 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 99 | 0 | 99 | [5 empty] | FALSE
OCB EQP -14 | NOTM TX-New A-12.160 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 99 | 0 | 99 | [5 empty] | FALSE
OCB EQP -15 | NOTM TX-New A-12.160 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 99 | 0 | 99 | Generator | 0.062827 | 6.2199 | 0 | 6.2199 | TRUE
OCB EQP -6 | NOTM TX-New A-12.160 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.3 |  |  | 99 | 0 | 99 | Smooth wheel tandem roller | 0.12565 | 12.4398 | 0 | 12.4398 | TRUE
OCB EQP -9 | NOTM TX-New A-12.100 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.2 |  |  | 80 | 0 | 80 | Tipper | 0.083333 | 6.6667 | 0 | 6.6667 | TRUE
OCB EQP -5 | NOTM TX-New A-12.100 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 80 | 0 | 80 | Pneumatic Roller | 0.062827 | 5.0262 | 0 | 5.0262 | TRUE
OCB EQP -13 | NOTM TX-New A-12.100 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 80 | 0 | 80 | [5 empty] | FALSE
OCB EQP -14 | NOTM TX-New A-12.100 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 80 | 0 | 80 | [5 empty] | FALSE
OCB EQP -15 | NOTM TX-New A-12.100 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 80 | 0 | 80 | Generator | 0.062827 | 5.0262 | 0 | 5.0262 | TRUE
OCB EQP -6 | NOTM TX-New A-12.100 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.2 |  |  | 80 | 0 | 80 | Smooth wheel tandem roller | 0.12565 | 10.0524 | 0 | 10.0524 | TRUE
OCB EQP -9 | NOTM TX-New A-12.120 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.2 |  |  | 55 | 0 | 55 | Tipper | 0.083333 | 4.5833 | 0 | 4.5833 | TRUE
OCB EQP -5 | NOTM TX-New A-12.120 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 55 | 0 | 55 | Pneumatic Roller | 0.062827 | 3.4555 | 0 | 3.4555 | TRUE
OCB EQP -13 | NOTM TX-New A-12.120 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 55 | 0 | 55 | [5 empty] | FALSE
OCB EQP -14 | NOTM TX-New A-12.120 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 55 | 0 | 55 | [5 empty] | FALSE
OCB EQP -15 | NOTM TX-New A-12.120 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.2 |  |  | 55 | 0 | 55 | Generator | 0.062827 | 3.4555 | 0 | 3.4555 | TRUE
OCB EQP -6 | NOTM TX-New A-12.120 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.2 |  |  | 55 | 0 | 55 | Smooth wheel tandem roller | 0.12565 | 6.911 | 0 | 6.911 | TRUE
OCB EQP -9 | NOTM TX-New A-12.140 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.3 |  |  | 100 | 0 | 100 | Tipper | 0.083333 | 8.3333 | 0 | 8.3333 | TRUE
OCB EQP -5 | NOTM TX-New A-12.140 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 100 | 0 | 100 | Pneumatic Roller | 0.062827 | 6.2827 | 0 | 6.2827 | TRUE
OCB EQP -13 | NOTM TX-New A-12.140 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 100 | 0 | 100 | [5 empty] | FALSE
OCB EQP -14 | NOTM TX-New A-12.140 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 100 | 0 | 100 | [5 empty] | FALSE
OCB EQP -15 | NOTM TX-New A-12.140 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.3 |  |  | 100 | 0 | 100 | Generator | 0.062827 | 6.2827 | 0 | 6.2827 | TRUE
OCB EQP -6 | NOTM TX-New A-12.140 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.3 |  |  | 100 | 0 | 100 | Smooth wheel tandem roller | 0.12565 | 12.5654 | 0 | 12.5654 | TRUE
OCB EQP -17 | NOTM TX-New A-12.110 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 1512 | 0 | 1512 | Air compressor | 0.0012 | 1.8144 | 0 | 1.8144 | TRUE
OCB EQP -19 | NOTM TX-New A-12.110 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 1512 | 0 | 1512 | Boiler | 0.0012 | 1.8144 | 0 | 1.8144 | TRUE
OCB EQP -18 | NOTM TX-New A-12.110 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 1512 | 0 | 1512 | [5 empty] | FALSE
OCB EQP -15 | NOTM TX-New A-12.110 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 1512 | 0 | 1512 | Generator | 0.0012 | 1.8144 | 0 | 1.8144 | TRUE
OCB EQP -17 | NOTM TX-New A-12.150 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 1153 | 0 | 1153 | Air compressor | 0.0012 | 1.3836 | 0 | 1.3836 | TRUE
OCB EQP -19 | NOTM TX-New A-12.150 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 1153 | 0 | 1153 | Boiler | 0.0012 | 1.3836 | 0 | 1.3836 | TRUE
OCB EQP -18 | NOTM TX-New A-12.150 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 1153 | 0 | 1153 | [5 empty] | FALSE
OCB EQP -15 | NOTM TX-New A-12.150 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 1153 | 0 | 1153 | Generator | 0.0012 | 1.3836 | 0 | 1.3836 | TRUE
OCB EQP -17 | NOTM TX-New A-12.200 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 2417 | 0 | 2417 | [5 empty] | FALSE
OCB EQP -16 | NOTM TX-New A-12.200 | Not Started |  |  | Nonlabor | Mechanical Broom | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 2417 | 0 | 2417 | [5 empty] | FALSE
OCB EQP -19 | NOTM TX-New A-12.200 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 2417 | 0 | 2417 | [5 empty] | FALSE
OCB EQP -18 | NOTM TX-New A-12.200 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 2417 | 0 | 2417 | [5 empty] | FALSE
OCB EQP -15 | NOTM TX-New A-12.200 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.4 |  |  | 2417 | 0 | 2417 | [5 empty] | FALSE
OCB EQP -17 | NOTM TX-New A-12.220 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 672 | 0 | 672 | [5 empty] | FALSE
OCB EQP -19 | NOTM TX-New A-12.220 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 672 | 0 | 672 | [5 empty] | FALSE
OCB EQP -18 | NOTM TX-New A-12.220 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 672 | 0 | 672 | [5 empty] | FALSE
OCB EQP -15 | NOTM TX-New A-12.220 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.7.5 |  |  | 672 | 0 | 672 | [5 empty] | FALSE
OCB EQP -9 | NOTM TX-New A-12.210 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.7.2 |  |  | 235 | 0 | 235 | [5 empty] | FALSE
OCB EQP -5 | NOTM TX-New A-12.210 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.2 |  |  | 235 | 0 | 235 | [5 empty] | FALSE
OCB EQP -13 | NOTM TX-New A-12.210 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.2 |  |  | 235 | 0 | 235 | [5 empty] | FALSE
OCB EQP -14 | NOTM TX-New A-12.210 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.2 |  |  | 235 | 0 | 235 | [5 empty] | FALSE
OCB EQP -15 | NOTM TX-New A-12.210 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.2 |  |  | 235 | 0 | 235 | [5 empty] | FALSE
OCB EQP -6 | NOTM TX-New A-12.210 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.7.2 |  |  | 235 | 0 | 235 | [5 empty] | FALSE
OCB EQP -9 | NOTM TX-New A-12.230 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.7.3 |  |  | 85 | 0 | 85 | [5 empty] | FALSE
OCB EQP -5 | NOTM TX-New A-12.230 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.3 |  |  | 85 | 0 | 85 | [5 empty] | FALSE
OCB EQP -13 | NOTM TX-New A-12.230 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.3 |  |  | 85 | 0 | 85 | [5 empty] | FALSE
OCB EQP -14 | NOTM TX-New A-12.230 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.3 |  |  | 85 | 0 | 85 | [5 empty] | FALSE
OCB EQP -15 | NOTM TX-New A-12.230 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.3 |  |  | 85 | 0 | 85 | [5 empty] | FALSE
OCB EQP -6 | NOTM TX-New A-12.230 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.7.3 |  |  | 85 | 0 | 85 | [5 empty] | FALSE
OCB EQP -3 | NOTM TX-New A-12.190 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.7.1 |  |  | 576 | 0 | 576 | [5 empty] | FALSE
OCB EQP -9 | NOTM TX-New A-12.190 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 9 | 0 | 9 | 3.2.7.1 |  |  | 576 | 0 | 576 | [5 empty] | FALSE
OCB EQP -12 | NOTM TX-New A-12.190 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.7.1 |  |  | 576 | 0 | 576 | [5 empty] | FALSE
OCB EQP -8 | NOTM TX-New A-12.190 | Not Started |  |  | Nonlabor | Loader | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.7.1 |  |  | 576 | 0 | 576 | [5 empty] | FALSE
OCB EQP -4 | NOTM TX-New A-12.190 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.7.1 |  |  | 576 | 0 | 576 | [5 empty] | FALSE
OCB EQP -17 | EXE TXY P A-01.070 | Completed |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 40 | 0 | 0 | 3.2.3.4 |  |  | 13000 | 8394 | 0 | Air compressor | 0.0016 | 20.8 | 13.4304 | 0 | TRUE
OCB EQP -16 | EXE TXY P A-01.070 | Completed |  |  | Nonlabor | Mechanical Broom | 0 | 0 | 0 | 40 | 0 | 0 | 3.2.3.4 |  |  | 13000 | 8394 | 0 | Mechanical Broom | 0.0016 | 20.8 | 13.4304 | 0 | TRUE
OCB EQP -19 | EXE TXY P A-01.070 | Completed |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 40 | 0 | 0 | 3.2.3.4 |  |  | 13000 | 8394 | 0 | Boiler | 0.0016 | 20.8 | 13.4304 | 0 | TRUE
OCB EQP -18 | EXE TXY P A-01.070 | Completed |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 40 | 0 | 0 | 3.2.3.4 |  |  | 13000 | 8394 | 0 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-01.070 | Completed |  |  | Nonlabor | Generator | 0 | 0 | 0 | 40 | 0 | 0 | 3.2.3.4 |  |  | 13000 | 8394 | 0 | Generator | 0.0016 | 20.8 | 13.4304 | 0 | TRUE
OCB EQP -17 | EXE TXY P A-01.130 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.5 |  |  | 12000 | 0 | 12000 | Air compressor | 0.0012 | 14.4 | 0 | 14.4 | TRUE
OCB EQP -19 | EXE TXY P A-01.130 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.5 |  |  | 12000 | 0 | 12000 | Boiler | 0.0012 | 14.4 | 0 | 14.4 | TRUE
OCB EQP -18 | EXE TXY P A-01.130 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.5 |  |  | 12000 | 0 | 12000 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-01.130 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.5 |  |  | 12000 | 0 | 12000 | Generator | 0.0012 | 14.4 | 0 | 14.4 | TRUE
OCB EQP -5 | EXE TXY P A-01.080 | In Progress |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 2776 | 0 | 3 | 3.2.3.2 |  |  | 885 | 597 | 288 | Pneumatic Roller | 0.062827 | 55.6021 | 37.5079 | 18.0942 | TRUE
OCB EQP -13 | EXE TXY P A-01.080 | In Progress |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 2776 | 0 | 3 | 3.2.3.2 |  |  | 885 | 597 | 288 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-01.080 | In Progress |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 2776 | 0 | 3 | 3.2.3.2 |  |  | 885 | 597 | 288 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-01.080 | In Progress |  |  | Nonlabor | Generator | 0 | 0 | 0 | 2776 | 0 | 3 | 3.2.3.2 |  |  | 885 | 597 | 288 | Generator | 0.062827 | 55.6021 | 37.5079 | 18.0942 | TRUE
OCB EQP -6 | EXE TXY P A-01.080 | In Progress |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 2776 | 0 | 6 | 3.2.3.2 |  |  | 885 | 597 | 288 | Smooth wheel tandem roller | 0.12565 | 111.2042 | 75.0157 | 36.1885 | TRUE
OCB EQP -17 | EXE TXY P A-01.090 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 12000 | 0 | 12000 | Air compressor | 0.0012 | 14.4 | 0 | 14.4 | TRUE
OCB EQP -19 | EXE TXY P A-01.090 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 12000 | 0 | 12000 | Boiler | 0.0012 | 14.4 | 0 | 14.4 | TRUE
OCB EQP -18 | EXE TXY P A-01.090 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 12000 | 0 | 12000 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-01.090 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 12000 | 0 | 12000 | Generator | 0.0012 | 14.4 | 0 | 14.4 | TRUE
OCB EQP -9 | EXE TXY P A-01.160 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.3 |  |  | 750 | 0 | 750 | Tipper | 0.083333 | 62.5 | 0 | 62.5 | TRUE
OCB EQP -5 | EXE TXY P A-01.160 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.3 |  |  | 750 | 0 | 750 | Pneumatic Roller | 0.062827 | 47.1204 | 0 | 47.1204 | TRUE
OCB EQP -13 | EXE TXY P A-01.160 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.3 |  |  | 750 | 0 | 750 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-01.160 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.3 |  |  | 750 | 0 | 750 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-01.160 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.3 |  |  | 750 | 0 | 750 | Generator | 0.062827 | 47.1204 | 0 | 47.1204 | TRUE
OCB EQP -6 | EXE TXY P A-01.160 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 5 | 0 | 5 | 3.2.3.3 |  |  | 750 | 0 | 750 | Smooth wheel tandem roller | 0.12565 | 94.2408 | 0 | 94.2408 | TRUE
OCB EQP -9 | EXE TXY P A-01.100 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 5 | 0 | 5 | 3.2.3.2 |  |  | 885 | 0 | 885 | Tipper | 0.083333 | 73.75 | 0 | 73.75 | TRUE
OCB EQP -5 | EXE TXY P A-01.100 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.2 |  |  | 885 | 0 | 885 | Pneumatic Roller | 0.062827 | 55.6021 | 0 | 55.6021 | TRUE
OCB EQP -13 | EXE TXY P A-01.100 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.2 |  |  | 885 | 0 | 885 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-01.100 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.2 |  |  | 885 | 0 | 885 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-01.100 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.2 |  |  | 885 | 0 | 885 | Generator | 0.062827 | 55.6021 | 0 | 55.6021 | TRUE
OCB EQP -6 | EXE TXY P A-01.100 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 7 | 0 | 7 | 3.2.3.2 |  |  | 885 | 0 | 885 | Smooth wheel tandem roller | 0.12565 | 111.2042 | 0 | 111.2042 | TRUE
OCB EQP -9 | EXE TXY P A-01.120 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.2 |  |  | 845 | 0 | 845 | Tipper | 0.083333 | 70.4167 | 0 | 70.4167 | TRUE
OCB EQP -5 | EXE TXY P A-01.120 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.2 |  |  | 845 | 0 | 845 | Pneumatic Roller | 0.062827 | 53.089 | 0 | 53.089 | TRUE
OCB EQP -13 | EXE TXY P A-01.120 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.2 |  |  | 845 | 0 | 845 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-01.120 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.2 |  |  | 845 | 0 | 845 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-01.120 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.2 |  |  | 845 | 0 | 845 | Generator | 0.062827 | 53.089 | 0 | 53.089 | TRUE
OCB EQP -6 | EXE TXY P A-01.120 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 5 | 0 | 5 | 3.2.3.2 |  |  | 845 | 0 | 845 | Smooth wheel tandem roller | 0.12565 | 106.178 | 0 | 106.178 | TRUE
OCB EQP -9 | EXE TXY P A-01.140 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.3 |  |  | 750 | 0 | 750 | Tipper | 0.083333 | 62.5 | 0 | 62.5 | TRUE
OCB EQP -5 | EXE TXY P A-01.140 | Not Started |  |  | Nonlabor | Pneumatic Roller | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.3 |  |  | 750 | 0 | 750 | Pneumatic Roller | 0.062827 | 47.1204 | 0 | 47.1204 | TRUE
OCB EQP -13 | EXE TXY P A-01.140 | Not Started |  |  | Nonlabor | Asphalt Mixing Plant | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.3 |  |  | 750 | 0 | 750 | [5 empty] | FALSE
OCB EQP -14 | EXE TXY P A-01.140 | Not Started |  |  | Nonlabor | Asphalt Paver | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.3 |  |  | 750 | 0 | 750 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-01.140 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.3 |  |  | 750 | 0 | 750 | Generator | 0.062827 | 47.1204 | 0 | 47.1204 | TRUE
OCB EQP -6 | EXE TXY P A-01.140 | Not Started |  |  | Nonlabor | Smooth wheel tandem Roller | 0 | 0 | 0 | 5 | 0 | 5 | 3.2.3.3 |  |  | 750 | 0 | 750 | Smooth wheel tandem roller | 0.12565 | 94.2408 | 0 | 94.2408 | TRUE
OCB EQP -17 | EXE TXY P A-01.110 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 12000 | 0 | 12000 | Air compressor | 0.0012 | 14.4 | 0 | 14.4 | TRUE
OCB EQP -19 | EXE TXY P A-01.110 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 12000 | 0 | 12000 | Boiler | 0.0012 | 14.4 | 0 | 14.4 | TRUE
OCB EQP -18 | EXE TXY P A-01.110 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 12000 | 0 | 12000 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-01.110 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 12000 | 0 | 12000 | Generator | 0.0012 | 14.4 | 0 | 14.4 | TRUE
OCB EQP -17 | EXE TXY P A-01.150 | Not Started |  |  | Nonlabor | Air compressor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 12000 | 0 | 12000 | Air compressor | 0.0012 | 14.4 | 0 | 14.4 | TRUE
OCB EQP -19 | EXE TXY P A-01.150 | Not Started |  |  | Nonlabor | Boiler | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 12000 | 0 | 12000 | Boiler | 0.0012 | 14.4 | 0 | 14.4 | TRUE
OCB EQP -18 | EXE TXY P A-01.150 | Not Started |  |  | Nonlabor | Bitumen Distributor | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 12000 | 0 | 12000 | [5 empty] | FALSE
OCB EQP -15 | EXE TXY P A-01.150 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 0 | 0 | 0 | 3.2.3.6 |  |  | 12000 | 0 | 12000 | Generator | 0.0012 | 14.4 | 0 | 14.4 | TRUE
OCB EQP -3 | EXE TXY P A-01.060 | Completed |  |  | Nonlabor | Grader | 0 | 0 | 0 | 104 | 0 | 0 | 3.2.3.1 |  |  | 4830 | 3638 | 0 | motor grader | 0.02 | 96.6 | 72.76 | 0 | TRUE
OCB EQP -9 | EXE TXY P A-01.060 | Completed |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 104 | 0 | 0 | 3.2.3.1 |  |  | 4830 | 3638 | 0 | Tipper | 0.083333 | 402.5 | 303.1667 | 0 | TRUE
OCB EQP -12 | EXE TXY P A-01.060 | Completed |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 104 | 0 | 0 | 3.2.3.1 |  |  | 4830 | 3638 | 0 | Water Bowser | 0.033 | 159.39 | 120.054 | 0 | TRUE
OCB EQP -8 | EXE TXY P A-01.060 | Completed |  |  | Nonlabor | Loader | 0 | 0 | 0 | 104 | 0 | 0 | 3.2.3.1 |  |  | 4830 | 3638 | 0 | Loader | 0.04 | 193.2 | 145.52 | 0 | TRUE
OCB EQP -4 | EXE TXY P A-01.060 | Completed |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 104 | 0 | 0 | 3.2.3.1 |  |  | 4830 | 3638 | 0 | vibratory road roller | 0.04 | 193.2 | 145.52 | 0 | TRUE
OCB EQP -3 | NOTM TX-New A-12.060 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.3.1 |  |  | 680 | 0 | 680 | motor grader | 0.02 | 13.6 | 0 | 13.6 | TRUE
OCB EQP -9 | NOTM TX-New A-12.060 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 8 | 0 | 8 | 3.2.3.1 |  |  | 680 | 0 | 680 | Tipper | 0.083333 | 56.6667 | 0 | 56.6667 | TRUE
OCB EQP -12 | NOTM TX-New A-12.060 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.3.1 |  |  | 680 | 0 | 680 | Water Bowser | 0.033 | 22.44 | 0 | 22.44 | TRUE
OCB EQP -8 | NOTM TX-New A-12.060 | Not Started |  |  | Nonlabor | Loader | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.1 |  |  | 680 | 0 | 680 | Loader | 0.04 | 27.2 | 0 | 27.2 | TRUE
OCB EQP -4 | NOTM TX-New A-12.060 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 4 | 0 | 4 | 3.2.3.1 |  |  | 680 | 0 | 680 | vibratory road roller | 0.04 | 27.2 | 0 | 27.2 | TRUE
OCB EQP -1 | EX TS A-14.020 | Not Started |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 2 | 0 | 2 | 3.1.1.1a |  |  | 100 | 0 | 100 | hydraulic excavator | 0.025 | 2.5 | 0 | 2.5 | TRUE
OCB EQP -9 | EX TS A-14.020 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 4 | 0 | 4 | 3.1.1.1a |  |  | 100 | 0 | 100 | Tipper | 0.044 | 4.4 | 0 | 4.4 | TRUE
OCB EQP -3 | EX TS A-14.030 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.5 |  |  | 5129 | 0 | 5129 | motor grader | 0.01 | 51.29 | 0 | 51.29 | TRUE
OCB EQP -1 | EX TS A-14.030 | Not Started |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.5 |  |  | 5129 | 0 | 5129 | hydraulic excavator | 0.02 | 102.58 | 0 | 102.58 | TRUE
OCB EQP -9 | EX TS A-14.030 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 10 | 0 | 10 | 3.2.2.5 |  |  | 5129 | 0 | 5129 | Tipper | 0.083333 | 427.4167 | 0 | 427.4167 | TRUE
OCB EQP -12 | EX TS A-14.030 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.5 |  |  | 5129 | 0 | 5129 | Water Bowser | 0.02 | 102.58 | 0 | 102.58 | TRUE
OCB EQP -2 | EX TS A-14.030 | Not Started |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.5 |  |  | 5129 | 0 | 5129 | dozer | 0.01 | 51.29 | 0 | 51.29 | TRUE
OCB EQP -4 | EX TS A-14.030 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.5 |  |  | 5129 | 0 | 5129 | vibratory road roller | 0.02 | 102.58 | 0 | 102.58 | TRUE
OCB EQP -3 | EX TS A-14.040 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.6 |  |  | 1750 | 0 | 1750 | motor grader | 0.01 | 17.5 | 0 | 17.5 | TRUE
OCB EQP -1 | EX TS A-14.040 | Not Started |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.2.6 |  |  | 1750 | 0 | 1750 | hydraulic excavator | 0.02 | 35 | 0 | 35 | TRUE
OCB EQP -9 | EX TS A-14.040 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 13 | 0 | 13 | 3.2.2.6 |  |  | 1750 | 0 | 1750 | Tipper | 0.083333 | 145.8333 | 0 | 145.8333 | TRUE
OCB EQP -12 | EX TS A-14.040 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.2.6 |  |  | 1750 | 0 | 1750 | Water Bowser | 0.02 | 35 | 0 | 35 | TRUE
OCB EQP -2 | EX TS A-14.040 | Not Started |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.6 |  |  | 1750 | 0 | 1750 | dozer | 0.01 | 17.5 | 0 | 17.5 | TRUE
OCB EQP -4 | EX TS A-14.040 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 3 | 0 | 3 | 3.2.2.6 |  |  | 1750 | 0 | 1750 | vibratory road roller | 0.02 | 35 | 0 | 35 | TRUE
OCB EQP -1 | EX NOTM RS B-08.020 | Completed |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 360 | 0 | 0 | 3.1.1.1 |  |  | 100 | 0 | 0 | hydraulic excavator | 0.025 | 2.5 | 0 | 0 | TRUE
OCB EQP -9 | EX NOTM RS B-08.020 | Completed |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 360 | 0 | 0 | 3.1.1.1 |  |  | 100 | 0 | 0 | Tipper | 0.044 | 4.4 | 0 | 0 | TRUE
OCB EQP -3 | EX NOTM RS B-08.030 | Completed |  |  | Nonlabor | Grader | 0 | 0 | 0 | 160 | 0 | 0 | 3.1.1.2 |  |  | 12368 | 12217 | 0 | motor grader | 0.01 | 123.68 | 122.17 | 0 | TRUE
OCB EQP -1 | EX NOTM RS B-08.030 | Completed |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 160 | 0 | 0 | 3.1.1.2 |  |  | 12368 | 12217 | 0 | hydraulic excavator | 0.02 | 247.36 | 244.34 | 0 | TRUE
OCB EQP -9 | EX NOTM RS B-08.030 | Completed |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 160 | 0 | 0 | 3.1.1.2 |  |  | 12368 | 12217 | 0 | Tipper | 0.083333 | 1030.6667 | 1018.0833 | 0 | TRUE
OCB EQP -12 | EX NOTM RS B-08.030 | Completed |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 160 | 0 | 0 | 3.1.1.2 |  |  | 12368 | 12217 | 0 | Water Bowser | 0.02 | 247.36 | 244.34 | 0 | TRUE
OCB EQP -2 | EX NOTM RS B-08.030 | Completed |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 160 | 0 | 0 | 3.1.1.2 |  |  | 12368 | 12217 | 0 | dozer | 0.01 | 123.68 | 122.17 | 0 | TRUE
OCB EQP -4 | EX NOTM RS B-08.030 | Completed |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 160 | 0 | 0 | 3.1.1.2 |  |  | 12368 | 12217 | 0 | vibratory road roller | 0.02 | 247.36 | 244.34 | 0 | TRUE
OCB EQP -3 | EX NOTM RS B-08.040 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 16 | 0 | 16 | 3.1.1.3 |  |  | 8340 | 0 | 8340 | motor grader | 0.01 | 83.4 | 0 | 83.4 | TRUE
OCB EQP -1 | EX NOTM RS B-08.040 | Not Started |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 16 | 0 | 16 | 3.1.1.3 |  |  | 8340 | 0 | 8340 | hydraulic excavator | 0.02 | 166.8 | 0 | 166.8 | TRUE
OCB EQP -9 | EX NOTM RS B-08.040 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 16 | 0 | 16 | 3.1.1.3 |  |  | 8340 | 0 | 8340 | Tipper | 0.083333 | 695 | 0 | 695 | TRUE
OCB EQP -12 | EX NOTM RS B-08.040 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 16 | 0 | 16 | 3.1.1.3 |  |  | 8340 | 0 | 8340 | Water Bowser | 0.02 | 166.8 | 0 | 166.8 | TRUE
OCB EQP -2 | EX NOTM RS B-08.040 | Not Started |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 16 | 0 | 16 | 3.1.1.3 |  |  | 8340 | 0 | 8340 | dozer | 0.01 | 83.4 | 0 | 83.4 | TRUE
OCB EQP -4 | EX NOTM RS B-08.040 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 16 | 0 | 16 | 3.1.1.3 |  |  | 8340 | 0 | 8340 | vibratory road roller | 0.02 | 166.8 | 0 | 166.8 | TRUE
OCB EQP -1 | EX NOTM RS C-08.020 | Not Started |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 2 | 0 | 2 | 3.1.1.1 |  |  | 100 | 0 | 100 | hydraulic excavator | 0.025 | 2.5 | 0 | 2.5 | TRUE
OCB EQP -9 | EX NOTM RS C-08.020 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 4 | 0 | 4 | 3.1.1.1 |  |  | 100 | 0 | 100 | Tipper | 0.044 | 4.4 | 0 | 4.4 | TRUE
OCB EQP -3 | EX NOTM RS C-08.030 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.5 |  |  | 1259 | 0 | 1259 | motor grader | 0.01 | 12.59 | 0 | 12.59 | TRUE
OCB EQP -1 | EX NOTM RS C-08.030 | Not Started |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.5 |  |  | 1259 | 0 | 1259 | hydraulic excavator | 0.02 | 25.18 | 0 | 25.18 | TRUE
OCB EQP -9 | EX NOTM RS C-08.030 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 9 | 0 | 9 | 3.2.2.5 |  |  | 1259 | 0 | 1259 | Tipper | 0.083333 | 104.9167 | 0 | 104.9167 | TRUE
OCB EQP -12 | EX NOTM RS C-08.030 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.5 |  |  | 1259 | 0 | 1259 | Water Bowser | 0.02 | 25.18 | 0 | 25.18 | TRUE
OCB EQP -2 | EX NOTM RS C-08.030 | Not Started |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.5 |  |  | 1259 | 0 | 1259 | dozer | 0.01 | 12.59 | 0 | 12.59 | TRUE
OCB EQP -4 | EX NOTM RS C-08.030 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.2.5 |  |  | 1259 | 0 | 1259 | vibratory road roller | 0.02 | 25.18 | 0 | 25.18 | TRUE
OCB EQP -3 | EX NOTM RS C-08.040 | Not Started |  |  | Nonlabor | Grader | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 50 | 0 | 50 | motor grader | 0.01 | 0.5 | 0 | 0.5 | TRUE
OCB EQP -1 | EX NOTM RS C-08.040 | Not Started |  |  | Nonlabor | Excavator | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 50 | 0 | 50 | hydraulic excavator | 0.02 | 1 | 0 | 1 | TRUE
OCB EQP -9 | EX NOTM RS C-08.040 | Not Started |  |  | Nonlabor | Tipper/ Truck | 0 | 0 | 0 | 5 | 0 | 5 | 3.2.2.6 |  |  | 50 | 0 | 50 | Tipper | 0.083333 | 4.1667 | 0 | 4.1667 | TRUE
OCB EQP -12 | EX NOTM RS C-08.040 | Not Started |  |  | Nonlabor | Water Browser | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 50 | 0 | 50 | Water Bowser | 0.02 | 1 | 0 | 1 | TRUE
OCB EQP -2 | EX NOTM RS C-08.040 | Not Started |  |  | Nonlabor | Dozer | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 50 | 0 | 50 | dozer | 0.01 | 0.5 | 0 | 0.5 | TRUE
OCB EQP -4 | EX NOTM RS C-08.040 | Not Started |  |  | Nonlabor | Vibratory Roller | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.2.6 |  |  | 50 | 0 | 50 | vibratory road roller | 0.02 | 1 | 0 | 1 | TRUE
OCB EQP -15 | EXE RS A-08.251 | In Progress |  |  | Nonlabor | Generator | 0 | 0 | 0 | 40 | 0 | 96 | 3.2.13.5f (i) |  |  | 24 | 10 | 14 | [5 empty] | FALSE
OCB EQP - 21 | EXE RS A-08.251 | In Progress |  |  | Nonlabor | Transit Mixture | 0 | 0 | 0 | 40 | 0 | 60 | 3.2.13.5f (i) |  |  | 24 | 10 | 14 | [5 empty] | FALSE
OCB EQP - 20 | EXE RS A-08.251 | In Progress |  |  | Nonlabor | Batching Plant | 0 | 0 | 0 | 40 | 0 | 4 | 3.2.13.5f (i) |  |  | 24 | 10 | 14 | [5 empty] | FALSE
OCB EQP - 22 | EXE RS A-08.252 | In Progress |  |  | Nonlabor | Concrete Mixture | 0 | 0 | 0 | 40 | 0 | 36 | 3.2.13.5f (ii) |  |  | 253 | 100 | 153 | [5 empty] | FALSE
OCB EQP -15 | EXE RS A-08.253 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 16 | 0 | 16 | 3.2.13.5f (iii) |  |  | 21 | 0 | 21 | [5 empty] | FALSE
OCB EQP - 21 | EXE RS A-08.253 | Not Started |  |  | Nonlabor | Transit Mixture | 0 | 0 | 0 | 10 | 0 | 10 | 3.2.13.5f (iii) |  |  | 21 | 0 | 21 | [5 empty] | FALSE
OCB EQP - 20 | EXE RS A-08.253 | Not Started |  |  | Nonlabor | Batching Plant | 0 | 0 | 0 | 1 | 0 | 1 | 3.2.13.5f (iii) |  |  | 21 | 0 | 21 | [5 empty] | FALSE
OCB EQP -15 | EX NOTM RS C-08.071 | Not Started |  |  | Nonlabor | Generator | 0 | 0 | 0 | 48 | 0 | 48 | 3.2.12.6c |  |  | 28 | 0 | 28 | Generator | 0.4 | 11.2 | 0 | 11.2 | TRUE
OCB EQP - 21 | EX NOTM RS C-08.071 | Not Started |  |  | Nonlabor | Transit Mixture | 0 | 0 | 0 | 30 | 0 | 30 | 3.2.12.6c |  |  | 28 | 0 | 28 | Transit Mixer | 0.25 | 7 | 0 | 7 | TRUE
OCB EQP - 20 | EX NOTM RS C-08.071 | Not Started |  |  | Nonlabor | Batching Plant | 0 | 0 | 0 | 2 | 0 | 2 | 3.2.12.6c |  |  | 28 | 0 | 28 | Batching Plant | 0.016667 | 0.46667 | 0 | 0.46667 | TRUE