## Sheet1
rsrc_id | task_id | TASK__status_code | role_id | acct_id | rsrc_type | target_qty | act_qty | remain_qty | user_field_130 | delete_record_flag
Resource ID | Activity ID | (*)Activity Status | Role ID | Cost Account ID | (*)Resource Type |  |  |  | (*)BOQ Item No | Delete This Row
R.3.2.2.1 | EXE RE A-05.020 | Completed |  |  | Material | 12216 | 12216 | 0 | 3.2.2.1
R.3.2.2.2 | EXE RE A-05.030 | Completed |  |  | Material | 13833 | 12899 | 0 | 3.2.2.2
R.3.2.2.3 | EXE RE A-05.040 | Completed |  |  | Material | 6596 | 6596 | 0 | 3.2.2.3
R.3.2.2.4 | EXE RE A-05.050 | In Progress |  |  | Material | 121373 | 132534 | 0 | 3.2.2.4
R.3.2.12.6 | EX NOTM TX A-11E.280 | Not Started |  |  | Material | 105 | 0 | 105 | 3.2.12.6
R.3.2.12.6 | EXE RS A-08.056 | In Progress |  |  | Material | 230 | 225 | 5 | 3.2.12.6
R.3.2.13.1 | EXE RS A-08.130 | Not Started |  |  | Material | 500 | 0 | 500 | 3.2.13.1
R.3.1.1.1 | EXE RS A-08.020 | In Progress |  |  | Material | 46642 | 6927 | 39915 | 3.1.1.1
R.3.1.1.2 | EX NOTM RS A-08.032 | In Progress |  |  | Material | 98500 | 17701 | 80799 | 3.2.2.5
R.3.1.1.3 | EX NOTM RS A-08.042 | Not Started |  |  | Material | 50 | 0 | 50 | 3.2.2.6
R.3.1.2.1 | EX SR A-13.050 | In Progress |  |  | Material | 1738 | 840 | 898 | 3.1.2.1
R.3.1.2.4 | EX SR A-13.060 | In Progress |  |  | Material | 10800 | 5055 | 5745 | 3.1.2.4
R.3.1.2.2 | EX SR A-13.070 | In Progress |  |  | Material | 481 | 228 | 253 | 3.1.2.2
R.3.1.2.5 | EX SR A-13.080 | In Progress |  |  | Material | 7668 | 2386 | 5282 | 3.1.2.5
R.3.1.2.3 | EX SR A-13.090 | In Progress |  |  | Material | 481 | 144 | 337 | 3.1.2.3
R.3.2.11.1 | EX SR A-13.140 | Not Started |  |  | Material | 2215 | 0 | 2215 | 3.2.11.1
R.4.3.1 | EXE AGL ALL-15.30 | In Progress |  |  | Material | 142 | 15 | 127 | 4.3.1
R.4.3.3 | EXE AGL ALL-15.50 | In Progress |  |  | Material | 6 | 4 | 2 | 4.3.3
R.4.3.4 | EXE AGL ALL-15.60 | Not Started |  |  | Material | 0 | 0 | 0 | 4.3.4
R.3.2.2.7 | EXE RE A-05.060 | Completed |  |  | Material | 17836 | 11890 | 0 | 3.2.2.7
R.3.2.2.8 | EXE RE A-05.070 | Completed |  |  | Material | 400 | 395 | 0 | 3.2.2.8
R.3.2.8 | EX SR A-13.130 | Not Started |  |  | Material | 750 | 0 | 750 | 3.2.8
R.3.2.2.15 | EXE RE A-05.080 | Completed |  |  | Material | 0 | 0 | 0 | 3.2.2.15
R.4.2.1 | EXE AGL ALL-15.20 | Not Started |  |  | Material | 1980 | 0 | 1980 | 4.2.1
R.4.6.1.1 | EXE AGL ALL-15.100 | Not Started |  |  | Material | 1 | 0 | 1 | 4.6.1.1
R.4.8 | EXE AGL ALL-15.150 | Not Started |  |  | Material | 200 | 0 | 200 | 4.8
R.4.9 | EXE AGL ALL-15.160 | Not Started |  |  | Material | 1 | 0 | 1 | 4.9
R.4.10 | EXE AGL ALL-15.170 | Not Started |  |  | Material | 1 | 0 | 1 | 4.10
R.4.11.1 | EXE AGL ALL-15.180 | Not Started |  |  | Material | 2 | 0 | 2 | 4.11.1
R.4.12.1 | EXE AGL ALL-15.210 | Not Started |  |  | Material | 1 | 0 | 1 | 4.12.1
R.4.6.2.1 | EXE AGL ALL-15.110 | Not Started |  |  | Material | 20 | 0 | 20 | 4.6.2.1
R.4.6.3.1 | EXE AGL ALL-15.120 | Not Started |  |  | Material | 1 | 0 | 1 | 4.6.3.1
R.4.7.1 | EXE AGL ALL-15.130 | Not Started |  |  | Material | 1 | 0 | 1 | 4.7.1
R.4.7.2 | EXE AGL ALL-15.140 | Not Started |  |  | Material | 1 | 0 | 1 | 4.7.2
R.4.11.2 | EXE AGL ALL-15.190 | Not Started |  |  | Material | 1 | 0 | 1 | 4.11.2
R.4.11.3 | EXE AGL ALL-15.200 | Not Started |  |  | Material | 1 | 0 | 1 | 4.11.3
R.4.12.2 | EXE AGL ALL-15.220 | Not Started |  |  | Material | 1 | 0 | 1 | 4.12.2
R.3.2.2.5 | EXE TXY P A-02.030 | In Progress |  |  | Material | 96550 | 77306 | 19244 | 3.2.2.5
R.3.2.2.6 | EXE TXY P A-02.040 | Not Started |  |  | Material | 17000 | 0 | 17000 | 3.2.2.6
R.3.2.1.5 | EXE CGD 1050 | In Progress |  |  | Material | 264269 | 97694 | 166577 | 3.2.1.5
R.3.2.1.7 | EXE CGD 1070 | In Progress |  |  | Material | 2291 | 1575 | 717 | 3.2.1.7
R.3.2.2.5 | EXE TXY P A-01.030 | Completed |  |  | Material | 891 | 891 | 0 | 3.2.2.5
R.3.2.2.6 | EXE TXY P A-01.040 | Completed |  |  | Material | 24817 | 21817 | 0 | 3.2.2.6
R.3.2.1.2 | EXE CGD 1020 | In Progress |  |  | Material | 13875 | 2248 | 11628 | 3.2.1.2
R.3.2.1.3 | EXE CGD 1030 | In Progress |  |  | Material | 2175 | 310 | 1865 | 3.2.1.3
R.3.2.1.4 | EXE CGD 1040 | In Progress |  |  | Material | 11191 | 7193 | 3998 | 3.2.1.4
R.3.2.1.6 | EXE CGD 1060 | In Progress |  |  | Material | 0 | 0 | 0 | 3.2.1.6
R.3.2.2.9 | EXE TXY P A-01.170 | Not Started |  |  | Material | 6220 | 0 | 6220 | 3.2.2.9
R.3.2.7.4 | EXE TXY P A-01.200 | Not Started |  |  | Material | 6000 | 0 | 6000 | 3.2.7.4
R.3.2.7.5 | EXE TXY P A-01.220 | Not Started |  |  | Material | 5888 | 0 | 5888 | 3.2.7.5
R.3.2.7.2 | EXE TXY P A-01.210 | Not Started |  |  | Material | 490 | 0 | 490 | 3.2.7.2
R.3.2.7.3 | EXE TXY P A-01.230 | Not Started |  |  | Material | 75 | 0 | 75 | 3.2.7.3
R.3.2.7.1 | EXE TXY P A-01.190 | Not Started |  |  | Material | 1750 | 0 | 1750 | 3.2.7.1
R.3.2.2.1 | EXE RE A-06.020 | Completed |  |  | Material | 20450 | 19553 | 0 | 3.2.2.1
R.3.2.2.2 | EXE RE A-06.030 | Completed |  |  | Material | 18821 | 16867 | 0 | 3.2.2.2
R.3.2.2.3 | EXE RE A-06.040 | Completed |  |  | Material | 9092 | 9092 | 0 | 3.2.2.3
R.3.2.2.4 | EXE RE A-06.050 | In Progress |  |  | Material | 220650 | 207044 | 13606 | 3.2.2.4
R.3.2.2.7 | EXE RE A-06.060 | In Progress |  |  | Material | 22000 | 15796 | 6204 | 3.2.2.7
R.3.2.2.8 | EXE RE A-06.070 | Not Started |  |  | Material | 200 | 0 | 200 | 3.2.2.8
R.3.2.2.15 | EXE RE A-06.080 | Completed |  |  | Material | 0 | 0 | 0 | 3.2.2.15
R.3.2.2.3 | EXE RE A-07.040 | Completed |  |  | Material | 2600 | 2600 | 0 | 3.2.2.3
R.3.2.2.4 | EXE RE A-07.050 | In Progress |  |  | Material | 34375 | 30469 | 3906 | 3.2.2.4
R.3.2.2.7 | EXE RE A-07.060 | In Progress |  |  | Material | 6700 | 4453 | 2247 | 3.2.2.7
R.3.2.2.8 | EXE RE A-07.070 | In Progress |  |  | Material | 165 | 164 | 1 | 3.2.2.8
R.3.2.2.15 | EXE RE A-07.080 | Completed |  |  | Material | 0 | 0 | 0 | 3.2.2.15
R.3.2.2.1 | EXE RE A-07.020 | Completed |  |  | Material | 5534 | 5534 | 0 | 3.2.2.1
R.3.2.2.2 | EXE RE A-07.030 | Completed |  |  | Material | 5546 | 5546 | 0 | 3.2.2.2
R.3.2.2.6 | EXE TXY P A-03.040 | In Progress |  |  | Material | 30183 | 2879 | 27304 | 3.2.2.6
R.3.2.2.5 | EXE TXY P A-03.030 | In Progress |  |  | Material | 161006 | 151985 | 9021 | 3.2.2.5
R.3.2.2.6 | EX SR A-13.040 | In Progress |  |  | Material | 25000 | 13482 | 11518 | 3.2.2.6
R.3.2.2.5 | EX SR A-13.030 | In Progress |  |  | Material | 20500 | 19923 | 577 | 3.2.2.5
R.4.1.1.1 | EXE AGL ALL-15.10 | Not Started |  |  | Material | 3235 | 0 | 3235 | 4.1.1.1
R.3.2.9 | EXE RS A-08.050 | Completed |  |  | Material | 28900 | 28900 | 0 | 3.2.9
R.3.2.10 | EXE RS A-08.060 | In Progress |  |  | Material | 54900 | 15554 | 39346 | 3.2.10
R.3.2.2.6 | EXE TXY P A-04.040 | Not Started |  |  | Material | 13000 | 0 | 13000 | 3.2.2.6
R.3.2.2.5 | EXE TXY P A-04.030 | In Progress |  |  | Material | 103844 | 70963 | 32881 | 3.2.2.5
R.3.1.1.1a | EX NOTM TX A-09L.020 | Completed |  |  | Material | 3150 | 3115 | 0 | 3.1.1.1a
R.3.2.2.5 | EX NOTM TX A-09L.030 | Completed |  |  | Material | 100 | 0 | 0 | 3.2.2.5
R.3.2.2.6 | EX NOTM TX A-09L.040 | Completed |  |  | Material | 2500 | 3437 | 0 | 3.2.2.6
R.3.1.1.1a | EX NOTM TX A-10K.020 | In Progress |  |  | Material | 6550 | 6543 | 7 | 3.1.1.1a
R.3.2.2.5 | EX NOTM TX A-10K.030 | Completed |  |  | Material | 100 | 0 | 0 | 3.2.2.5
R.3.2.2.6 | EX NOTM TX A-10K.040 | Completed |  |  | Material | 5600 | 5103 | 0 | 3.2.2.6
R.3.2.3.1 | EXE TXY P A-04.060 | Not Started |  |  | Material | 2400 | 0 | 2400 | 3.2.3.1
R.3.2.2.9 | EXE TXY P A-04.170 | Not Started |  |  | Material | 2618 | 0 | 2618 | 3.2.2.9
R.3.2.2.10 | EXE TXY P A-04.050 | Not Started |  |  | Material | 2800 | 0 | 2800 | 3.2.2.10
R.3.2.1.1 | EXE CGD 1010 | In Progress |  |  | Material | 6900 | 0 | 6900 | 3.2.1.1
R.3.1.1.1a | EXE TXY P A-01.020 | Completed |  |  | Material | 33637 | 33637 | 0 | 3.1.1.1a
R.3.1.1.1a | EXE TXY P A-02.020 | Not Started |  |  | Material | 100 | 0 | 100 | 3.1.1.1a
R.3.2.3.1 | EXE TXY P A-02.060 | Not Started |  |  | Material | 3200 | 0 | 3200 | 3.2.3.1
R.3.2.2.9 | EXE TXY P A-02.170 | Not Started |  |  | Material | 5280 | 0 | 5280 | 3.2.2.9
R.3.2.2.10 | EXE TXY P A-02.050 | Not Started |  |  | Material | 8095 | 0 | 8095 | 3.2.2.10
R.3.2.3.4 | EXE TXY P A-02.070 | Not Started |  |  | Material | 7632 | 0 | 7632 | 3.2.3.4
R.3.2.3.5 | EXE TXY P A-02.130 | Not Started |  |  | Material | 6500 | 0 | 6500 | 3.2.3.5
R.3.2.3.2 | EXE TXY P A-02.080 | Not Started |  |  | Material | 565 | 0 | 565 | 3.2.3.2
R.3.2.3.6 | EXE TXY P A-02.150 | Not Started |  |  | Material | 7000 | 0 | 7000 | 3.2.3.6
R.3.2.3.3 | EXE TXY P A-02.140 | Not Started |  |  | Material | 465 | 0 | 465 | 3.2.3.3
R.3.2.7.4 | EXE TXY P A-02.200 | Not Started |  |  | Material | 5300 | 0 | 5300 | 3.2.7.4
R.3.2.7.5 | EXE TXY P A-02.220 | Not Started |  |  | Material | 5278 | 0 | 5278 | 3.2.7.5
R.3.2.7.2 | EXE TXY P A-02.210 | Not Started |  |  | Material | 445 | 0 | 445 | 3.2.7.2
R.3.2.7.3 | EXE TXY P A-02.230 | Not Started |  |  | Material | 375 | 0 | 375 | 3.2.7.3
R.3.2.7.1 | EXE TXY P A-02.190 | Not Started |  |  | Material | 1585 | 0 | 1585 | 3.2.7.1
R.3.1.1.1a | EXE TXY P A-03.020 | Not Started |  |  | Material | 100 | 0 | 100 | 3.1.1.1a
R.3.2.3.1 | EXE TXY P A-03.060 | Not Started |  |  | Material | 4946 | 0 | 4946 | 3.2.3.1
R.3.2.2.9 | EXE TXY P A-03.170 | Not Started |  |  | Material | 6550 | 0 | 6550 | 3.2.2.9
R.3.2.2.10 | EXE TXY P A-03.050 | Not Started |  |  | Material | 13633 | 0 | 13633 | 3.2.2.10
R.3.2.3.4 | EXE TXY P A-03.070 | Not Started |  |  | Material | 13000 | 0 | 13000 | 3.2.3.4
R.3.2.3.5 | EXE TXY P A-03.130 | Not Started |  |  | Material | 12000 | 0 | 12000 | 3.2.3.5
R.3.2.3.2 | EXE TXY P A-03.080 | Not Started |  |  | Material | 900 | 0 | 900 | 3.2.3.2
R.3.2.3.6 | EXE TXY P A-03.090 | Not Started |  |  | Material | 12000 | 0 | 12000 | 3.2.3.6
R.3.2.3.3 | EXE TXY P A-03.140 | Not Started |  |  | Material | 590 | 0 | 590 | 3.2.3.3
R.3.2.7.4 | EXE TXY P A-03.200 | Not Started |  |  | Material | 6550 | 0 | 6550 | 3.2.7.4
R.3.2.7.5 | EXE TXY P A-03.220 | Not Started |  |  | Material | 6548 | 0 | 6548 | 3.2.7.5
R.3.2.7.2 | EXE TXY P A-03.210 | Not Started |  |  | Material | 545 | 0 | 545 | 3.2.7.2
R.3.2.7.3 | EXE TXY P A-03.230 | Not Started |  |  | Material | 465 | 0 | 465 | 3.2.7.3
R.3.2.7.1 | EXE TXY P A-03.190 | Not Started |  |  | Material | 1970 | 0 | 1970 | 3.2.7.1
R.3.1.1.1a | EXE TXY P A-04.020 | Not Started |  |  | Material | 100 | 0 | 100 | 3.1.1.1a
R.3.2.3.4 | EXE TXY P A-04.070 | Not Started |  |  | Material | 5000 | 0 | 5000 | 3.2.3.4
R.3.2.3.5 | EXE TXY P A-04.130 | Not Started |  |  | Material | 5000 | 0 | 5000 | 3.2.3.5
R.3.2.3.2 | EXE TXY P A-04.080 | Not Started |  |  | Material | 410 | 0 | 410 | 3.2.3.2
R.3.2.3.6 | EXE TXY P A-04.090 | Not Started |  |  | Material | 5500 | 0 | 5500 | 3.2.3.6
R.3.2.3.3 | EXE TXY P A-04.160 | Not Started |  |  | Material | 330 | 0 | 330 | 3.2.3.3
R.3.2.7.4 | EXE TXY P A-04.200 | Not Started |  |  | Material | 3400 | 0 | 3400 | 3.2.7.4
R.3.2.7.5 | EXE TXY P A-04.220 | Not Started |  |  | Material | 3396 | 0 | 3396 | 3.2.7.5
R.3.2.7.2 | EXE TXY P A-04.210 | Not Started |  |  | Material | 300 | 0 | 300 | 3.2.7.2
R.3.2.7.3 | EXE TXY P A-04.230 | Not Started |  |  | Material | 150 | 0 | 150 | 3.2.7.3
R.3.2.6.4 | EX NOTM TX A-09L.070 | Completed |  |  | Material | 3741 | 4322 | 0 | 3.2.6.4
R.3.2.6.5 | EX NOTM TX A-09L.130 | Not Started |  |  | Material | 3653 | 0 | 3653 | 3.2.6.5
R.3.2.6.2 | EX NOTM TX A-09L.080 | Completed |  |  | Material | 280 | 292 | 0 | 3.2.6.2
R.3.2.6.6 | EX NOTM TX A-09L.090 | Completed |  |  | Material | 3650 | 4322 | 0 | 3.2.6.6
R.3.2.6.3 | EX NOTM TX A-09L.140 | Not Started |  |  | Material | 218 | 0 | 218 | 3.2.6.3
R.3.2.6.1 | EX NOTM TX A-09L.060 | Completed |  |  | Material | 1496 | 1299 | 0 | 3.2.6.1
R.3.2.5.4 | EX NOTM TX A-10K.070 | Completed |  |  | Material | 6454 | 6045 | 0 | 3.2.5.4
R.3.2.5.5 | EX NOTM TX A-10K.130 | Not Started |  |  | Material | 6327 | 0 | 6327 | 3.2.5.5
R.3.2.5.2 | EX NOTM TX A-10K.080 | Completed |  |  | Material | 505 | 506 | 0 | 3.2.5.2
R.3.2.5.6 | EX NOTM TX A-10K.090 | Completed |  |  | Material | 6326 | 5820 | 0 | 3.2.5.6
R.3.2.5.3 | EX NOTM TX A-10K.140 | Not Started |  |  | Material | 380 | 0 | 380 | 3.2.5.3
R.3.2.5.1 | EX NOTM TX A-10K.060 | Completed |  |  | Material | 2581 | 1717 | 0 | 3.2.5.1
R.3.2.2.9 | EX NOTM TX A-09L.170 | Completed |  |  | Material | 370 | 1901 | 0 | 3.2.2.9
R.3.2.2.10 | EX NOTM TX A-09L.050 | Completed |  |  | Material | 1800 | 1462 | 0 | 3.2.2.10
R.3.2.2.9 | EX NOTM TX A-10K.170 | Completed |  |  | Material | 1060 | 2258 | 0 | 3.2.2.9
R.3.2.2.10 | EX NOTM TX A-10K.050 | Completed |  |  | Material | 3000 | 2432 | 0 | 3.2.2.10
R.3.1.1.1a | EX SR A-13.020 | In Progress |  |  | Material | 28760 | 28759 | 1 | 3.1.1.1a
R.3.2.8 | EXE TXY P A-01.280 | Not Started |  |  | Material | 450 | 0 | 450 | 3.2.8
R.3.2.8 | EXE TXY P A-02.270 | Not Started |  |  | Material | 350 | 0 | 350 | 3.2.8
R.3.2.8 | EXE TXY P A-03.270 | Not Started |  |  | Material | 500 | 0 | 500 | 3.2.8
R.3.2.8 | EXE TXY P A-04.270 | Not Started |  |  | Material | 450 | 0 | 450 | 3.2.8
R.3.2.8 | EX NOTM TX A-09L.290 | Not Started |  |  | Material | 50 | 0 | 50 | 3.2.8
R.3.2.8 | EX NOTM TX A-10K.290 | Not Started |  |  | Material | 100 | 0 | 100 | 3.2.8
R.3.2.7.4 | EX NOTM TX A-09L.200 | Not Started |  |  | Material | 1550 | 0 | 1550 | 3.2.7.4
R.3.2.7.5 | EX NOTM TX A-09L.220 | Not Started |  |  | Material | 1544 | 0 | 1544 | 3.2.7.5
R.3.2.7.2 | EX NOTM TX A-09L.210 | Not Started |  |  | Material | 60 | 0 | 60 | 3.2.7.2
R.3.2.7.3 | EX NOTM TX A-09L.230 | Not Started |  |  | Material | 100 | 0 | 100 | 3.2.7.3
R.3.2.7.1 | EX NOTM TX A-09L.190 | Completed |  |  | Material | 340 | 387 | 0 | 3.2.7.1
R.3.2.7.4 | EX NOTM TX A-10K.200 | Not Started |  |  | Material | 1220 | 0 | 1220 | 3.2.7.4
R.3.2.7.5 | EX NOTM TX A-10K.220 | Not Started |  |  | Material | 1215 | 0 | 1215 | 3.2.7.5
R.3.2.7.2 | EX NOTM TX A-10K.210 | Not Started |  |  | Material | 110 | 0 | 110 | 3.2.7.2
R.3.2.7.3 | EX NOTM TX A-10K.230 | Not Started |  |  | Material | 90 | 0 | 90 | 3.2.7.3
R.3.2.7.1 | EX NOTM TX A-10K.190 | Completed |  |  | Material | 545 | 461 | 0 | 3.2.7.1
R.4.4.1.3 | EXE AGL ALL-15.224 | Not Started |  |  | Material | 28 | 0 | 28 | 4.4.1.3 (c)
R-1.1a | EXE PS1 1010 | Completed |  |  | Material | 1 | 1 | 0 | 1.1a
R-1.2 | EXE PS2 1010 | Not Started |  |  | Material | 1 | 0 | 1 | 1.2
R-1.3 | EXE PS3 1010 | Not Started |  |  | Material | 1 | 0 | 1 | 1.3
R.3.1.1.1a | EX NOTM TX A-11E.030 | In Progress |  |  | Material | 100 | 100 | 0 | 3.1.1.1a
R.3.2.2.5 | EX NOTM TX A-11E.040 | Not Started |  |  | Material | 100 | 0 | 100 | 3.2.2.5
R.3.2.2.6 | EX NOTM TX A-11E.050 | Not Started |  |  | Material | 4900 | 0 | 4900 | 3.2.2.6
R.3.2.4.4 | EX NOTM TX A-11E.080 | Not Started |  |  | Material | 5780 | 0 | 5780 | 3.2.4.4
R.3.2.4.5 | EX NOTM TX A-11E.150 | Not Started |  |  | Material | 5687 | 0 | 5687 | 3.2.4.5
R.3.2.4.2 | EX NOTM TX A-11E.090 | Not Started |  |  | Material | 420 | 0 | 420 | 3.2.4.2
R.3.2.4.6 | EX NOTM TX A-11E.100 | Not Started |  |  | Material | 5690 | 0 | 5690 | 3.2.4.6
R.3.2.4.3 | EX NOTM TX A-11E.160 | Not Started |  |  | Material | 341 | 0 | 341 | 3.2.4.3
R.3.2.4.1 | EX NOTM TX A-11E.070 | Not Started |  |  | Material | 2312 | 0 | 2312 | 3.2.4.1
R.3.2.2.9 | EX NOTM TX A-11E.190 | Not Started |  |  | Material | 630 | 0 | 630 | 3.2.2.9
R.3.2.2.10 | EX NOTM TX A-11E.060 | Not Started |  |  | Material | 1050 | 0 | 1050 | 3.2.2.10
R.3.2.8 | EX NOTM TX A-11E.320 | Not Started |  |  | Material | 100 | 0 | 100 | 3.2.8
R.3.2.7.4 | EX NOTM TX A-11E.220 | Not Started |  |  | Material | 650 | 0 | 650 | 3.2.7.4
R.3.2.7.5 | EX NOTM TX A-11E.240 | Not Started |  |  | Material | 631 | 0 | 631 | 3.2.7.5
R.3.2.7.2 | EX NOTM TX A-11E.230 | Not Started |  |  | Material | 80 | 0 | 80 | 3.2.7.2
R.3.2.7.3 | EX NOTM TX A-11E.250 | Not Started |  |  | Material | 75 | 0 | 75 | 3.2.7.3
R.3.2.7.1 | EX NOTM TX A-11E.210 | Not Started |  |  | Material | 340 | 0 | 340 | 3.2.7.1
R.3.1.1.1a | NOTM TX-New A-12.020 | In Progress |  |  | Material | 100 | 100 | 0 | 3.1.1.1a
R.3.2.2.5 | NOTM TX-New A-12.030 | Not Started |  |  | Material | 50 | 0 | 50 | 3.2.2.5
R.3.2.2.6 | NOTM TX-New A-12.040 | Not Started |  |  | Material | 3843 | 0 | 3843 | 3.2.2.6
R.3.2.2.9 | NOTM TX-New A-12.170 | Not Started |  |  | Material | 1680 | 0 | 1680 | 3.2.2.9
R.3.2.2.10 | NOTM TX-New A-12.050 | Not Started |  |  | Material | 1327 | 0 | 1327 | 3.2.2.10
R.3.2.8 | NOTM TX-New A-12.260 | Not Started |  |  | Material | 100 | 0 | 100 | 3.2.8
R.3.2.3.2 | EXE TXY P A-02.100 | Not Started |  |  | Material | 565 | 0 | 565 | 3.2.3.2
R.3.2.3.2 | EXE TXY P A-02.120 | Not Started |  |  | Material | 485 | 0 | 485 | 3.2.3.2
R.3.2.3.3 | EXE TXY P A-02.160 | Not Started |  |  | Material | 465 | 0 | 465 | 3.2.3.3
R.3.2.3.6 | EXE TXY P A-02.090 | Not Started |  |  | Material | 7000 | 0 | 7000 | 3.2.3.6
R.3.2.3.6 | EXE TXY P A-02.110 | Not Started |  |  | Material | 7000 | 0 | 7000 | 3.2.3.6
R.3.2.3.2 | EXE TXY P A-03.100 | Not Started |  |  | Material | 929 | 0 | 929 | 3.2.3.2
R.3.2.3.2 | EXE TXY P A-03.120 | Not Started |  |  | Material | 865 | 0 | 865 | 3.2.3.2
R.3.2.3.6 | EXE TXY P A-03.110 | Not Started |  |  | Material | 12000 | 0 | 12000 | 3.2.3.6
R.3.2.3.6 | EXE TXY P A-03.150 | Not Started |  |  | Material | 12000 | 0 | 12000 | 3.2.3.6
R.3.2.3.3 | EXE TXY P A-03.160 | Not Started |  |  | Material | 550 | 0 | 550 | 3.2.3.3
R.3.2.2.6 | EXE TXY P A-01.180 | Not Started |  |  | Material | 1000 | 0 | 1000 | 3.2.2.6
R.3.2.2.6 | EXE TXY P A-02.180 | Not Started |  |  | Material | 850 | 0 | 850 | 3.2.2.6
R.3.2.3.2 | EXE TXY P A-04.100 | Not Started |  |  | Material | 410 | 0 | 410 | 3.2.3.2
R.3.2.3.2 | EXE TXY P A-04.120 | Not Started |  |  | Material | 350 | 0 | 350 | 3.2.3.2
R.3.2.3.3 | EXE TXY P A-04.140 | Not Started |  |  | Material | 330 | 0 | 330 | 3.2.3.3
R.3.2.3.6 | EXE TXY P A-04.110 | Not Started |  |  | Material | 5500 | 0 | 5500 | 3.2.3.6
R.3.2.3.6 | EXE TXY P A-04.150 | Not Started |  |  | Material | 5500 | 0 | 5500 | 3.2.3.6
R.3.2.7.1 | EXE TXY P A-04.190 | Not Started |  |  | Material | 1020 | 0 | 1020 | 3.2.7.1
R.3.2.2.6 | EXE TXY P A-03.180 | Not Started |  |  | Material | 1000 | 0 | 1000 | 3.2.2.6
R.3.2.2.6 | EXE TXY P A-04.180 | Not Started |  |  | Material | 500 | 0 | 500 | 3.2.2.6
R.3.2.2.6 | EX NOTM TX A-09L.180 | Completed |  |  | Material | 100 | 270 | 0 | 3.2.2.6
R.3.2.6.2 | EX NOTM TX A-09L.100 | Completed |  |  | Material | 270 | 292 | 0 | 3.2.6.2
R.3.2.6.2 | EX NOTM TX A-09L.120 | Completed |  |  | Material | 253 | 219 | 0 | 3.2.6.2
R.3.2.6.3 | EX NOTM TX A-09L.160 | Not Started |  |  | Material | 220 | 0 | 220 | 3.2.6.3
R.3.2.6.6 | EX NOTM TX A-09L.110 | Completed |  |  | Material | 3650 | 3890 | 0 | 3.2.6.6
R.3.2.6.6 | EX NOTM TX A-09L.150 | Not Started |  |  | Material | 3661 | 0 | 3661 | 3.2.6.6
R.3.2.2.6 | EX NOTM TX A-10K.180 | Completed |  |  | Material | 200 | 285 | 0 | 3.2.2.6
R.3.2.5.3 | EX NOTM TX A-10K.160 | Not Started |  |  | Material | 378 | 0 | 378 | 3.2.5.3
R.3.2.5.2 | EX NOTM TX A-10K.100 | Completed |  |  | Material | 505 | 506 | 0 | 3.2.5.2
R.3.2.5.2 | EX NOTM TX A-10K.120 | Completed |  |  | Material | 380 | 380 | 0 | 3.2.5.2
R.3.2.5.6 | EX NOTM TX A-10K.110 | Completed |  |  | Material | 6326 | 5820 | 0 | 3.2.5.6
R.3.2.5.6 | EX NOTM TX A-10K.150 | Not Started |  |  | Material | 6326 | 0 | 6326 | 3.2.5.6
R.3.2.2.6 | EX NOTM TX A-11E.200 | Not Started |  |  | Material | 100 | 0 | 100 | 3.2.2.6
R.3.2.4.3 | EX NOTM TX A-11E.180 | Not Started |  |  | Material | 341 | 0 | 341 | 3.2.4.3
R.3.2.4.2 | EX NOTM TX A-11E.110 | Not Started |  |  | Material | 415 | 0 | 415 | 3.2.4.2
R.3.2.4.2 | EX NOTM TX A-11E.130 | Not Started |  |  | Material | 416 | 0 | 416 | 3.2.4.2
R.3.2.4.6 | EX NOTM TX A-11E.120 | Not Started |  |  | Material | 5690 | 0 | 5690 | 3.2.4.6
R.3.2.4.6 | EX NOTM TX A-11E.170 | Not Started |  |  | Material | 5686 | 0 | 5686 | 3.2.4.6
R.3.2.2.6 | NOTM TX-New A-12.180 | Not Started |  |  | Material | 150 | 0 | 150 | 3.2.2.6
R.3.2.3.4 | NOTM TX-New A-12.070 | Not Started |  |  | Material | 1508 | 0 | 1508 | 3.2.3.4
R.3.2.3.5 | NOTM TX-New A-12.130 | Not Started |  |  | Material | 1527 | 0 | 1527 | 3.2.3.5
R.3.2.3.2 | NOTM TX-New A-12.080 | Not Started |  |  | Material | 80 | 0 | 80 | 3.2.3.2
R.3.2.3.6 | NOTM TX-New A-12.090 | Not Started |  |  | Material | 1512 | 0 | 1512 | 3.2.3.6
R.3.2.3.3 | NOTM TX-New A-12.160 | Not Started |  |  | Material | 99 | 0 | 99 | 3.2.3.3
R.3.2.3.2 | NOTM TX-New A-12.100 | Not Started |  |  | Material | 80 | 0 | 80 | 3.2.3.2
R.3.2.3.2 | NOTM TX-New A-12.120 | Not Started |  |  | Material | 55 | 0 | 55 | 3.2.3.2
R.3.2.3.3 | NOTM TX-New A-12.140 | Not Started |  |  | Material | 100 | 0 | 100 | 3.2.3.3
R.3.2.3.6 | NOTM TX-New A-12.110 | Not Started |  |  | Material | 1512 | 0 | 1512 | 3.2.3.6
R.3.2.3.6 | NOTM TX-New A-12.150 | Not Started |  |  | Material | 1153 | 0 | 1153 | 3.2.3.6
R.3.2.7.4 | NOTM TX-New A-12.200 | Not Started |  |  | Material | 2417 | 0 | 2417 | 3.2.7.4
R.3.2.7.5 | NOTM TX-New A-12.220 | Not Started |  |  | Material | 672 | 0 | 672 | 3.2.7.5
R.3.2.7.2 | NOTM TX-New A-12.210 | Not Started |  |  | Material | 235 | 0 | 235 | 3.2.7.2
R.3.2.7.3 | NOTM TX-New A-12.230 | Not Started |  |  | Material | 85 | 0 | 85 | 3.2.7.3
R.3.2.7.1 | NOTM TX-New A-12.190 | Not Started |  |  | Material | 576 | 0 | 576 | 3.2.7.1
R.3.2.2.10 | EXE TXY P A-01.050 | Completed |  |  | Material | 14940 | 9249 | 0 | 3.2.2.10
R.3.2.3.4 | EXE TXY P A-01.070 | Completed |  |  | Material | 13000 | 8394 | 0 | 3.2.3.4
R.3.2.3.5 | EXE TXY P A-01.130 | Not Started |  |  | Material | 12000 | 0 | 12000 | 3.2.3.5
R.3.2.3.2 | EXE TXY P A-01.080 | In Progress |  |  | Material | 885 | 597 | 288 | 3.2.3.2
R.3.2.3.6 | EXE TXY P A-01.090 | Not Started |  |  | Material | 12000 | 0 | 12000 | 3.2.3.6
R.3.2.3.3 | EXE TXY P A-01.160 | Not Started |  |  | Material | 750 | 0 | 750 | 3.2.3.3
R.3.2.3.2 | EXE TXY P A-01.100 | Not Started |  |  | Material | 885 | 0 | 885 | 3.2.3.2
R.3.2.3.2 | EXE TXY P A-01.120 | Not Started |  |  | Material | 845 | 0 | 845 | 3.2.3.2
R.3.2.3.3 | EXE TXY P A-01.140 | Not Started |  |  | Material | 750 | 0 | 750 | 3.2.3.3
R.3.2.3.6 | EXE TXY P A-01.110 | Not Started |  |  | Material | 12000 | 0 | 12000 | 3.2.3.6
R.3.2.3.6 | EXE TXY P A-01.150 | Not Started |  |  | Material | 12000 | 0 | 12000 | 3.2.3.6
R.3.2.3.1 | EXE TXY P A-01.060 | Completed |  |  | Material | 4830 | 3638 | 0 | 3.2.3.1
R.3.2.3.1 | NOTM TX-New A-12.060 | Not Started |  |  | Material | 680 | 0 | 680 | 3.2.3.1
R.3.2.3.6a | EX NOTM TX A-11P.020 | Not Started |  |  | Material | 571 | 0 | 571 | 3.2.3.6a
R.3.2.3.6b | EX NOTM TX A-11P.140 | Not Started |  |  | Material | 993 | 0 | 993 | 3.2.3.6b
R-1.1i | EXE TXY P A-01.240 | Not Started |  |  | Material | 0 | 0 | 0 | 1.1i
R.4.14.2 | EXE TXY P A-01.260 | Completed |  |  | Material | 350 | 576 | 0 | 4.14.2
R-1.1i | EXE TXY P A-02.240 | Not Started |  |  | Material | 0 | 0 | 0 | 1.1i
R-1.1i | EXE TXY P A-03.240 | Not Started |  |  | Material | 0 | 0 | 0 | 1.1i
R-1.1i | EXE TXY P A-04.240 | Not Started |  |  | Material | 0 | 0 | 0 | 1.1i
R.3.2.13.2 | EXE RS A-08.140 | Not Started |  |  | Material | 294 | 0 | 294 | 3.2.13.2
R.3.2.13.5 | EXE RS A-08.210 | Completed |  |  | Material | 4 | 4 | 0 | 3.2.13.5
R 3.2.13.5a | EXE RS A-08.220 | Completed |  |  | Material | 1 | 1 | 0 | 3.2.13.5a
R 3.2.13.5b | EXE RS A-08.230 | Completed |  |  | Material | 1 | 1 | 0 | 3.2.13.5b
R 3.2.13.6a | EXE RS A-08.270 | Not Started |  |  | Material | 1 | 0 | 1 | 3.2.13.6a
R.3.2.13.3 | EX NOTM RS C-08.110 | Not Started |  |  | Material | 4 | 0 | 4 | 3.2.13.3
R 3.2.13.5c | EXE RS A-08.240 | Completed |  |  | Material | 1 | 1 | 0 | 3.2.13.5c
R 3.2.13.5d | EXE RS A-08.250 | Completed |  |  | Material | 1 | 1 | 0 | 3.2.13.5d
R-1.1i | EXE RS A-08.070 | Not Started |  |  | Material | 0 | 0 | 0 | 1.1i
R-1.1i | EX NOTM TX A-09L.240 | Not Started |  |  | Material | 0 | 0 | 0 | 1.1i
R-1.1i | EX NOTM TX A-10K.240 | Not Started |  |  | Material | 0 | 0 | 0 | 1.1i
R-1.1i | EX NOTM TX A-11E.260 | Not Started |  |  | Material | 0 | 0 | 0 | 1.1i
R-1.1b | EXE PS1 1020 | Completed |  |  | Material | 1 | 1 | 0 | 1.1b
R-1.1c | EXE PS1 1030 | Completed |  |  | Material | 1 | 1 | 0 | 1.1c
R-1.1d | EXE PS1 1040 | Completed |  |  | Material | 1 | 1 | 0 | 1.1d
R-1.1e | EXE PS1 1050 | Completed |  |  | Material | 1 | 1 | 0 | 1.1e
R-1.1f | EXE PS1 1060 | Completed |  |  | Material | 1 | 1 | 0 | 1.1f
R-1.1g | EXE PS1 1070 | Completed |  |  | Material | 1 | 1 | 0 | 1.1g
R-1.1h | EXE PS1 1080 | Completed |  |  | Material | 1 | 1 | 0 | 1.1h
R-1.1i | EXE PS1 1090 | Not Started |  |  | Material | 1 | 0 | 1 | 1.1i
R-1.1j | EXE PS1 1100 | Completed |  |  | Material | 1 | 1 | 0 | 1.1j
R-1.1k | EXE PS1 1110 | Not Started |  |  | Material | 1 | 0 | 1 | 1.1k
R-1.1l | EXE PS1 1120 | Completed |  |  | Material | 1 | 1 | 0 | 1.1l
R-1.1m | EXE PS1 1130 | Not Started |  |  | Material | 1 | 0 | 1 | 1.1m
R-1.2a | EXE PS2 1020 | In Progress |  |  | Material | 1 | 1 | 0 | 1.2a
R-1.3a | EXE PS3 1020 | Completed |  |  | Material | 1 | 1 | 0 | 1.3a
R-1.3b | EXE PS3 1030 | Completed |  |  | Material | 1 | 1 | 0 | 1.3b
R.3.1.1.1a | EX TS A-14.020 | Not Started |  |  | Material | 100 | 0 | 100 | 3.1.1.1a
R.3.2.2.5 | EX TS A-14.030 | Not Started |  |  | Material | 5129 | 0 | 5129 | 3.2.2.5
R.3.2.2.6 | EX TS A-14.040 | Not Started |  |  | Material | 1750 | 0 | 1750 | 3.2.2.6
R.3.2.9 | EX TS A-14.050 | Not Started |  |  | Material | 22000 | 0 | 22000 | 3.2.9
R.3.2.10 | EX TS A-14.060 | Not Started |  |  | Material | 21000 | 0 | 21000 | 3.2.10
R-1.1i | EX TS A-14.070 | Not Started |  |  | Material | 0 | 0 | 0 | 1.1i
R 3.2.12.6b | EX NOTM RS C-08.070 | Not Started |  |  | Material | 215 | 0 | 215 | 3.2.12.6b
R 3.2.12.6d | EX SR A-13.100 | In Progress |  |  | Material | 245 | 168 | 78 | 3.2.12.6d
R 3.2.13.2e | EXE RE A-05.120 | Not Started |  |  | Material | 500 | 0 | 500 | 3.2.13.2e
R 3.2.13.2f | EXE RE A-05.130 | Not Started |  |  | Material | 360 | 0 | 360 | 3.2.13.2f
R-3.2.13.1h | EXE RE A-05.140 | Completed |  |  | Material | 175 | 175 | 0 | 3.2.13.2h
R 3.2.13.2e | EXE RE A-06.120 | Not Started |  |  | Material | 450 | 0 | 450 | 3.2.13.2e
R 3.2.13.2f | EXE RE A-06.130 | Not Started |  |  | Material | 400 | 0 | 400 | 3.2.13.2f
R 3.2.13.2g | EXE RE A-06.140 | In Progress |  |  | Material | 450 | 420 | 30 | 3.2.13.2g
R 3.2.13.2e | EXE RE A-07.120 | Not Started |  |  | Material | 810 | 0 | 810 | 3.2.13.2e
R 3.2.13.2f | EXE RE A-07.130 | Not Started |  |  | Material | 15 | 0 | 15 | 3.2.13.2f
R 3.2.13.2g | EXE RE A-07.140 | Completed |  |  | Material | 480 | 480 | 0 | 3.2.13.2g
R.3.2.2.11 | EXE RE A-05.090 | Completed |  |  | Material | 630 | 664 | 0 | 3.2.2.11
R.3.2.2.12 | EXE RE A-05.100 | Not Started |  |  | Material | 31 | 0 | 31 | 3.2.2.12
R.3.2.2.13 | EXE RE A-05.110 | Not Started |  |  | Material | 230 | 0 | 230 | 3.2.2.13
R.3.2.2.11 | EXE RE A-06.090 | Completed |  |  | Material | 500 | 168 | 0 | 3.2.2.11
R.3.2.2.12 | EXE RE A-06.100 | Not Started |  |  | Material | 25 | 0 | 25 | 3.2.2.12
R.3.2.2.11 | EXE RE A-07.090 | Completed |  |  | Material | 50 | 19 | 0 | 3.2.2.11
R.3.2.2.12 | EXE RE A-07.100 | Not Started |  |  | Material | 3 | 0 | 3 | 3.2.2.12
R.3.1.1.1 | EX NOTM RS B-08.020 | Completed |  |  | Material | 100 | 0 | 0 | 3.1.1.1
R.3.1.1.2 | EX NOTM RS B-08.030 | Completed |  |  | Material | 12368 | 12217 | 0 | 3.1.1.2
R.3.1.1.3 | EX NOTM RS B-08.040 | Not Started |  |  | Material | 8340 | 0 | 8340 | 3.1.1.3
R.3.2.9 | EX NOTM RS B-08.050 | Completed |  |  | Material | 40000 | 40000 | 0 | 3.2.9
R.3.2.10 | EX NOTM RS B-08.060 | Completed |  |  | Material | 42000 | 42000 | 0 | 3.2.10
R.3.2.2.14 | EXE RE A-05.115 | Not Started |  |  | Material | 9 | 0 | 9 | 3.2.2.14
R.3.2.2.13 | EXE RE A-06.112 | Not Started |  |  | Material | 120 | 0 | 120 | 3.2.2.13
R.3.2.2.14 | EXE RE A-06.114 | Not Started |  |  | Material | 11 | 0 | 11 | 3.2.2.14
R.3.2.2.13 | EXE RE A-07.112 | Not Started |  |  | Material | 65 | 0 | 65 | 3.2.2.13
R.3.2.2.14 | EXE RE A-07.114 | Not Started |  |  | Material | 7 | 0 | 7 | 3.2.2.14
R.4.1.1.2 | EXE AGL ALL-15.11 | Not Started |  |  | Material | 4000 | 0 | 4000 | 4.1.1.2
R.4.1.1.3 | EXE AGL ALL-15.12 | Not Started |  |  | Material | 20606 | 0 | 20606 | 4.1.1.3
R.4.1.2 | EXE AGL ALL-15.13 | Not Started |  |  | Material | 175 | 0 | 175 | 4.1.2
R.4.1.3 | EXE AGL ALL-15.14 | Not Started |  |  | Material | 4 | 0 | 4 | 4.1.3
R.4.2.2 | EXE AGL ALL-15.21 | Not Started |  |  | Material | 175 | 0 | 175 | 4.2.2
R 4.3.5.6a | EXE AGL ALL-15.76 | Not Started |  |  | Material | 2 | 0 | 2 | 4.3.5.6a
R4.3.5.6b | EXE AGL ALL-15.77 | Not Started |  |  | Material | 11 | 0 | 11 | 4.3.5.6b
R 4.3.5.6c | EXE AGL ALL-15.78 | Not Started |  |  | Material | 9 | 0 | 9 | 4.3.5.6c
R 4.3.5.6d | EXE AGL ALL-15.79 | Not Started |  |  | Material | 4 | 0 | 4 | 4.3.5.6d
R 4.3.5.6e | EXE AGL ALL-15.81 | Not Started |  |  | Material | 6 | 0 | 6 | 4.3.5.6e
R.4.4.1.4 | EXE AGL ALL-15.225 | Not Started |  |  | Material | 142 | 0 | 142 | 4.4.1.4 (d)
R.4.6.1.2 | EXE AGL ALL-15.101 | Not Started |  |  | Material | 1 | 0 | 1 | 4.6.1.2
R.4.6.2.2 | EXE AGL ALL-15.111 | Not Started |  |  | Material | 20 | 0 | 20 | 4.6.2.2
R.4.6.3.2 | EXE AGL ALL-15.121 | Not Started |  |  | Material | 1 | 0 | 1 | 4.6.3.2
R.4.6.3.3 | EXE AGL ALL-15.122 | Not Started |  |  | Material | 1 | 0 | 1 | 4.6.3.3
R-1.1 | EXE PS1 1000 | In Progress |  |  | Material | 1 | 0 | 1 | 1.1
R.3.2.2.8 | EXE RE A-05.071 | Completed |  |  | Material | 100 | 31 | 0 | 3.2.2.8
R.3.2.2.8 | EXE RE A-06.071 | Not Started |  |  | Material | 200 | 0 | 200 | 3.2.2.8
R.3.2.2.8 | EXE RE A-07.071 | In Progress |  |  | Material | 210 | 210 | 0 | 3.2.2.8
R.3.2.12.6 | EXE RS A-08.055 | In Progress |  |  | Material | 50 | 48 | 3 | 3.2.12.6
R.3.2.12.7 | EXE RS A-08.058 | In Progress |  |  | Material | 750 | 740 | 10 | 3.2.12.7
R.3.2.12.6 | EXE RS A-08.057 | In Progress |  |  | Material | 100 | 90 | 10 | 3.2.12.6
R.3.2.12.7 | EXE RS A-08.59 | In Progress |  |  | Material | 240 | 235 | 5 | 3.2.12.7
R.3.1.1.1 | EX NOTM RS C-08.020 | Not Started |  |  | Material | 100 | 0 | 100 | 3.1.1.1
R.3.1.1.2 | EX NOTM RS C-08.030 | Not Started |  |  | Material | 1259 | 0 | 1259 | 3.2.2.5
R.3.1.1.3 | EX NOTM RS C-08.040 | Not Started |  |  | Material | 50 | 0 | 50 | 3.2.2.6
R.3.2.9 | EX NOTM RS C-08.050 | In Progress |  |  | Material | 32000 | 20343 | 11657 | 3.2.9
R.3.2.10 | EX NOTM RS C-08.060 | Not Started |  |  | Material | 5000 | 0 | 5000 | 3.2.10
R.3.2.13.4 | EX NOTM RS C-08.120 | Completed |  |  | Material | 2 | 2 | 0 | 3.2.13.4
R.4.14.3 | EXE TXY P A-01.270 | Not Started |  |  | Material | 250 | 0 | 250 | 4.14.3
R.4.3.1 | EXE TXY P A-01.250 | Not Started |  |  | Material | 0 | 0 | 0 | 4.3.1
R.4.14.3 | EXE TXY P A-02.260 | Not Started |  |  | Material | 250 | 0 | 250 | 4.14.3
R.4.3.1 | EXE TXY P A-02.250 | Not Started |  |  | Material | 0 | 0 | 0 | 4.3.1
R.4.14.3 | EXE TXY P A-03.260 | Not Started |  |  | Material | 250 | 0 | 250 | 4.14.3
R.4.3.1 | EXE TXY P A-03.250 | Not Started |  |  | Material | 0 | 0 | 0 | 4.3.1
R.4.14.3 | EXE TXY P A-04.260 | Not Started |  |  | Material | 135 | 0 | 135 | 4.14.3
R.4.3.1 | EXE TXY P A-04.250 | Not Started |  |  | Material | 0 | 0 | 0 | 4.3.1
R.4.14.2 | EX NOTM TX A-09L.270 | In Progress |  |  | Material | 350 | 437 | 0 | 4.14.2
R.4.14.3 | EX NOTM TX A-09L.280 | In Progress |  |  | Material | 95 | 30 | 65 | 4.14.3
R.4.3.1 | EX NOTM TX A-09L.260 | Not Started |  |  | Material | 0 | 0 | 0 | 4.3.1
R.4.14.2 | EX NOTM TX A-10K.270 | In Progress |  |  | Material | 350 | 412 | 0 | 4.14.2
R.4.14.3 | EX NOTM TX A-10K.280 | In Progress |  |  | Material | 45 | 20 | 25 | 4.14.3
R.4.3.1 | EX NOTM TX A-10K.260 | Not Started |  |  | Material | 0 | 0 | 0 | 4.3.1
R.4.14.2 | EX NOTM TX A-11E.300 | Not Started |  |  | Material | 350 | 0 | 350 | 4.14.2
R.4.14.3 | EX NOTM TX A-11E.310 | Not Started |  |  | Material | 95 | 0 | 95 | 4.14.3
R.4.3.1 | EX NOTM TX A-11E.290 | Not Started |  |  | Material | 0 | 0 | 0 | 4.3.1
R.4.14.3 | NOTM TX-New A-12.250 | Not Started |  |  | Material | 80 | 0 | 80 | 4.14.3
R.4.3.1 | NOTM TX-New A-12.240 | Not Started |  |  | Material | 0 | 0 | 0 | 4.3.1
R.3.1.1.1a | EXE RE A-05.015 | Completed |  |  | Material | 30000 | 29985 | 0 | 3.1.1.1a
R.3.1.1.1a | EXE RE A-06.015 | Completed |  |  | Material | 19678 | 17196 | 0 | 3.1.1.1a
R.3.1.1.1a | EXE RE A-07.015 | Completed |  |  | Material | 5325 | 5326 | 0 | 3.1.1.1a
R-1.1d.1 | EXE PS1 1041 | Completed |  |  | Material | 1 | 1 | 0 | 1.1d.1
R.4.14.1 | EXE AGL ALL-15.010 | In Progress |  |  | Material | 10256 | 6 | 10250 | 4.14.1
R.4.5.1.1 | EXE AGL ALL-15.030 | Not Started |  |  | Material | 12517 | 0 | 12517 | 4.5.1.1
R.4.5.1.2 | EXE AGL ALL-15.040 | Not Started |  |  | Material | 32 | 0 | 32 | 4.5.1.2
R.4.13.1 | EXE AGL ALL-15.050 | Not Started |  |  | Material | 200 | 0 | 200 | 4.13.1
R.4.13.2 | EXE AGL ALL-15.060 | Not Started |  |  | Material | 40 | 0 | 40 | 4.13.2
R-4.15.2a | EXE AGL ALL-15.070 | In Progress |  |  | Material | 134 | 38 | 96 | 4.15.2a
R 4.15.3a | EXE AGL ALL-15.080 | Not Started |  |  | Material | 7 | 0 | 7 | 4.15.3a
R.3.2.13.1 | EX SR A-13.120 | In Progress |  |  | Material | 1428 | 761 | 667 | 3.2.13.1
R.4.14.2 | OCB-0111 | In Progress |  |  | Material | 360 | 180 | 180 | 4.14.2
R 3.2.13.5e | EX NOTM D-08.080 | Completed |  |  | Material | 1 | 1 | 0 | 3.2.13.5e
R.3.2.12.7 | EX NOTM D-08.060 | Completed |  |  | Material | 335 | 335 | 0 | 3.2.12.7
R.3.2.12.7 | EX NOTM D-08.070 | Completed |  |  | Material | 265 | 255 | 0 | 3.2.12.7
R.3.2.2.9 | EXE RE A-06.061 | In Progress |  |  | Material | 31284 | 17662 | 23622 | 3.2.2.9
R-8 4.3.5.6f | EXE AGL ALL-15.82 | Not Started |  |  | Material | 2 | 0 | 2 | 4.3.5.6f
R.4.4.1.2 | EXE AGL ALL-15.223 | Not Started |  |  | Material | 0 | 0 | 0 | 4.4.1.2 (b)
R.4.4.1.1 | EXE AGL ALL-15.222 | Not Started |  |  | Material | 0 | 0 | 0 | 4.4.1.1 (a)
R-8 4.14.3a | NOTM TX-New A-12.261 | Not Started |  |  | Material | 55 | 0 | 55 | 4.14.3a
R.3.2.11.2 | EX SR A-13.141 | Not Started |  |  | Material | 2 | 0 | 2 | 3.2.11.2
R.3.2.2.15a | EXE RE A-05.116 | Not Started |  |  | Material | 400 | 0 | 400 | 3.2.2.15a
R.3.2.2.15c | EXE RE A-05.118 | Not Started |  |  | Material | 8000 | 0 | 8000 | 3.2.2.15c
R.3.2.2.15a | EXE RE A-06.115 | Not Started |  |  | Material | 450 | 0 | 450 | 3.2.2.15a
R.3.2.2.15b | EXE RE A-06.116 | Not Started |  |  | Material | 300 | 0 | 300 | 3.2.2.15b
R.3.2.2.15c | EXE RE A-06.117 | Not Started |  |  | Material | 12000 | 0 | 12000 | 3.2.2.15c
R.3.2.2.15a | EXE RE A-07.115 | Not Started |  |  | Material | 410 | 0 | 410 | 3.2.2.15a
R.3.2.2.15c | EXE RE A-07.117 | Not Started |  |  | Material | 5572 | 0 | 5572 | 3.2.2.15c
R 3.2.13.5f | EX NOTM D-08.081 | Completed |  |  | Material | 1 | 1 | 0 | 3.2.13.5f
i | EXE RS A-08.251 | In Progress |  |  | Material | 24 | 10 | 14 | 3.2.13.5f (i)
ii | EXE RS A-08.252 | In Progress |  |  | Material | 253 | 100 | 153 | 3.2.13.5f (ii)
iii | EXE RS A-08.253 | Not Started |  |  | Material | 21 | 0 | 21 | 3.2.13.5f (iii)
iv | EXE RS A-08.254 | Not Started |  |  | Material | 9 | 0 | 9 | 3.2.13.5f (iv)
v | EXE RS A-08.255 | Not Started |  |  | Material | 2 | 0 | 2 | 3.2.13.5f (v)
3.2.13.5g | EXE TXY P A-01.241 | Not Started |  |  | Material | 135 | 0 | 135 | 3.2.13.5g
3.2.13.5h | EXE RE A-07.118 | Not Started |  |  | Material | 420 | 0 | 420 | 3.2.13.5h
3.2.13.5i | EXE RE A-07.119 | Not Started |  |  | Material | 384 | 0 | 384 | 3.2.13.5i
R-3.2.13.6b | EXE RS A-08.271 | Not Started |  |  | Material | 1 | 0 | 1 | 3.2.13.6b
R.3.2.12.6c | EX NOTM RS C-08.071 | Not Started |  |  | Material | 28 | 0 | 28 | 3.2.12.6c
R.3.2.12.6a | EXE RS A-08.107 | Completed |  |  | Material | 446 | 281 | 0 | 3.2.12.6a
R.3.2.12.7a | EXE RS A-08.108 | Completed |  |  | Material | 428 | 428 | 0 | 3.2.12.7a
R.3.2.12.7b | EXE RS A-08.109 | Completed |  |  | Material | 300 | 250 | 0 | 3.2.12.7b
R.3.2.12.7c | EXE RS A-08.110 | Completed |  |  | Material | 700 | 550 | 0 | 3.2.12.7c
R.3.2.12.7d | EXE RS A-08.111 | Completed |  |  | Material | 140 | 100 | 0 | 3.2.12.7d
R.3.2.12.7e | EXE RS A-08.112 | Completed |  |  | Material | 235 | 100 | 0 | 3.2.12.7e
R 3.2.13.2a | EXE RS A-08.141 | Not Started |  |  | Material | 45 | 0 | 45 | 3.2.13.2a
R 3.2.13.2b | EXE RS A-08.142 | Not Started |  |  | Material | 145 | 0 | 145 | 3.2.13.2b
R 3.2.13.2c | EXE RS A-08.143 | Not Started |  |  | Material | 80 | 0 | 80 | 3.2.13.2c
R.3.2.5.6a | EX NOTM TX A-10K.021 | Completed |  |  | Material | 245 | 245 | 0 | 3.2.5.6a
R.3.2.6.6a | EX NOTM TX A-09L.021 | Completed |  |  | Material | 1448 | 1448 | 0 | 3.2.6.6a
R.3.2.6.6b | EX NOTM TX A-09L.022 | Completed |  |  | Material | 4327 | 4327 | 0 | 3.2.6.6b
R.3.2.6.6c | EX NOTM TX A-09L.023 | Completed |  |  | Material | 4500 | 4500 | 0 | 3.2.6.6c
R-4.15.1a | EXE AGL ALL-15.071 | In Progress |  |  | Material | 18 | 5 | 14 | 4.15.1a
R.3.2.2.9 | EXE RE A-05.062 | Completed |  |  | Material | 10000 | 8986 | 0 | 3.2.2.9
OCB EQP -1 | EXE RE A-05.020 |  |  |  | Nonlabor | 305.4 | 305.4 | 0 | 3.2.2.1
OCB EQP -9 | EXE RE A-05.020 |  |  |  | Nonlabor | 537.504 | 537.504 | 0 | 3.2.2.1
OCB EQP -1 | EXE RE A-05.030 |  |  |  | Nonlabor | 276.66 | 257.98 | 0 | 3.2.2.2
OCB EQP -2 | EXE RE A-05.030 |  |  |  | Nonlabor | 138.33 | 128.99 | 0 | 3.2.2.2
OCB EQP -3 | EXE RE A-05.030 |  |  |  | Nonlabor | 138.33 | 128.99 | 0 | 3.2.2.2
OCB EQP -4 | EXE RE A-05.030 |  |  |  | Nonlabor | 276.66 | 257.98 | 0 | 3.2.2.2
OCB EQP -9 | EXE RE A-05.030 |  |  |  | Nonlabor | 1152.75 | 1074.9167 | 0 | 3.2.2.2
OCB EQP -12 | EXE RE A-05.030 |  |  |  | Nonlabor | 276.66 | 257.98 | 0 | 3.2.2.2
OCB EQP -9 | EXE RE A-05.040 |  |  |  | Nonlabor | 263.84 | 263.84 | 0 | 3.2.2.3
OCB EQP -9 | EXE RE A-05.050 |  |  |  | Nonlabor | 4854.92 | 5301.36 | 0 | 3.2.2.4
OCB EQP -3 | EXE RE A-05.050 |  |  |  | Nonlabor | 2670.206 | 2915.748 | 0 | 3.2.2.4
OCB EQP -4 | EXE RE A-05.050 |  |  |  | Nonlabor | 2670.206 | 2915.748 | 0 | 3.2.2.4
OCB EQP -12 | EXE RE A-05.050 |  |  |  | Nonlabor | 4612.174 | 5036.292 | 0 | 3.2.2.4
OCB EQP -8 | EXE RE A-05.050 |  |  |  | Nonlabor | 1335.103 | 1457.874 | 0 | 3.2.2.4
OCB EQP -1 | EXE RS A-08.020 |  |  |  | Nonlabor | 1166.05 | 173.175 | 997.875 | 3.1.1.1
OCB EQP -9 | EXE RS A-08.020 |  |  |  | Nonlabor | 2052.248 | 304.788 | 1756.26 | 3.1.1.1
OCB EQP -1 | EX NOTM RS A-08.032 |  |  |  | Nonlabor | 1970 | 354.02 | 1615.98 | 3.2.2.5
OCB EQP -2 | EX NOTM RS A-08.032 |  |  |  | Nonlabor | 985 | 177.01 | 807.99 | 3.2.2.5
OCB EQP -3 | EX NOTM RS A-08.032 |  |  |  | Nonlabor | 985 | 177.01 | 807.99 | 3.2.2.5
OCB EQP -4 | EX NOTM RS A-08.032 |  |  |  | Nonlabor | 1970 | 354.02 | 1615.98 | 3.2.2.5
OCB EQP -9 | EX NOTM RS A-08.032 |  |  |  | Nonlabor | 8208.3333 | 1475.0833 | 6733.25 | 3.2.2.5
OCB EQP -12 | EX NOTM RS A-08.032 |  |  |  | Nonlabor | 1970 | 354.02 | 1615.98 | 3.2.2.5
OCB EQP -1 | EX NOTM RS A-08.042 |  |  |  | Nonlabor | 1 | 0 | 1 | 3.2.2.6
OCB EQP -2 | EX NOTM RS A-08.042 |  |  |  | Nonlabor | 0.5 | 0 | 0.5 | 3.2.2.6
OCB EQP -3 | EX NOTM RS A-08.042 |  |  |  | Nonlabor | 0.5 | 0 | 0.5 | 3.2.2.6
OCB EQP -4 | EX NOTM RS A-08.042 |  |  |  | Nonlabor | 1 | 0 | 1 | 3.2.2.6
OCB EQP -9 | EX NOTM RS A-08.042 |  |  |  | Nonlabor | 4.1667 | 0 | 4.1667 | 3.2.2.6
OCB EQP -12 | EX NOTM RS A-08.042 |  |  |  | Nonlabor | 1 | 0 | 1 | 3.2.2.6
OCB EQP -3 | EX SR A-13.050 |  |  |  | Nonlabor | 34.76 | 16.8 | 17.96 | 3.1.2.1
OCB EQP -4 | EX SR A-13.050 |  |  |  | Nonlabor | 69.52 | 33.6 | 35.92 | 3.1.2.1
OCB EQP -8 | EX SR A-13.050 |  |  |  | Nonlabor | 69.52 | 33.6 | 35.92 | 3.1.2.1
OCB EQP -9 | EX SR A-13.050 |  |  |  | Nonlabor | 144.8333 | 70 | 74.8333 | 3.1.2.1
OCB EQP -12 | EX SR A-13.050 |  |  |  | Nonlabor | 57.354 | 27.72 | 29.634 | 3.1.2.1
OCB EQP -16 | EX SR A-13.060 |  |  |  | Nonlabor | 17.28 | 8.088 | 9.192 | 3.1.2.4
OCB EQP -17 | EX SR A-13.060 |  |  |  | Nonlabor | 17.28 | 8.088 | 9.192 | 3.1.2.4
OCB EQP -19 | EX SR A-13.060 |  |  |  | Nonlabor | 17.28 | 8.088 | 9.192 | 3.1.2.4
OCB EQP -15 | EX SR A-13.060 |  |  |  | Nonlabor | 17.28 | 8.088 | 9.192 | 3.1.2.4
OCB EQP -15 | EX SR A-13.070 |  |  |  | Nonlabor | 30.2199 | 14.3246 | 15.8953 | 3.1.2.2
OCB EQP -5 | EX SR A-13.070 |  |  |  | Nonlabor | 30.2199 | 14.3246 | 15.8953 | 3.1.2.2
OCB EQP -6 | EX SR A-13.070 |  |  |  | Nonlabor | 60.4398 | 28.6492 | 31.7906 | 3.1.2.2
OCB EQP -9 | EX SR A-13.070 |  |  |  | Nonlabor | 40.0833 | 19 | 21.0833 | 3.1.2.2
OCB EQP -17 | EX SR A-13.080 |  |  |  | Nonlabor | 9.2016 | 2.8632 | 6.3384 | 3.1.2.5
OCB EQP -19 | EX SR A-13.080 |  |  |  | Nonlabor | 9.2016 | 2.8632 | 6.3384 | 3.1.2.5
OCB EQP -15 | EX SR A-13.080 |  |  |  | Nonlabor | 9.2016 | 2.8632 | 6.3384 | 3.1.2.5
OCB EQP -15 | EX SR A-13.090 |  |  |  | Nonlabor | 30.2199 | 9.0471 | 21.1728 | 3.1.2.3
OCB EQP -5 | EX SR A-13.090 |  |  |  | Nonlabor | 30.2199 | 9.0471 | 21.1728 | 3.1.2.3
OCB EQP -6 | EX SR A-13.090 |  |  |  | Nonlabor | 60.4398 | 18.0942 | 42.3455 | 3.1.2.3
OCB EQP -9 | EX SR A-13.090 |  |  |  | Nonlabor | 40.0833 | 12 | 28.0833 | 3.1.2.3
OCB EQP -1 | EXE TXY P A-02.030 |  |  |  | Nonlabor | 1931 | 1546.12 | 384.88 | 3.2.2.5
OCB EQP -2 | EXE TXY P A-02.030 |  |  |  | Nonlabor | 965.5 | 773.06 | 192.44 | 3.2.2.5
OCB EQP -3 | EXE TXY P A-02.030 |  |  |  | Nonlabor | 965.5 | 773.06 | 192.44 | 3.2.2.5
OCB EQP -4 | EXE TXY P A-02.030 |  |  |  | Nonlabor | 1931 | 1546.12 | 384.88 | 3.2.2.5
OCB EQP -9 | EXE TXY P A-02.030 |  |  |  | Nonlabor | 8045.8333 | 6442.1667 | 1603.6667 | 3.2.2.5
OCB EQP -12 | EXE TXY P A-02.030 |  |  |  | Nonlabor | 1931 | 1546.12 | 384.88 | 3.2.2.5
OCB EQP -1 | EXE TXY P A-02.040 |  |  |  | Nonlabor | 340 | 0 | 340 | 3.2.2.6
OCB EQP -2 | EXE TXY P A-02.040 |  |  |  | Nonlabor | 170 | 0 | 170 | 3.2.2.6
OCB EQP -3 | EXE TXY P A-02.040 |  |  |  | Nonlabor | 170 | 0 | 170 | 3.2.2.6
OCB EQP -4 | EXE TXY P A-02.040 |  |  |  | Nonlabor | 340 | 0 | 340 | 3.2.2.6
OCB EQP -9 | EXE TXY P A-02.040 |  |  |  | Nonlabor | 1416.6667 | 0 | 1416.6667 | 3.2.2.6
OCB EQP -12 | EXE TXY P A-02.040 |  |  |  | Nonlabor | 340 | 0 | 340 | 3.2.2.6
OCB EQP -2 | EXE CGD 1050 |  |  |  | Nonlabor | 317.1228 | 117.2328 | 199.8924 | 3.2.1.5
OCB EQP -11 | EXE CGD 1050 |  |  |  | Nonlabor | 317.1228 | 117.2328 | 199.8924 | 3.2.1.5
OCB EQP -1 | EXE TXY P A-01.030 |  |  |  | Nonlabor | 17.82 | 17.82 | 0 | 3.2.2.5
OCB EQP -2 | EXE TXY P A-01.030 |  |  |  | Nonlabor | 8.91 | 8.91 | 0 | 3.2.2.5
OCB EQP -3 | EXE TXY P A-01.030 |  |  |  | Nonlabor | 8.91 | 8.91 | 0 | 3.2.2.5
OCB EQP -4 | EXE TXY P A-01.030 |  |  |  | Nonlabor | 17.82 | 17.82 | 0 | 3.2.2.5
OCB EQP -9 | EXE TXY P A-01.030 |  |  |  | Nonlabor | 74.25 | 74.25 | 0 | 3.2.2.5
OCB EQP -12 | EXE TXY P A-01.030 |  |  |  | Nonlabor | 17.82 | 17.82 | 0 | 3.2.2.5
OCB EQP -1 | EXE TXY P A-01.040 |  |  |  | Nonlabor | 496.34 | 436.34 | 0 | 3.2.2.6
OCB EQP -2 | EXE TXY P A-01.040 |  |  |  | Nonlabor | 248.17 | 218.17 | 0 | 3.2.2.6
OCB EQP -3 | EXE TXY P A-01.040 |  |  |  | Nonlabor | 248.17 | 218.17 | 0 | 3.2.2.6
OCB EQP -4 | EXE TXY P A-01.040 |  |  |  | Nonlabor | 496.34 | 436.34 | 0 | 3.2.2.6
OCB EQP -9 | EXE TXY P A-01.040 |  |  |  | Nonlabor | 2068.0833 | 1818.0833 | 0 | 3.2.2.6
OCB EQP -12 | EXE TXY P A-01.040 |  |  |  | Nonlabor | 496.34 | 436.34 | 0 | 3.2.2.6
OCB EQP -10 | EXE CGD 1020 |  |  |  | Nonlabor | 138.75 | 22.48 | 116.28 | 3.2.1.2
OCB EQP -1 | EXE RE A-06.020 |  |  |  | Nonlabor | 511.25 | 488.825 | 0 | 3.2.2.1
OCB EQP -9 | EXE RE A-06.020 |  |  |  | Nonlabor | 899.8 | 860.332 | 0 | 3.2.2.1
OCB EQP -1 | EXE RE A-06.030 |  |  |  | Nonlabor | 376.42 | 337.34 | 0 | 3.2.2.2
OCB EQP -2 | EXE RE A-06.030 |  |  |  | Nonlabor | 188.21 | 168.67 | 0 | 3.2.2.2
OCB EQP -3 | EXE RE A-06.030 |  |  |  | Nonlabor | 188.21 | 168.67 | 0 | 3.2.2.2
OCB EQP -4 | EXE RE A-06.030 |  |  |  | Nonlabor | 376.42 | 337.34 | 0 | 3.2.2.2
OCB EQP -9 | EXE RE A-06.030 |  |  |  | Nonlabor | 1568.4167 | 1405.5833 | 0 | 3.2.2.2
OCB EQP -12 | EXE RE A-06.030 |  |  |  | Nonlabor | 376.42 | 337.34 | 0 | 3.2.2.2
OCB EQP -9 | EXE RE A-06.040 |  |  |  | Nonlabor | 363.68 | 363.68 | 0 | 3.2.2.3
OCB EQP -9 | EXE RE A-06.050 |  |  |  | Nonlabor | 8826 | 8281.76 | 544.24 | 3.2.2.4
OCB EQP -3 | EXE RE A-06.050 |  |  |  | Nonlabor | 4854.3 | 4554.968 | 299.332 | 3.2.2.4
OCB EQP -4 | EXE RE A-06.050 |  |  |  | Nonlabor | 4854.3 | 4554.968 | 299.332 | 3.2.2.4
OCB EQP -12 | EXE RE A-06.050 |  |  |  | Nonlabor | 8384.7 | 7867.672 | 517.028 | 3.2.2.4
OCB EQP -8 | EXE RE A-06.050 |  |  |  | Nonlabor | 2427.15 | 2277.484 | 149.666 | 3.2.2.4
OCB EQP -9 | EXE RE A-07.040 |  |  |  | Nonlabor | 104 | 104 | 0 | 3.2.2.3
OCB EQP -9 | EXE RE A-07.050 |  |  |  | Nonlabor | 1375 | 1218.76 | 156.24 | 3.2.2.4
OCB EQP -3 | EXE RE A-07.050 |  |  |  | Nonlabor | 756.25 | 670.318 | 85.932 | 3.2.2.4
OCB EQP -4 | EXE RE A-07.050 |  |  |  | Nonlabor | 756.25 | 670.318 | 85.932 | 3.2.2.4
OCB EQP -12 | EXE RE A-07.050 |  |  |  | Nonlabor | 1306.25 | 1157.822 | 148.428 | 3.2.2.4
OCB EQP -8 | EXE RE A-07.050 |  |  |  | Nonlabor | 378.125 | 335.159 | 42.966 | 3.2.2.4
OCB EQP -1 | EXE RE A-07.020 |  |  |  | Nonlabor | 138.35 | 138.35 | 0 | 3.2.2.1
OCB EQP -9 | EXE RE A-07.020 |  |  |  | Nonlabor | 243.496 | 243.496 | 0 | 3.2.2.1
OCB EQP -1 | EXE RE A-07.030 |  |  |  | Nonlabor | 110.92 | 110.92 | 0 | 3.2.2.2
OCB EQP -2 | EXE RE A-07.030 |  |  |  | Nonlabor | 55.46 | 55.46 | 0 | 3.2.2.2
OCB EQP -3 | EXE RE A-07.030 |  |  |  | Nonlabor | 55.46 | 55.46 | 0 | 3.2.2.2
OCB EQP -4 | EXE RE A-07.030 |  |  |  | Nonlabor | 110.92 | 110.92 | 0 | 3.2.2.2
OCB EQP -9 | EXE RE A-07.030 |  |  |  | Nonlabor | 462.1667 | 462.1667 | 0 | 3.2.2.2
OCB EQP -12 | EXE RE A-07.030 |  |  |  | Nonlabor | 110.92 | 110.92 | 0 | 3.2.2.2
OCB EQP -1 | EXE TXY P A-03.040 |  |  |  | Nonlabor | 603.66 | 57.58 | 546.08 | 3.2.2.6
OCB EQP -2 | EXE TXY P A-03.040 |  |  |  | Nonlabor | 301.83 | 28.79 | 273.04 | 3.2.2.6
OCB EQP -3 | EXE TXY P A-03.040 |  |  |  | Nonlabor | 301.83 | 28.79 | 273.04 | 3.2.2.6
OCB EQP -4 | EXE TXY P A-03.040 |  |  |  | Nonlabor | 603.66 | 57.58 | 546.08 | 3.2.2.6
OCB EQP -9 | EXE TXY P A-03.040 |  |  |  | Nonlabor | 2515.25 | 239.9167 | 2275.3333 | 3.2.2.6
OCB EQP -12 | EXE TXY P A-03.040 |  |  |  | Nonlabor | 603.66 | 57.58 | 546.08 | 3.2.2.6
OCB EQP -1 | EXE TXY P A-03.030 |  |  |  | Nonlabor | 3220.12 | 3039.7 | 180.42 | 3.2.2.5
OCB EQP -2 | EXE TXY P A-03.030 |  |  |  | Nonlabor | 1610.06 | 1519.85 | 90.21 | 3.2.2.5
OCB EQP -3 | EXE TXY P A-03.030 |  |  |  | Nonlabor | 1610.06 | 1519.85 | 90.21 | 3.2.2.5
OCB EQP -4 | EXE TXY P A-03.030 |  |  |  | Nonlabor | 3220.12 | 3039.7 | 180.42 | 3.2.2.5
OCB EQP -9 | EXE TXY P A-03.030 |  |  |  | Nonlabor | 13417.1667 | 12665.4167 | 751.75 | 3.2.2.5
OCB EQP -12 | EXE TXY P A-03.030 |  |  |  | Nonlabor | 3220.12 | 3039.7 | 180.42 | 3.2.2.5
OCB EQP -1 | EX SR A-13.040 |  |  |  | Nonlabor | 500 | 269.64 | 230.36 | 3.2.2.6
OCB EQP -2 | EX SR A-13.040 |  |  |  | Nonlabor | 250 | 134.82 | 115.18 | 3.2.2.6
OCB EQP -3 | EX SR A-13.040 |  |  |  | Nonlabor | 250 | 134.82 | 115.18 | 3.2.2.6
OCB EQP -4 | EX SR A-13.040 |  |  |  | Nonlabor | 500 | 269.64 | 230.36 | 3.2.2.6
OCB EQP -9 | EX SR A-13.040 |  |  |  | Nonlabor | 2083.3333 | 1123.5 | 959.8333 | 3.2.2.6
OCB EQP -12 | EX SR A-13.040 |  |  |  | Nonlabor | 500 | 269.64 | 230.36 | 3.2.2.6
OCB EQP -1 | EX SR A-13.030 |  |  |  | Nonlabor | 410 | 398.46 | 11.54 | 3.2.2.5
OCB EQP -2 | EX SR A-13.030 |  |  |  | Nonlabor | 205 | 199.23 | 5.77 | 3.2.2.5
OCB EQP -3 | EX SR A-13.030 |  |  |  | Nonlabor | 205 | 199.23 | 5.77 | 3.2.2.5
OCB EQP -4 | EX SR A-13.030 |  |  |  | Nonlabor | 410 | 398.46 | 11.54 | 3.2.2.5
OCB EQP -9 | EX SR A-13.030 |  |  |  | Nonlabor | 1708.3333 | 1660.25 | 48.0833 | 3.2.2.5
OCB EQP -12 | EX SR A-13.030 |  |  |  | Nonlabor | 410 | 398.46 | 11.54 | 3.2.2.5
OCB EQP -1 | EXE TXY P A-04.040 |  |  |  | Nonlabor | 260 | 0 | 260 | 3.2.2.6
OCB EQP -2 | EXE TXY P A-04.040 |  |  |  | Nonlabor | 130 | 0 | 130 | 3.2.2.6
OCB EQP -3 | EXE TXY P A-04.040 |  |  |  | Nonlabor | 130 | 0 | 130 | 3.2.2.6
OCB EQP -4 | EXE TXY P A-04.040 |  |  |  | Nonlabor | 260 | 0 | 260 | 3.2.2.6
OCB EQP -9 | EXE TXY P A-04.040 |  |  |  | Nonlabor | 1083.3333 | 0 | 1083.3333 | 3.2.2.6
OCB EQP -12 | EXE TXY P A-04.040 |  |  |  | Nonlabor | 260 | 0 | 260 | 3.2.2.6
OCB EQP -1 | EXE TXY P A-04.030 |  |  |  | Nonlabor | 2076.88 | 1419.26 | 657.62 | 3.2.2.5
OCB EQP -2 | EXE TXY P A-04.030 |  |  |  | Nonlabor | 1038.44 | 709.63 | 328.81 | 3.2.2.5
OCB EQP -3 | EXE TXY P A-04.030 |  |  |  | Nonlabor | 1038.44 | 709.63 | 328.81 | 3.2.2.5
OCB EQP -4 | EXE TXY P A-04.030 |  |  |  | Nonlabor | 2076.88 | 1419.26 | 657.62 | 3.2.2.5
OCB EQP -9 | EXE TXY P A-04.030 |  |  |  | Nonlabor | 8653.6667 | 5913.5833 | 2740.0833 | 3.2.2.5
OCB EQP -12 | EXE TXY P A-04.030 |  |  |  | Nonlabor | 2076.88 | 1419.26 | 657.62 | 3.2.2.5
OCB EQP -1 | EX NOTM TX A-09L.020 |  |  |  | Nonlabor | 78.75 | 77.875 | 0 | 3.1.1.1a
OCB EQP -9 | EX NOTM TX A-09L.020 |  |  |  | Nonlabor | 138.6 | 137.06 | 0 | 3.1.1.1a
OCB EQP -1 | EX NOTM TX A-09L.030 |  |  |  | Nonlabor | 2 | 0 | 0 | 3.2.2.5
OCB EQP -2 | EX NOTM TX A-09L.030 |  |  |  | Nonlabor | 1 | 0 | 0 | 3.2.2.5
OCB EQP -3 | EX NOTM TX A-09L.030 |  |  |  | Nonlabor | 1 | 0 | 0 | 3.2.2.5
OCB EQP -4 | EX NOTM TX A-09L.030 |  |  |  | Nonlabor | 2 | 0 | 0 | 3.2.2.5
OCB EQP -9 | EX NOTM TX A-09L.030 |  |  |  | Nonlabor | 8.3333 | 0 | 0 | 3.2.2.5
OCB EQP -12 | EX NOTM TX A-09L.030 |  |  |  | Nonlabor | 2 | 0 | 0 | 3.2.2.5
OCB EQP -1 | EX NOTM TX A-09L.040 |  |  |  | Nonlabor | 50 | 68.74 | 0 | 3.2.2.6
OCB EQP -2 | EX NOTM TX A-09L.040 |  |  |  | Nonlabor | 25 | 34.37 | 0 | 3.2.2.6
OCB EQP -3 | EX NOTM TX A-09L.040 |  |  |  | Nonlabor | 25 | 34.37 | 0 | 3.2.2.6
OCB EQP -4 | EX NOTM TX A-09L.040 |  |  |  | Nonlabor | 50 | 68.74 | 0 | 3.2.2.6
OCB EQP -9 | EX NOTM TX A-09L.040 |  |  |  | Nonlabor | 208.3333 | 286.4167 | 0 | 3.2.2.6
OCB EQP -12 | EX NOTM TX A-09L.040 |  |  |  | Nonlabor | 50 | 68.74 | 0 | 3.2.2.6
OCB EQP -1 | EX NOTM TX A-10K.020 |  |  |  | Nonlabor | 163.75 | 163.575 | 0.175 | 3.1.1.1a
OCB EQP -9 | EX NOTM TX A-10K.020 |  |  |  | Nonlabor | 288.2 | 287.892 | 0.308 | 3.1.1.1a
OCB EQP -1 | EX NOTM TX A-10K.030 |  |  |  | Nonlabor | 2 | 0 | 0 | 3.2.2.5
OCB EQP -2 | EX NOTM TX A-10K.030 |  |  |  | Nonlabor | 1 | 0 | 0 | 3.2.2.5
OCB EQP -3 | EX NOTM TX A-10K.030 |  |  |  | Nonlabor | 1 | 0 | 0 | 3.2.2.5
OCB EQP -4 | EX NOTM TX A-10K.030 |  |  |  | Nonlabor | 2 | 0 | 0 | 3.2.2.5
OCB EQP -9 | EX NOTM TX A-10K.030 |  |  |  | Nonlabor | 8.3333 | 0 | 0 | 3.2.2.5
OCB EQP -12 | EX NOTM TX A-10K.030 |  |  |  | Nonlabor | 2 | 0 | 0 | 3.2.2.5
OCB EQP -1 | EX NOTM TX A-10K.040 |  |  |  | Nonlabor | 112 | 102.06 | 0 | 3.2.2.6
OCB EQP -2 | EX NOTM TX A-10K.040 |  |  |  | Nonlabor | 56 | 51.03 | 0 | 3.2.2.6
OCB EQP -3 | EX NOTM TX A-10K.040 |  |  |  | Nonlabor | 56 | 51.03 | 0 | 3.2.2.6
OCB EQP -4 | EX NOTM TX A-10K.040 |  |  |  | Nonlabor | 112 | 102.06 | 0 | 3.2.2.6
OCB EQP -9 | EX NOTM TX A-10K.040 |  |  |  | Nonlabor | 466.6667 | 425.25 | 0 | 3.2.2.6
OCB EQP -12 | EX NOTM TX A-10K.040 |  |  |  | Nonlabor | 112 | 102.06 | 0 | 3.2.2.6
OCB EQP -3 | EXE TXY P A-04.060 |  |  |  | Nonlabor | 48 | 0 | 48 | 3.2.3.1
OCB EQP -4 | EXE TXY P A-04.060 |  |  |  | Nonlabor | 96 | 0 | 96 | 3.2.3.1
OCB EQP -8 | EXE TXY P A-04.060 |  |  |  | Nonlabor | 96 | 0 | 96 | 3.2.3.1
OCB EQP -9 | EXE TXY P A-04.060 |  |  |  | Nonlabor | 200 | 0 | 200 | 3.2.3.1
OCB EQP -12 | EXE TXY P A-04.060 |  |  |  | Nonlabor | 79.2 | 0 | 79.2 | 3.2.3.1
OCB EQP -9 | EXE CGD 1010 |  |  |  | Nonlabor | 13.8 | 0 | 13.8 | 3.2.1.1
OCB EQP -8 | EXE CGD 1010 |  |  |  | Nonlabor | 13.8 | 0 | 13.8 | 3.2.1.1
OCB EQP -10 | EXE CGD 1010 |  |  |  | Nonlabor | 13.8 | 0 | 13.8 | 3.2.1.1
OCB EQP -1 | EXE TXY P A-01.020 |  |  |  | Nonlabor | 840.925 | 840.925 | 0 | 3.1.1.1a
OCB EQP -9 | EXE TXY P A-01.020 |  |  |  | Nonlabor | 1480.028 | 1480.028 | 0 | 3.1.1.1a
OCB EQP -1 | EXE TXY P A-02.020 |  |  |  | Nonlabor | 2.5 | 0 | 2.5 | 3.1.1.1a
OCB EQP -9 | EXE TXY P A-02.020 |  |  |  | Nonlabor | 4.4 | 0 | 4.4 | 3.1.1.1a
OCB EQP -3 | EXE TXY P A-02.060 |  |  |  | Nonlabor | 64 | 0 | 64 | 3.2.3.1
OCB EQP -4 | EXE TXY P A-02.060 |  |  |  | Nonlabor | 128 | 0 | 128 | 3.2.3.1
OCB EQP -8 | EXE TXY P A-02.060 |  |  |  | Nonlabor | 128 | 0 | 128 | 3.2.3.1
OCB EQP -9 | EXE TXY P A-02.060 |  |  |  | Nonlabor | 266.6667 | 0 | 266.6667 | 3.2.3.1
OCB EQP -12 | EXE TXY P A-02.060 |  |  |  | Nonlabor | 105.6 | 0 | 105.6 | 3.2.3.1
OCB EQP -16 | EXE TXY P A-02.070 |  |  |  | Nonlabor | 12.2112 | 0 | 12.2112 | 3.2.3.4
OCB EQP -17 | EXE TXY P A-02.070 |  |  |  | Nonlabor | 12.2112 | 0 | 12.2112 | 3.2.3.4
OCB EQP -19 | EXE TXY P A-02.070 |  |  |  | Nonlabor | 12.2112 | 0 | 12.2112 | 3.2.3.4
OCB EQP -15 | EXE TXY P A-02.070 |  |  |  | Nonlabor | 12.2112 | 0 | 12.2112 | 3.2.3.4
OCB EQP -17 | EXE TXY P A-02.130 |  |  |  | Nonlabor | 7.8 | 0 | 7.8 | 3.2.3.5
OCB EQP -19 | EXE TXY P A-02.130 |  |  |  | Nonlabor | 7.8 | 0 | 7.8 | 3.2.3.5
OCB EQP -15 | EXE TXY P A-02.130 |  |  |  | Nonlabor | 7.8 | 0 | 7.8 | 3.2.3.5
OCB EQP -15 | EXE TXY P A-02.080 |  |  |  | Nonlabor | 35.4974 | 0 | 35.4974 | 3.2.3.2
OCB EQP -5 | EXE TXY P A-02.080 |  |  |  | Nonlabor | 35.4974 | 0 | 35.4974 | 3.2.3.2
OCB EQP -6 | EXE TXY P A-02.080 |  |  |  | Nonlabor | 70.9948 | 0 | 70.9948 | 3.2.3.2
OCB EQP -9 | EXE TXY P A-02.080 |  |  |  | Nonlabor | 47.0833 | 0 | 47.0833 | 3.2.3.2
OCB EQP -17 | EXE TXY P A-02.150 |  |  |  | Nonlabor | 8.4 | 0 | 8.4 | 3.2.3.6
OCB EQP -19 | EXE TXY P A-02.150 |  |  |  | Nonlabor | 8.4 | 0 | 8.4 | 3.2.3.6
OCB EQP -15 | EXE TXY P A-02.150 |  |  |  | Nonlabor | 8.4 | 0 | 8.4 | 3.2.3.6
OCB EQP -15 | EXE TXY P A-02.140 |  |  |  | Nonlabor | 29.2147 | 0 | 29.2147 | 3.2.3.3
OCB EQP -5 | EXE TXY P A-02.140 |  |  |  | Nonlabor | 29.2147 | 0 | 29.2147 | 3.2.3.3
OCB EQP -6 | EXE TXY P A-02.140 |  |  |  | Nonlabor | 58.4293 | 0 | 58.4293 | 3.2.3.3
OCB EQP -9 | EXE TXY P A-02.140 |  |  |  | Nonlabor | 38.75 | 0 | 38.75 | 3.2.3.3
OCB EQP -1 | EXE TXY P A-03.020 |  |  |  | Nonlabor | 2.5 | 0 | 2.5 | 3.1.1.1a
OCB EQP -9 | EXE TXY P A-03.020 |  |  |  | Nonlabor | 4.4 | 0 | 4.4 | 3.1.1.1a
OCB EQP -3 | EXE TXY P A-03.060 |  |  |  | Nonlabor | 98.92 | 0 | 98.92 | 3.2.3.1
OCB EQP -4 | EXE TXY P A-03.060 |  |  |  | Nonlabor | 197.84 | 0 | 197.84 | 3.2.3.1
OCB EQP -8 | EXE TXY P A-03.060 |  |  |  | Nonlabor | 197.84 | 0 | 197.84 | 3.2.3.1
OCB EQP -9 | EXE TXY P A-03.060 |  |  |  | Nonlabor | 412.1667 | 0 | 412.1667 | 3.2.3.1
OCB EQP -12 | EXE TXY P A-03.060 |  |  |  | Nonlabor | 163.218 | 0 | 163.218 | 3.2.3.1
OCB EQP -16 | EXE TXY P A-03.070 |  |  |  | Nonlabor | 20.8 | 0 | 20.8 | 3.2.3.4
OCB EQP -17 | EXE TXY P A-03.070 |  |  |  | Nonlabor | 20.8 | 0 | 20.8 | 3.2.3.4
OCB EQP -19 | EXE TXY P A-03.070 |  |  |  | Nonlabor | 20.8 | 0 | 20.8 | 3.2.3.4
OCB EQP -15 | EXE TXY P A-03.070 |  |  |  | Nonlabor | 20.8 | 0 | 20.8 | 3.2.3.4
OCB EQP -17 | EXE TXY P A-03.130 |  |  |  | Nonlabor | 14.4 | 0 | 14.4 | 3.2.3.5
OCB EQP -19 | EXE TXY P A-03.130 |  |  |  | Nonlabor | 14.4 | 0 | 14.4 | 3.2.3.5
OCB EQP -15 | EXE TXY P A-03.130 |  |  |  | Nonlabor | 14.4 | 0 | 14.4 | 3.2.3.5
OCB EQP -15 | EXE TXY P A-03.080 |  |  |  | Nonlabor | 56.5445 | 0 | 56.5445 | 3.2.3.2
OCB EQP -5 | EXE TXY P A-03.080 |  |  |  | Nonlabor | 56.5445 | 0 | 56.5445 | 3.2.3.2
OCB EQP -6 | EXE TXY P A-03.080 |  |  |  | Nonlabor | 113.089 | 0 | 113.089 | 3.2.3.2
OCB EQP -9 | EXE TXY P A-03.080 |  |  |  | Nonlabor | 75 | 0 | 75 | 3.2.3.2
OCB EQP -17 | EXE TXY P A-03.090 |  |  |  | Nonlabor | 14.4 | 0 | 14.4 | 3.2.3.6
OCB EQP -19 | EXE TXY P A-03.090 |  |  |  | Nonlabor | 14.4 | 0 | 14.4 | 3.2.3.6
OCB EQP -15 | EXE TXY P A-03.090 |  |  |  | Nonlabor | 14.4 | 0 | 14.4 | 3.2.3.6
OCB EQP -15 | EXE TXY P A-03.140 |  |  |  | Nonlabor | 37.0681 | 0 | 37.0681 | 3.2.3.3
OCB EQP -5 | EXE TXY P A-03.140 |  |  |  | Nonlabor | 37.0681 | 0 | 37.0681 | 3.2.3.3
OCB EQP -6 | EXE TXY P A-03.140 |  |  |  | Nonlabor | 74.1361 | 0 | 74.1361 | 3.2.3.3
OCB EQP -9 | EXE TXY P A-03.140 |  |  |  | Nonlabor | 49.1667 | 0 | 49.1667 | 3.2.3.3
OCB EQP -1 | EXE TXY P A-04.020 |  |  |  | Nonlabor | 2.5 | 0 | 2.5 | 3.1.1.1a
OCB EQP -9 | EXE TXY P A-04.020 |  |  |  | Nonlabor | 4.4 | 0 | 4.4 | 3.1.1.1a
OCB EQP -16 | EXE TXY P A-04.070 |  |  |  | Nonlabor | 8 | 0 | 8 | 3.2.3.4
OCB EQP -17 | EXE TXY P A-04.070 |  |  |  | Nonlabor | 8 | 0 | 8 | 3.2.3.4
OCB EQP -19 | EXE TXY P A-04.070 |  |  |  | Nonlabor | 8 | 0 | 8 | 3.2.3.4
OCB EQP -15 | EXE TXY P A-04.070 |  |  |  | Nonlabor | 8 | 0 | 8 | 3.2.3.4
OCB EQP -17 | EXE TXY P A-04.130 |  |  |  | Nonlabor | 6 | 0 | 6 | 3.2.3.5
OCB EQP -19 | EXE TXY P A-04.130 |  |  |  | Nonlabor | 6 | 0 | 6 | 3.2.3.5
OCB EQP -15 | EXE TXY P A-04.130 |  |  |  | Nonlabor | 6 | 0 | 6 | 3.2.3.5
OCB EQP -15 | EXE TXY P A-04.080 |  |  |  | Nonlabor | 25.7592 | 0 | 25.7592 | 3.2.3.2
OCB EQP -5 | EXE TXY P A-04.080 |  |  |  | Nonlabor | 25.7592 | 0 | 25.7592 | 3.2.3.2
OCB EQP -6 | EXE TXY P A-04.080 |  |  |  | Nonlabor | 51.5183 | 0 | 51.5183 | 3.2.3.2
OCB EQP -9 | EXE TXY P A-04.080 |  |  |  | Nonlabor | 34.1667 | 0 | 34.1667 | 3.2.3.2
OCB EQP -17 | EXE TXY P A-04.090 |  |  |  | Nonlabor | 6.6 | 0 | 6.6 | 3.2.3.6
OCB EQP -19 | EXE TXY P A-04.090 |  |  |  | Nonlabor | 6.6 | 0 | 6.6 | 3.2.3.6
OCB EQP -15 | EXE TXY P A-04.090 |  |  |  | Nonlabor | 6.6 | 0 | 6.6 | 3.2.3.6
OCB EQP -15 | EXE TXY P A-04.160 |  |  |  | Nonlabor | 20.733 | 0 | 20.733 | 3.2.3.3
OCB EQP -5 | EXE TXY P A-04.160 |  |  |  | Nonlabor | 20.733 | 0 | 20.733 | 3.2.3.3
OCB EQP -6 | EXE TXY P A-04.160 |  |  |  | Nonlabor | 41.466 | 0 | 41.466 | 3.2.3.3
OCB EQP -9 | EXE TXY P A-04.160 |  |  |  | Nonlabor | 27.5 | 0 | 27.5 | 3.2.3.3
OCB EQP -1 | EX SR A-13.020 |  |  |  | Nonlabor | 719 | 718.975 | 0.025 | 3.1.1.1a
OCB EQP -9 | EX SR A-13.020 |  |  |  | Nonlabor | 1265.44 | 1265.396 | 0.044 | 3.1.1.1a
OCB EQP -1 | EX NOTM TX A-11E.030 |  |  |  | Nonlabor | 2.5 | 2.5 | 0 | 3.1.1.1a
OCB EQP -9 | EX NOTM TX A-11E.030 |  |  |  | Nonlabor | 4.4 | 4.4 | 0 | 3.1.1.1a
OCB EQP -1 | EX NOTM TX A-11E.040 |  |  |  | Nonlabor | 2 | 0 | 2 | 3.2.2.5
OCB EQP -2 | EX NOTM TX A-11E.040 |  |  |  | Nonlabor | 1 | 0 | 1 | 3.2.2.5
OCB EQP -3 | EX NOTM TX A-11E.040 |  |  |  | Nonlabor | 1 | 0 | 1 | 3.2.2.5
OCB EQP -4 | EX NOTM TX A-11E.040 |  |  |  | Nonlabor | 2 | 0 | 2 | 3.2.2.5
OCB EQP -9 | EX NOTM TX A-11E.040 |  |  |  | Nonlabor | 8.3333 | 0 | 8.3333 | 3.2.2.5
OCB EQP -12 | EX NOTM TX A-11E.040 |  |  |  | Nonlabor | 2 | 0 | 2 | 3.2.2.5
OCB EQP -1 | EX NOTM TX A-11E.050 |  |  |  | Nonlabor | 98 | 0 | 98 | 3.2.2.6
OCB EQP -2 | EX NOTM TX A-11E.050 |  |  |  | Nonlabor | 49 | 0 | 49 | 3.2.2.6
OCB EQP -3 | EX NOTM TX A-11E.050 |  |  |  | Nonlabor | 49 | 0 | 49 | 3.2.2.6
OCB EQP -4 | EX NOTM TX A-11E.050 |  |  |  | Nonlabor | 98 | 0 | 98 | 3.2.2.6
OCB EQP -9 | EX NOTM TX A-11E.050 |  |  |  | Nonlabor | 408.3333 | 0 | 408.3333 | 3.2.2.6
OCB EQP -12 | EX NOTM TX A-11E.050 |  |  |  | Nonlabor | 98 | 0 | 98 | 3.2.2.6
OCB EQP -1 | NOTM TX-New A-12.020 |  |  |  | Nonlabor | 2.5 | 2.5 | 0 | 3.1.1.1a
OCB EQP -9 | NOTM TX-New A-12.020 |  |  |  | Nonlabor | 4.4 | 4.4 | 0 | 3.1.1.1a
OCB EQP -1 | NOTM TX-New A-12.030 |  |  |  | Nonlabor | 1 | 0 | 1 | 3.2.2.5
OCB EQP -2 | NOTM TX-New A-12.030 |  |  |  | Nonlabor | 0.5 | 0 | 0.5 | 3.2.2.5
OCB EQP -3 | NOTM TX-New A-12.030 |  |  |  | Nonlabor | 0.5 | 0 | 0.5 | 3.2.2.5
OCB EQP -4 | NOTM TX-New A-12.030 |  |  |  | Nonlabor | 1 | 0 | 1 | 3.2.2.5
OCB EQP -9 | NOTM TX-New A-12.030 |  |  |  | Nonlabor | 4.1667 | 0 | 4.1667 | 3.2.2.5
OCB EQP -12 | NOTM TX-New A-12.030 |  |  |  | Nonlabor | 1 | 0 | 1 | 3.2.2.5
OCB EQP -1 | NOTM TX-New A-12.040 |  |  |  | Nonlabor | 76.86 | 0 | 76.86 | 3.2.2.6
OCB EQP -2 | NOTM TX-New A-12.040 |  |  |  | Nonlabor | 38.43 | 0 | 38.43 | 3.2.2.6
OCB EQP -3 | NOTM TX-New A-12.040 |  |  |  | Nonlabor | 38.43 | 0 | 38.43 | 3.2.2.6
OCB EQP -4 | NOTM TX-New A-12.040 |  |  |  | Nonlabor | 76.86 | 0 | 76.86 | 3.2.2.6
OCB EQP -9 | NOTM TX-New A-12.040 |  |  |  | Nonlabor | 320.25 | 0 | 320.25 | 3.2.2.6
OCB EQP -12 | NOTM TX-New A-12.040 |  |  |  | Nonlabor | 76.86 | 0 | 76.86 | 3.2.2.6
OCB EQP -15 | EXE TXY P A-02.100 |  |  |  | Nonlabor | 35.4974 | 0 | 35.4974 | 3.2.3.2
OCB EQP -5 | EXE TXY P A-02.100 |  |  |  | Nonlabor | 35.4974 | 0 | 35.4974 | 3.2.3.2
OCB EQP -6 | EXE TXY P A-02.100 |  |  |  | Nonlabor | 70.9948 | 0 | 70.9948 | 3.2.3.2
OCB EQP -9 | EXE TXY P A-02.100 |  |  |  | Nonlabor | 47.0833 | 0 | 47.0833 | 3.2.3.2
OCB EQP -15 | EXE TXY P A-02.120 |  |  |  | Nonlabor | 30.4712 | 0 | 30.4712 | 3.2.3.2
OCB EQP -5 | EXE TXY P A-02.120 |  |  |  | Nonlabor | 30.4712 | 0 | 30.4712 | 3.2.3.2
OCB EQP -6 | EXE TXY P A-02.120 |  |  |  | Nonlabor | 60.9424 | 0 | 60.9424 | 3.2.3.2
OCB EQP -9 | EXE TXY P A-02.120 |  |  |  | Nonlabor | 40.4167 | 0 | 40.4167 | 3.2.3.2
OCB EQP -15 | EXE TXY P A-02.160 |  |  |  | Nonlabor | 29.2147 | 0 | 29.2147 | 3.2.3.3
OCB EQP -5 | EXE TXY P A-02.160 |  |  |  | Nonlabor | 29.2147 | 0 | 29.2147 | 3.2.3.3
OCB EQP -6 | EXE TXY P A-02.160 |  |  |  | Nonlabor | 58.4293 | 0 | 58.4293 | 3.2.3.3
OCB EQP -9 | EXE TXY P A-02.160 |  |  |  | Nonlabor | 38.75 | 0 | 38.75 | 3.2.3.3
OCB EQP -17 | EXE TXY P A-02.090 |  |  |  | Nonlabor | 8.4 | 0 | 8.4 | 3.2.3.6
OCB EQP -19 | EXE TXY P A-02.090 |  |  |  | Nonlabor | 8.4 | 0 | 8.4 | 3.2.3.6
OCB EQP -15 | EXE TXY P A-02.090 |  |  |  | Nonlabor | 8.4 | 0 | 8.4 | 3.2.3.6
OCB EQP -17 | EXE TXY P A-02.110 |  |  |  | Nonlabor | 8.4 | 0 | 8.4 | 3.2.3.6
OCB EQP -19 | EXE TXY P A-02.110 |  |  |  | Nonlabor | 8.4 | 0 | 8.4 | 3.2.3.6
OCB EQP -15 | EXE TXY P A-02.110 |  |  |  | Nonlabor | 8.4 | 0 | 8.4 | 3.2.3.6
OCB EQP -15 | EXE TXY P A-03.100 |  |  |  | Nonlabor | 58.3665 | 0 | 58.3665 | 3.2.3.2
OCB EQP -5 | EXE TXY P A-03.100 |  |  |  | Nonlabor | 58.3665 | 0 | 58.3665 | 3.2.3.2
OCB EQP -6 | EXE TXY P A-03.100 |  |  |  | Nonlabor | 116.733 | 0 | 116.733 | 3.2.3.2
OCB EQP -9 | EXE TXY P A-03.100 |  |  |  | Nonlabor | 77.4167 | 0 | 77.4167 | 3.2.3.2
OCB EQP -15 | EXE TXY P A-03.120 |  |  |  | Nonlabor | 54.3455 | 0 | 54.3455 | 3.2.3.2
OCB EQP -5 | EXE TXY P A-03.120 |  |  |  | Nonlabor | 54.3455 | 0 | 54.3455 | 3.2.3.2
OCB EQP -6 | EXE TXY P A-03.120 |  |  |  | Nonlabor | 108.6911 | 0 | 108.6911 | 3.2.3.2
OCB EQP -9 | EXE TXY P A-03.120 |  |  |  | Nonlabor | 72.0833 | 0 | 72.0833 | 3.2.3.2
OCB EQP -17 | EXE TXY P A-03.110 |  |  |  | Nonlabor | 14.4 | 0 | 14.4 | 3.2.3.6
OCB EQP -19 | EXE TXY P A-03.110 |  |  |  | Nonlabor | 14.4 | 0 | 14.4 | 3.2.3.6
OCB EQP -15 | EXE TXY P A-03.110 |  |  |  | Nonlabor | 14.4 | 0 | 14.4 | 3.2.3.6
OCB EQP -17 | EXE TXY P A-03.150 |  |  |  | Nonlabor | 14.4 | 0 | 14.4 | 3.2.3.6
OCB EQP -19 | EXE TXY P A-03.150 |  |  |  | Nonlabor | 14.4 | 0 | 14.4 | 3.2.3.6
OCB EQP -15 | EXE TXY P A-03.150 |  |  |  | Nonlabor | 14.4 | 0 | 14.4 | 3.2.3.6
OCB EQP -15 | EXE TXY P A-03.160 |  |  |  | Nonlabor | 34.555 | 0 | 34.555 | 3.2.3.3
OCB EQP -5 | EXE TXY P A-03.160 |  |  |  | Nonlabor | 34.555 | 0 | 34.555 | 3.2.3.3
OCB EQP -6 | EXE TXY P A-03.160 |  |  |  | Nonlabor | 69.1099 | 0 | 69.1099 | 3.2.3.3
OCB EQP -9 | EXE TXY P A-03.160 |  |  |  | Nonlabor | 45.8333 | 0 | 45.8333 | 3.2.3.3
OCB EQP -1 | EXE TXY P A-01.180 |  |  |  | Nonlabor | 20 | 0 | 20 | 3.2.2.6
OCB EQP -2 | EXE TXY P A-01.180 |  |  |  | Nonlabor | 10 | 0 | 10 | 3.2.2.6
OCB EQP -3 | EXE TXY P A-01.180 |  |  |  | Nonlabor | 10 | 0 | 10 | 3.2.2.6
OCB EQP -4 | EXE TXY P A-01.180 |  |  |  | Nonlabor | 20 | 0 | 20 | 3.2.2.6
OCB EQP -9 | EXE TXY P A-01.180 |  |  |  | Nonlabor | 83.3333 | 0 | 83.3333 | 3.2.2.6
OCB EQP -12 | EXE TXY P A-01.180 |  |  |  | Nonlabor | 20 | 0 | 20 | 3.2.2.6
OCB EQP -1 | EXE TXY P A-02.180 |  |  |  | Nonlabor | 17 | 0 | 17 | 3.2.2.6
OCB EQP -2 | EXE TXY P A-02.180 |  |  |  | Nonlabor | 8.5 | 0 | 8.5 | 3.2.2.6
OCB EQP -3 | EXE TXY P A-02.180 |  |  |  | Nonlabor | 8.5 | 0 | 8.5 | 3.2.2.6
OCB EQP -4 | EXE TXY P A-02.180 |  |  |  | Nonlabor | 17 | 0 | 17 | 3.2.2.6
OCB EQP -9 | EXE TXY P A-02.180 |  |  |  | Nonlabor | 70.8333 | 0 | 70.8333 | 3.2.2.6
OCB EQP -12 | EXE TXY P A-02.180 |  |  |  | Nonlabor | 17 | 0 | 17 | 3.2.2.6
OCB EQP -15 | EXE TXY P A-04.100 |  |  |  | Nonlabor | 25.7592 | 0 | 25.7592 | 3.2.3.2
OCB EQP -5 | EXE TXY P A-04.100 |  |  |  | Nonlabor | 25.7592 | 0 | 25.7592 | 3.2.3.2
OCB EQP -6 | EXE TXY P A-04.100 |  |  |  | Nonlabor | 51.5183 | 0 | 51.5183 | 3.2.3.2
OCB EQP -9 | EXE TXY P A-04.100 |  |  |  | Nonlabor | 34.1667 | 0 | 34.1667 | 3.2.3.2
OCB EQP -15 | EXE TXY P A-04.120 |  |  |  | Nonlabor | 21.9895 | 0 | 21.9895 | 3.2.3.2
OCB EQP -5 | EXE TXY P A-04.120 |  |  |  | Nonlabor | 21.9895 | 0 | 21.9895 | 3.2.3.2
OCB EQP -6 | EXE TXY P A-04.120 |  |  |  | Nonlabor | 43.9791 | 0 | 43.9791 | 3.2.3.2
OCB EQP -9 | EXE TXY P A-04.120 |  |  |  | Nonlabor | 29.1667 | 0 | 29.1667 | 3.2.3.2
OCB EQP -15 | EXE TXY P A-04.140 |  |  |  | Nonlabor | 20.733 | 0 | 20.733 | 3.2.3.3
OCB EQP -5 | EXE TXY P A-04.140 |  |  |  | Nonlabor | 20.733 | 0 | 20.733 | 3.2.3.3
OCB EQP -6 | EXE TXY P A-04.140 |  |  |  | Nonlabor | 41.466 | 0 | 41.466 | 3.2.3.3
OCB EQP -9 | EXE TXY P A-04.140 |  |  |  | Nonlabor | 27.5 | 0 | 27.5 | 3.2.3.3
OCB EQP -17 | EXE TXY P A-04.110 |  |  |  | Nonlabor | 6.6 | 0 | 6.6 | 3.2.3.6
OCB EQP -19 | EXE TXY P A-04.110 |  |  |  | Nonlabor | 6.6 | 0 | 6.6 | 3.2.3.6
OCB EQP -15 | EXE TXY P A-04.110 |  |  |  | Nonlabor | 6.6 | 0 | 6.6 | 3.2.3.6
OCB EQP -17 | EXE TXY P A-04.150 |  |  |  | Nonlabor | 6.6 | 0 | 6.6 | 3.2.3.6
OCB EQP -19 | EXE TXY P A-04.150 |  |  |  | Nonlabor | 6.6 | 0 | 6.6 | 3.2.3.6
OCB EQP -15 | EXE TXY P A-04.150 |  |  |  | Nonlabor | 6.6 | 0 | 6.6 | 3.2.3.6
OCB EQP -1 | EXE TXY P A-03.180 |  |  |  | Nonlabor | 20 | 0 | 20 | 3.2.2.6
OCB EQP -2 | EXE TXY P A-03.180 |  |  |  | Nonlabor | 10 | 0 | 10 | 3.2.2.6
OCB EQP -3 | EXE TXY P A-03.180 |  |  |  | Nonlabor | 10 | 0 | 10 | 3.2.2.6
OCB EQP -4 | EXE TXY P A-03.180 |  |  |  | Nonlabor | 20 | 0 | 20 | 3.2.2.6
OCB EQP -9 | EXE TXY P A-03.180 |  |  |  | Nonlabor | 83.3333 | 0 | 83.3333 | 3.2.2.6
OCB EQP -12 | EXE TXY P A-03.180 |  |  |  | Nonlabor | 20 | 0 | 20 | 3.2.2.6
OCB EQP -1 | EXE TXY P A-04.180 |  |  |  | Nonlabor | 10 | 0 | 10 | 3.2.2.6
OCB EQP -2 | EXE TXY P A-04.180 |  |  |  | Nonlabor | 5 | 0 | 5 | 3.2.2.6
OCB EQP -3 | EXE TXY P A-04.180 |  |  |  | Nonlabor | 5 | 0 | 5 | 3.2.2.6
OCB EQP -4 | EXE TXY P A-04.180 |  |  |  | Nonlabor | 10 | 0 | 10 | 3.2.2.6
OCB EQP -9 | EXE TXY P A-04.180 |  |  |  | Nonlabor | 41.6667 | 0 | 41.6667 | 3.2.2.6
OCB EQP -12 | EXE TXY P A-04.180 |  |  |  | Nonlabor | 10 | 0 | 10 | 3.2.2.6
OCB EQP -1 | EX NOTM TX A-09L.180 |  |  |  | Nonlabor | 2 | 5.4 | 0 | 3.2.2.6
OCB EQP -2 | EX NOTM TX A-09L.180 |  |  |  | Nonlabor | 1 | 2.7 | 0 | 3.2.2.6
OCB EQP -3 | EX NOTM TX A-09L.180 |  |  |  | Nonlabor | 1 | 2.7 | 0 | 3.2.2.6
OCB EQP -4 | EX NOTM TX A-09L.180 |  |  |  | Nonlabor | 2 | 5.4 | 0 | 3.2.2.6
OCB EQP -9 | EX NOTM TX A-09L.180 |  |  |  | Nonlabor | 8.3333 | 22.5 | 0 | 3.2.2.6
OCB EQP -12 | EX NOTM TX A-09L.180 |  |  |  | Nonlabor | 2 | 5.4 | 0 | 3.2.2.6
OCB EQP -1 | EX NOTM TX A-10K.180 |  |  |  | Nonlabor | 4 | 5.7 | 0 | 3.2.2.6
OCB EQP -2 | EX NOTM TX A-10K.180 |  |  |  | Nonlabor | 2 | 2.85 | 0 | 3.2.2.6
OCB EQP -3 | EX NOTM TX A-10K.180 |  |  |  | Nonlabor | 2 | 2.85 | 0 | 3.2.2.6
OCB EQP -4 | EX NOTM TX A-10K.180 |  |  |  | Nonlabor | 4 | 5.7 | 0 | 3.2.2.6
OCB EQP -9 | EX NOTM TX A-10K.180 |  |  |  | Nonlabor | 16.6667 | 23.75 | 0 | 3.2.2.6
OCB EQP -12 | EX NOTM TX A-10K.180 |  |  |  | Nonlabor | 4 | 5.7 | 0 | 3.2.2.6
OCB EQP -1 | EX NOTM TX A-11E.200 |  |  |  | Nonlabor | 2 | 0 | 2 | 3.2.2.6
OCB EQP -2 | EX NOTM TX A-11E.200 |  |  |  | Nonlabor | 1 | 0 | 1 | 3.2.2.6
OCB EQP -3 | EX NOTM TX A-11E.200 |  |  |  | Nonlabor | 1 | 0 | 1 | 3.2.2.6
OCB EQP -4 | EX NOTM TX A-11E.200 |  |  |  | Nonlabor | 2 | 0 | 2 | 3.2.2.6
OCB EQP -9 | EX NOTM TX A-11E.200 |  |  |  | Nonlabor | 8.3333 | 0 | 8.3333 | 3.2.2.6
OCB EQP -12 | EX NOTM TX A-11E.200 |  |  |  | Nonlabor | 2 | 0 | 2 | 3.2.2.6
OCB EQP -1 | NOTM TX-New A-12.180 |  |  |  | Nonlabor | 3 | 0 | 3 | 3.2.2.6
OCB EQP -2 | NOTM TX-New A-12.180 |  |  |  | Nonlabor | 1.5 | 0 | 1.5 | 3.2.2.6
OCB EQP -3 | NOTM TX-New A-12.180 |  |  |  | Nonlabor | 1.5 | 0 | 1.5 | 3.2.2.6
OCB EQP -4 | NOTM TX-New A-12.180 |  |  |  | Nonlabor | 3 | 0 | 3 | 3.2.2.6
OCB EQP -9 | NOTM TX-New A-12.180 |  |  |  | Nonlabor | 12.5 | 0 | 12.5 | 3.2.2.6
OCB EQP -12 | NOTM TX-New A-12.180 |  |  |  | Nonlabor | 3 | 0 | 3 | 3.2.2.6
OCB EQP -16 | NOTM TX-New A-12.070 |  |  |  | Nonlabor | 2.4128 | 0 | 2.4128 | 3.2.3.4
OCB EQP -17 | NOTM TX-New A-12.070 |  |  |  | Nonlabor | 2.4128 | 0 | 2.4128 | 3.2.3.4
OCB EQP -19 | NOTM TX-New A-12.070 |  |  |  | Nonlabor | 2.4128 | 0 | 2.4128 | 3.2.3.4
OCB EQP -15 | NOTM TX-New A-12.070 |  |  |  | Nonlabor | 2.4128 | 0 | 2.4128 | 3.2.3.4
OCB EQP -17 | NOTM TX-New A-12.130 |  |  |  | Nonlabor | 1.8324 | 0 | 1.8324 | 3.2.3.5
OCB EQP -19 | NOTM TX-New A-12.130 |  |  |  | Nonlabor | 1.8324 | 0 | 1.8324 | 3.2.3.5
OCB EQP -15 | NOTM TX-New A-12.130 |  |  |  | Nonlabor | 1.8324 | 0 | 1.8324 | 3.2.3.5
OCB EQP -15 | NOTM TX-New A-12.080 |  |  |  | Nonlabor | 5.0262 | 0 | 5.0262 | 3.2.3.2
OCB EQP -5 | NOTM TX-New A-12.080 |  |  |  | Nonlabor | 5.0262 | 0 | 5.0262 | 3.2.3.2
OCB EQP -6 | NOTM TX-New A-12.080 |  |  |  | Nonlabor | 10.0524 | 0 | 10.0524 | 3.2.3.2
OCB EQP -9 | NOTM TX-New A-12.080 |  |  |  | Nonlabor | 6.6667 | 0 | 6.6667 | 3.2.3.2
OCB EQP -17 | NOTM TX-New A-12.090 |  |  |  | Nonlabor | 1.8144 | 0 | 1.8144 | 3.2.3.6
OCB EQP -19 | NOTM TX-New A-12.090 |  |  |  | Nonlabor | 1.8144 | 0 | 1.8144 | 3.2.3.6
OCB EQP -15 | NOTM TX-New A-12.090 |  |  |  | Nonlabor | 1.8144 | 0 | 1.8144 | 3.2.3.6
OCB EQP -15 | NOTM TX-New A-12.160 |  |  |  | Nonlabor | 6.2199 | 0 | 6.2199 | 3.2.3.3
OCB EQP -5 | NOTM TX-New A-12.160 |  |  |  | Nonlabor | 6.2199 | 0 | 6.2199 | 3.2.3.3
OCB EQP -6 | NOTM TX-New A-12.160 |  |  |  | Nonlabor | 12.4398 | 0 | 12.4398 | 3.2.3.3
OCB EQP -9 | NOTM TX-New A-12.160 |  |  |  | Nonlabor | 8.25 | 0 | 8.25 | 3.2.3.3
OCB EQP -15 | NOTM TX-New A-12.100 |  |  |  | Nonlabor | 5.0262 | 0 | 5.0262 | 3.2.3.2
OCB EQP -5 | NOTM TX-New A-12.100 |  |  |  | Nonlabor | 5.0262 | 0 | 5.0262 | 3.2.3.2
OCB EQP -6 | NOTM TX-New A-12.100 |  |  |  | Nonlabor | 10.0524 | 0 | 10.0524 | 3.2.3.2
OCB EQP -9 | NOTM TX-New A-12.100 |  |  |  | Nonlabor | 6.6667 | 0 | 6.6667 | 3.2.3.2
OCB EQP -15 | NOTM TX-New A-12.120 |  |  |  | Nonlabor | 3.4555 | 0 | 3.4555 | 3.2.3.2
OCB EQP -5 | NOTM TX-New A-12.120 |  |  |  | Nonlabor | 3.4555 | 0 | 3.4555 | 3.2.3.2
OCB EQP -6 | NOTM TX-New A-12.120 |  |  |  | Nonlabor | 6.911 | 0 | 6.911 | 3.2.3.2
OCB EQP -9 | NOTM TX-New A-12.120 |  |  |  | Nonlabor | 4.5833 | 0 | 4.5833 | 3.2.3.2
OCB EQP -15 | NOTM TX-New A-12.140 |  |  |  | Nonlabor | 6.2827 | 0 | 6.2827 | 3.2.3.3
OCB EQP -5 | NOTM TX-New A-12.140 |  |  |  | Nonlabor | 6.2827 | 0 | 6.2827 | 3.2.3.3
OCB EQP -6 | NOTM TX-New A-12.140 |  |  |  | Nonlabor | 12.5654 | 0 | 12.5654 | 3.2.3.3
OCB EQP -9 | NOTM TX-New A-12.140 |  |  |  | Nonlabor | 8.3333 | 0 | 8.3333 | 3.2.3.3
OCB EQP -17 | NOTM TX-New A-12.110 |  |  |  | Nonlabor | 1.8144 | 0 | 1.8144 | 3.2.3.6
OCB EQP -19 | NOTM TX-New A-12.110 |  |  |  | Nonlabor | 1.8144 | 0 | 1.8144 | 3.2.3.6
OCB EQP -15 | NOTM TX-New A-12.110 |  |  |  | Nonlabor | 1.8144 | 0 | 1.8144 | 3.2.3.6
OCB EQP -17 | NOTM TX-New A-12.150 |  |  |  | Nonlabor | 1.3836 | 0 | 1.3836 | 3.2.3.6
OCB EQP -19 | NOTM TX-New A-12.150 |  |  |  | Nonlabor | 1.3836 | 0 | 1.3836 | 3.2.3.6
OCB EQP -15 | NOTM TX-New A-12.150 |  |  |  | Nonlabor | 1.3836 | 0 | 1.3836 | 3.2.3.6
OCB EQP -16 | EXE TXY P A-01.070 |  |  |  | Nonlabor | 20.8 | 13.4304 | 0 | 3.2.3.4
OCB EQP -17 | EXE TXY P A-01.070 |  |  |  | Nonlabor | 20.8 | 13.4304 | 0 | 3.2.3.4
OCB EQP -19 | EXE TXY P A-01.070 |  |  |  | Nonlabor | 20.8 | 13.4304 | 0 | 3.2.3.4
OCB EQP -15 | EXE TXY P A-01.070 |  |  |  | Nonlabor | 20.8 | 13.4304 | 0 | 3.2.3.4
OCB EQP -17 | EXE TXY P A-01.130 |  |  |  | Nonlabor | 14.4 | 0 | 14.4 | 3.2.3.5
OCB EQP -19 | EXE TXY P A-01.130 |  |  |  | Nonlabor | 14.4 | 0 | 14.4 | 3.2.3.5
OCB EQP -15 | EXE TXY P A-01.130 |  |  |  | Nonlabor | 14.4 | 0 | 14.4 | 3.2.3.5
OCB EQP -15 | EXE TXY P A-01.080 |  |  |  | Nonlabor | 55.6021 | 37.5079 | 18.0942 | 3.2.3.2
OCB EQP -5 | EXE TXY P A-01.080 |  |  |  | Nonlabor | 55.6021 | 37.5079 | 18.0942 | 3.2.3.2
OCB EQP -6 | EXE TXY P A-01.080 |  |  |  | Nonlabor | 111.2042 | 75.0157 | 36.1885 | 3.2.3.2
OCB EQP -9 | EXE TXY P A-01.080 |  |  |  | Nonlabor | 73.75 | 49.75 | 24 | 3.2.3.2
OCB EQP -17 | EXE TXY P A-01.090 |  |  |  | Nonlabor | 14.4 | 0 | 14.4 | 3.2.3.6
OCB EQP -19 | EXE TXY P A-01.090 |  |  |  | Nonlabor | 14.4 | 0 | 14.4 | 3.2.3.6
OCB EQP -15 | EXE TXY P A-01.090 |  |  |  | Nonlabor | 14.4 | 0 | 14.4 | 3.2.3.6
OCB EQP -15 | EXE TXY P A-01.160 |  |  |  | Nonlabor | 47.1204 | 0 | 47.1204 | 3.2.3.3
OCB EQP -5 | EXE TXY P A-01.160 |  |  |  | Nonlabor | 47.1204 | 0 | 47.1204 | 3.2.3.3
OCB EQP -6 | EXE TXY P A-01.160 |  |  |  | Nonlabor | 94.2408 | 0 | 94.2408 | 3.2.3.3
OCB EQP -9 | EXE TXY P A-01.160 |  |  |  | Nonlabor | 62.5 | 0 | 62.5 | 3.2.3.3
OCB EQP -15 | EXE TXY P A-01.100 |  |  |  | Nonlabor | 55.6021 | 0 | 55.6021 | 3.2.3.2
OCB EQP -5 | EXE TXY P A-01.100 |  |  |  | Nonlabor | 55.6021 | 0 | 55.6021 | 3.2.3.2
OCB EQP -6 | EXE TXY P A-01.100 |  |  |  | Nonlabor | 111.2042 | 0 | 111.2042 | 3.2.3.2
OCB EQP -9 | EXE TXY P A-01.100 |  |  |  | Nonlabor | 73.75 | 0 | 73.75 | 3.2.3.2
OCB EQP -15 | EXE TXY P A-01.120 |  |  |  | Nonlabor | 53.089 | 0 | 53.089 | 3.2.3.2
OCB EQP -5 | EXE TXY P A-01.120 |  |  |  | Nonlabor | 53.089 | 0 | 53.089 | 3.2.3.2
OCB EQP -6 | EXE TXY P A-01.120 |  |  |  | Nonlabor | 106.178 | 0 | 106.178 | 3.2.3.2
OCB EQP -9 | EXE TXY P A-01.120 |  |  |  | Nonlabor | 70.4167 | 0 | 70.4167 | 3.2.3.2
OCB EQP -15 | EXE TXY P A-01.140 |  |  |  | Nonlabor | 47.1204 | 0 | 47.1204 | 3.2.3.3
OCB EQP -5 | EXE TXY P A-01.140 |  |  |  | Nonlabor | 47.1204 | 0 | 47.1204 | 3.2.3.3
OCB EQP -6 | EXE TXY P A-01.140 |  |  |  | Nonlabor | 94.2408 | 0 | 94.2408 | 3.2.3.3
OCB EQP -9 | EXE TXY P A-01.140 |  |  |  | Nonlabor | 62.5 | 0 | 62.5 | 3.2.3.3
OCB EQP -17 | EXE TXY P A-01.110 |  |  |  | Nonlabor | 14.4 | 0 | 14.4 | 3.2.3.6
OCB EQP -19 | EXE TXY P A-01.110 |  |  |  | Nonlabor | 14.4 | 0 | 14.4 | 3.2.3.6
OCB EQP -15 | EXE TXY P A-01.110 |  |  |  | Nonlabor | 14.4 | 0 | 14.4 | 3.2.3.6
OCB EQP -17 | EXE TXY P A-01.150 |  |  |  | Nonlabor | 14.4 | 0 | 14.4 | 3.2.3.6
OCB EQP -19 | EXE TXY P A-01.150 |  |  |  | Nonlabor | 14.4 | 0 | 14.4 | 3.2.3.6
OCB EQP -15 | EXE TXY P A-01.150 |  |  |  | Nonlabor | 14.4 | 0 | 14.4 | 3.2.3.6
OCB EQP -3 | EXE TXY P A-01.060 |  |  |  | Nonlabor | 96.6 | 72.76 | 0 | 3.2.3.1
OCB EQP -4 | EXE TXY P A-01.060 |  |  |  | Nonlabor | 193.2 | 145.52 | 0 | 3.2.3.1
OCB EQP -8 | EXE TXY P A-01.060 |  |  |  | Nonlabor | 193.2 | 145.52 | 0 | 3.2.3.1
OCB EQP -9 | EXE TXY P A-01.060 |  |  |  | Nonlabor | 402.5 | 303.1667 | 0 | 3.2.3.1
OCB EQP -12 | EXE TXY P A-01.060 |  |  |  | Nonlabor | 159.39 | 120.054 | 0 | 3.2.3.1
OCB EQP -3 | NOTM TX-New A-12.060 |  |  |  | Nonlabor | 13.6 | 0 | 13.6 | 3.2.3.1
OCB EQP -4 | NOTM TX-New A-12.060 |  |  |  | Nonlabor | 27.2 | 0 | 27.2 | 3.2.3.1
OCB EQP -8 | NOTM TX-New A-12.060 |  |  |  | Nonlabor | 27.2 | 0 | 27.2 | 3.2.3.1
OCB EQP -9 | NOTM TX-New A-12.060 |  |  |  | Nonlabor | 56.6667 | 0 | 56.6667 | 3.2.3.1
OCB EQP -12 | NOTM TX-New A-12.060 |  |  |  | Nonlabor | 22.44 | 0 | 22.44 | 3.2.3.1
OCB EQP -8 | EX NOTM TX A-11P.020 |  |  |  | Nonlabor | 1.142 | 0 | 1.142 | 3.2.3.6a
OCB EQP -8 | EX NOTM TX A-11P.020 |  |  |  | Nonlabor | 1.142 | 0 | 1.142 | 3.2.3.6a
OCB EQP -9 | EX NOTM TX A-11P.020 |  |  |  | Nonlabor | 1.142 | 0 | 1.142 | 3.2.3.6a
OCB EQP -1 | EX TS A-14.020 |  |  |  | Nonlabor | 2.5 | 0 | 2.5 | 3.1.1.1a
OCB EQP -9 | EX TS A-14.020 |  |  |  | Nonlabor | 4.4 | 0 | 4.4 | 3.1.1.1a
OCB EQP -1 | EX TS A-14.030 |  |  |  | Nonlabor | 102.58 | 0 | 102.58 | 3.2.2.5
OCB EQP -2 | EX TS A-14.030 |  |  |  | Nonlabor | 51.29 | 0 | 51.29 | 3.2.2.5
OCB EQP -3 | EX TS A-14.030 |  |  |  | Nonlabor | 51.29 | 0 | 51.29 | 3.2.2.5
OCB EQP -4 | EX TS A-14.030 |  |  |  | Nonlabor | 102.58 | 0 | 102.58 | 3.2.2.5
OCB EQP -9 | EX TS A-14.030 |  |  |  | Nonlabor | 427.4167 | 0 | 427.4167 | 3.2.2.5
OCB EQP -12 | EX TS A-14.030 |  |  |  | Nonlabor | 102.58 | 0 | 102.58 | 3.2.2.5
OCB EQP -1 | EX TS A-14.040 |  |  |  | Nonlabor | 35 | 0 | 35 | 3.2.2.6
OCB EQP -2 | EX TS A-14.040 |  |  |  | Nonlabor | 17.5 | 0 | 17.5 | 3.2.2.6
OCB EQP -3 | EX TS A-14.040 |  |  |  | Nonlabor | 17.5 | 0 | 17.5 | 3.2.2.6
OCB EQP -4 | EX TS A-14.040 |  |  |  | Nonlabor | 35 | 0 | 35 | 3.2.2.6
OCB EQP -9 | EX TS A-14.040 |  |  |  | Nonlabor | 145.8333 | 0 | 145.8333 | 3.2.2.6
OCB EQP -12 | EX TS A-14.040 |  |  |  | Nonlabor | 35 | 0 | 35 | 3.2.2.6
OCB EQP - 21 | EXE RE A-05.100 |  |  |  | Nonlabor | 7.75 | 0 | 7.75 | 3.2.2.12
OCB EQP - 20 | EXE RE A-05.100 |  |  |  | Nonlabor | 0.51667 | 0 | 0.51667 | 3.2.2.12
OCB EQP -15 | EXE RE A-05.100 |  |  |  | Nonlabor | 12.4 | 0 | 12.4 | 3.2.2.12
OCB EQP - 21 | EXE RE A-05.110 |  |  |  | Nonlabor | 57.5 | 0 | 57.5 | 3.2.2.13
OCB EQP - 20 | EXE RE A-05.110 |  |  |  | Nonlabor | 3.8333 | 0 | 3.8333 | 3.2.2.13
OCB EQP -15 | EXE RE A-05.110 |  |  |  | Nonlabor | 92 | 0 | 92 | 3.2.2.13
OCB EQP - 21 | EXE RE A-06.100 |  |  |  | Nonlabor | 6.25 | 0 | 6.25 | 3.2.2.12
OCB EQP - 20 | EXE RE A-06.100 |  |  |  | Nonlabor | 0.41667 | 0 | 0.41667 | 3.2.2.12
OCB EQP -15 | EXE RE A-06.100 |  |  |  | Nonlabor | 10 | 0 | 10 | 3.2.2.12
OCB EQP - 21 | EXE RE A-07.100 |  |  |  | Nonlabor | 0.75 | 0 | 0.75 | 3.2.2.12
OCB EQP - 20 | EXE RE A-07.100 |  |  |  | Nonlabor | 0.05 | 0 | 0.05 | 3.2.2.12
OCB EQP -15 | EXE RE A-07.100 |  |  |  | Nonlabor | 1.2 | 0 | 1.2 | 3.2.2.12
OCB EQP -1 | EX NOTM RS B-08.020 |  |  |  | Nonlabor | 2.5 | 0 | 0 | 3.1.1.1
OCB EQP -9 | EX NOTM RS B-08.020 |  |  |  | Nonlabor | 4.4 | 0 | 0 | 3.1.1.1
OCB EQP -1 | EX NOTM RS B-08.030 |  |  |  | Nonlabor | 247.36 | 244.34 | 0 | 3.1.1.2
OCB EQP -2 | EX NOTM RS B-08.030 |  |  |  | Nonlabor | 123.68 | 122.17 | 0 | 3.1.1.2
OCB EQP -3 | EX NOTM RS B-08.030 |  |  |  | Nonlabor | 123.68 | 122.17 | 0 | 3.1.1.2
OCB EQP -4 | EX NOTM RS B-08.030 |  |  |  | Nonlabor | 247.36 | 244.34 | 0 | 3.1.1.2
OCB EQP -9 | EX NOTM RS B-08.030 |  |  |  | Nonlabor | 1030.6667 | 1018.0833 | 0 | 3.1.1.2
OCB EQP -12 | EX NOTM RS B-08.030 |  |  |  | Nonlabor | 247.36 | 244.34 | 0 | 3.1.1.2
OCB EQP -1 | EX NOTM RS B-08.040 |  |  |  | Nonlabor | 166.8 | 0 | 166.8 | 3.1.1.3
OCB EQP -2 | EX NOTM RS B-08.040 |  |  |  | Nonlabor | 83.4 | 0 | 83.4 | 3.1.1.3
OCB EQP -3 | EX NOTM RS B-08.040 |  |  |  | Nonlabor | 83.4 | 0 | 83.4 | 3.1.1.3
OCB EQP -4 | EX NOTM RS B-08.040 |  |  |  | Nonlabor | 166.8 | 0 | 166.8 | 3.1.1.3
OCB EQP -9 | EX NOTM RS B-08.040 |  |  |  | Nonlabor | 695 | 0 | 695 | 3.1.1.3
OCB EQP -12 | EX NOTM RS B-08.040 |  |  |  | Nonlabor | 166.8 | 0 | 166.8 | 3.1.1.3
OCB EQP - 21 | EXE RE A-06.112 |  |  |  | Nonlabor | 30 | 0 | 30 | 3.2.2.13
OCB EQP - 20 | EXE RE A-06.112 |  |  |  | Nonlabor | 2 | 0 | 2 | 3.2.2.13
OCB EQP -15 | EXE RE A-06.112 |  |  |  | Nonlabor | 48 | 0 | 48 | 3.2.2.13
OCB EQP - 21 | EXE RE A-07.112 |  |  |  | Nonlabor | 16.25 | 0 | 16.25 | 3.2.2.13
OCB EQP - 20 | EXE RE A-07.112 |  |  |  | Nonlabor | 1.0833 | 0 | 1.0833 | 3.2.2.13
OCB EQP -15 | EXE RE A-07.112 |  |  |  | Nonlabor | 26 | 0 | 26 | 3.2.2.13
OCB EQP -1 | EX NOTM RS C-08.020 |  |  |  | Nonlabor | 2.5 | 0 | 2.5 | 3.1.1.1
OCB EQP -9 | EX NOTM RS C-08.020 |  |  |  | Nonlabor | 4.4 | 0 | 4.4 | 3.1.1.1
OCB EQP -1 | EX NOTM RS C-08.030 |  |  |  | Nonlabor | 25.18 | 0 | 25.18 | 3.2.2.5
OCB EQP -2 | EX NOTM RS C-08.030 |  |  |  | Nonlabor | 12.59 | 0 | 12.59 | 3.2.2.5
OCB EQP -3 | EX NOTM RS C-08.030 |  |  |  | Nonlabor | 12.59 | 0 | 12.59 | 3.2.2.5
OCB EQP -4 | EX NOTM RS C-08.030 |  |  |  | Nonlabor | 25.18 | 0 | 25.18 | 3.2.2.5
OCB EQP -9 | EX NOTM RS C-08.030 |  |  |  | Nonlabor | 104.9167 | 0 | 104.9167 | 3.2.2.5
OCB EQP -12 | EX NOTM RS C-08.030 |  |  |  | Nonlabor | 25.18 | 0 | 25.18 | 3.2.2.5
OCB EQP -1 | EX NOTM RS C-08.040 |  |  |  | Nonlabor | 1 | 0 | 1 | 3.2.2.6
OCB EQP -2 | EX NOTM RS C-08.040 |  |  |  | Nonlabor | 0.5 | 0 | 0.5 | 3.2.2.6
OCB EQP -3 | EX NOTM RS C-08.040 |  |  |  | Nonlabor | 0.5 | 0 | 0.5 | 3.2.2.6
OCB EQP -4 | EX NOTM RS C-08.040 |  |  |  | Nonlabor | 1 | 0 | 1 | 3.2.2.6
OCB EQP -9 | EX NOTM RS C-08.040 |  |  |  | Nonlabor | 4.1667 | 0 | 4.1667 | 3.2.2.6
OCB EQP -12 | EX NOTM RS C-08.040 |  |  |  | Nonlabor | 1 | 0 | 1 | 3.2.2.6
OCB EQP -1 | EXE RE A-05.015 |  |  |  | Nonlabor | 750 | 749.625 | 0 | 3.1.1.1a
OCB EQP -9 | EXE RE A-05.015 |  |  |  | Nonlabor | 1320 | 1319.34 | 0 | 3.1.1.1a
OCB EQP -1 | EXE RE A-06.015 |  |  |  | Nonlabor | 491.95 | 429.9 | 0 | 3.1.1.1a
OCB EQP -9 | EXE RE A-06.015 |  |  |  | Nonlabor | 865.832 | 756.624 | 0 | 3.1.1.1a
OCB EQP -1 | EXE RE A-07.015 |  |  |  | Nonlabor | 133.125 | 133.15 | 0 | 3.1.1.1a
OCB EQP -9 | EXE RE A-07.015 |  |  |  | Nonlabor | 234.3 | 234.344 | 0 | 3.1.1.1a
OCB EQP -11 | EXE RE A-05.116 |  |  |  | Nonlabor | 0.75 | 0 | 0.75 | 3.2.2.15a
OCB EQP -11 | EXE RE A-06.115 |  |  |  | Nonlabor | 0.84375 | 0 | 0.84375 | 3.2.2.15a
OCB EQP -11 | EXE RE A-06.116 |  |  |  | Nonlabor | 0.5625 | 0 | 0.5625 | 3.2.2.15b
OCB EQP -11 | EXE RE A-07.115 |  |  |  | Nonlabor | 0.76875 | 0 | 0.76875 | 3.2.2.15a
OCB EQP - 21 | EX NOTM RS C-08.071 |  |  |  | Nonlabor | 7 | 0 | 7 | 3.2.12.6c
OCB EQP - 20 | EX NOTM RS C-08.071 |  |  |  | Nonlabor | 0.46667 | 0 | 0.46667 | 3.2.12.6c
OCB EQP -15 | EX NOTM RS C-08.071 |  |  |  | Nonlabor | 11.2 | 0 | 11.2 | 3.2.12.6c
OCB EQP - 21 | EXE RS A-08.107 |  |  |  | Nonlabor | 111.5 | 70.25 | 0 | 3.2.12.6a
OCB EQP - 20 | EXE RS A-08.107 |  |  |  | Nonlabor | 7.4333 | 4.6833 | 0 | 3.2.12.6a
OCB EQP -15 | EXE RS A-08.107 |  |  |  | Nonlabor | 178.4 | 112.4 | 0 | 3.2.12.6a
OCB EQP - 21 | EXE RS A-08.108 |  |  |  | Nonlabor | 107 | 107 | 0 | 3.2.12.7a
OCB EQP - 20 | EXE RS A-08.108 |  |  |  | Nonlabor | 7.1333 | 7.1333 | 0 | 3.2.12.7a
OCB EQP -15 | EXE RS A-08.108 |  |  |  | Nonlabor | 171.2 | 171.2 | 0 | 3.2.12.7a